THE REPUBLIC OF UGANDA

KIBAALE DISTRICT LOCAL GOVERNMENT

FOURTH FIVE YEAR LOCAL GOVERNMENT DEVELOPMENT PLAN

(2025/2026 TO 2029/2030)

### DISTRICT VISION:

### A PROSPEROUS POPULATION WITH A GOOD STANDARD OF LIVING AND FUNCTIONAL SKILLS FOR SUSTAINABLE DEVELOPMENT.

THEME:

SUSTAINABLE INDUSTRIALIZATION FOR INCLUSIVE GROWTH, EMPLOYMENT AND WEALTH CREATION

January 2025

# Map of Uganda showing the Location of Kibaale District

# Map of Kibaale District

## The District Vision

A prosperous population with a good standard of living and functional skills for sustainable development.

The District Mission

To serve the community through coordinated delivery of services focussing on National priorities and significant local needs in order to accelerate sustainable development in the District.

## The District Core Values

- Effectiveness: We shall achieve the intended results in terms of quality and quantity in accordance with targets and performance standards set for service delivery.

- Efficiency: We shall optimally use resources, including time, in the attainment of our objectives.

- Impartiality: In carrying out our work, we shall give fair treatment to all customers irrespective of sex, race, region, ability, ethnic background or political affiliation.

- Transparency: We shall be as open as possible about all the decisions and actions taken.

- Professionalism: We shall adhere to the code of conduct and ethics, high degree of competence and best practices.

- Accountability: We shall hold office in public trust and shall be responsible for our actions or inactions

- Responsiveness: We shall attend to our clients’ issues, suggestions, requests and criticisms in a timely manner.

- Integrity: We shall be honest and open in conducting public affairs

- Selfishness: We shall put public interest before personal interests. We shall not take decisions in order to gain personal, financial and other benefits.

- Partnership: We shall engage our partners including MDAs, other HLGs, LLGs, Development Partners, Civil Society and Private sector in designing, implementing, monitoring and evaluating our programmes.

- Decency: We shall present ourselves in a respectable manner that generally conforms to morally acceptance standards and values of society.

- Diligence: We shall be hardworking and careful in carrying out our official duties

- Discipline: We shall behave in a manner as to confirm with the rules, regulations, code of conduct and ethics for the public service generally and code of professional conduct for specific professions

- Loyalty: We shall be committed to policies and programmes of the Government

# Foreword

The Local Governments Act, CAP 243 devolves planning powers to Local Councils in their areas of jurisdiction. The Act was amended to include Subsection 35(4) which states that “The planning period for Local Governments shall be the same as that of the Central Government”.  It is in accordance with these statutory requirements that this Fourth Five Year Local Government Development Plan was approved by the District Council on ……….. vide Minute ……………..

The District vision is “a prosperous population with a good standard of living and functional skills for sustainable development” and will be achieved through coordinated delivery of services focusing on National priorities and significant local needs in order to accelerate sustainable development in the District. In line with the Fourth National Development Plan, the theme of this plan is “Sustainable Industrialization for inclusive Growth, Employment and Wealth Creation”.

Since the creation of the District in March 1991, tremendous development has been realized. However, there is a set of the most binding constraints that still undermine development in the district namely; low agricultural production, productivity and limited access to markets, high population growth rate, degradation of natural resources, negative cultural perceptions and gender imbalances and a weak private sector. These constraints, interalia, present the need for coherent and poverty focused approaches to planning that will address the felt needs of the people in the district in an effective and efficient manner.

During the plan period, the key priority Programmes of the district will be; Human Capital Development (through provision of Health, Education and Community Based services), Agro- Industrialisation, Public Sector Transformation and Integrated Transport Infrastructure and services among others.

In view of promoting Local Economic Development, the plan implementation modality will involve a quasi market approach which includes a mix of government investments in strategic areas and private sector market driven actions. The Private sector will remain the engine of growth and development, while the Local Government, in addition to undertaking the facilitating role will also actively promote and encourage Public – private partnerships in a rational manner. The District will also pursue outward oriented policies by encouraging investors from outside the district on top of promoting investors within the district.

In order to fast track the set objectives, I call upon the central Government, Development Partners, Civil Society Organisations, cultural institutions, Faith Based Organisations, the private sector and the entire district community to adopt a “business approach” in the implementation of this Plan. This approach will require all stakeholders to adjust to the perception of the district as a “corporate” or a “business entity”, jointly owned by all stakeholders and working in tandem in pursuit of a common vision.

This Development plan has got in-built mechanisms for sustainability of the existing projects and the investments to accrue from the plan. I strongly reiterate our commitment towards operation and maintenance of the projects therein so as to benefit the current and future generations.

The District leadership is committed to regular monitoring of the implementation of the plan within the Framework for promotion of good governance and anti - corruption. The lessons learned from the monitoring and evaluation activities shall be translated into improved performance of the Plan as we steadily progress towards realization of our vision.

Muhonge Godfrey Kasanga

DISTRICT CHAIRPERSON

# Acknowledgement

By and large, this Fourth Five Year Local Government Development Plan is a product of concerted efforts of several stakeholders at various levels.

I owe special tribute to the Ministry of Finance, Planning and Economic Development and National Planning Authority for providing the Planning Call Circular, Planning Guidelines and immense technical support that facilitated the process for formulation of the Five year Local Government Development Plan. Indeed, the aforementioned support eased what had appeared to be a much complex mandate.

I applaud the input and participation of Lower Local Governments right from the village level, Civil Society Organizations and other Development partners who made significant contribution during the plan formulation process.

I appreciate the enormous contribution made by the District Technical Planning Committee, the Standing Committees, the District Executive Committee and the District Council during the plan formulation process.  Indeed the team spirit exhibited by the aforementioned organs of council eased what ought to have been a complex process.

I am also greatly indebted to those stakeholders who participated in the District Planning Conference whose input fed into this Local Government Development Plan.

I appreciate the commitment of the District Planning Department for amalgamating the views from the various consultative processes into this plan and for backstopping Lower Local Governments through the Plan formulation process.

Finally, I thank all those stakeholders whose support was less direct but no less significant during the formulation process of this Plan. Together, we can.

Katotoroma John

CHIEF ADMINISTRATIVE OFFICER

Table of Contents

Foreword	iii

Acknowledgement	iv

Table of Contents	v

List of Tables	vii

EXECUTIVE SUMMARY	x

CHAPTER 1: INTRODUCTION	13

1.1 Background and Development Context	13

1.2 Key achievements from the previous Plan	13

1.3 Key outstanding development issues/challenges	16

1.4 Key lessons learnt from implementation of the previous Plan	17

1.5 Formulation Process and Approach	18

1.6 Structure of Plan	19

CHAPTER 2: SITUATION ANALYSIS	20

2.1 Geographical Location, Land Area and Population	20

2.1.1 Geographical Location and Land Area	20

2.1.2 Population	20

2.2 Potentials, Opportunities, Constraints and Challenges (POCC) Analysis	22

2.2.1 Potentials	22

2.2.2 Opportunities	22

2.2.3 Constraints	22

2.2.4 Challenges	23

2.3	Economic Infrastructure and services	23

2.3.1 Transport and Connectivity	23

2.3.2 Energy	23

2.3.3 Urbanization, Housing and Physical Planning	23

2.3.4 Information Communication Technology	24

2.3.5 Water for Production	24

2.3.6 Commerce	24

2.3.7 Industry	24

2.3.8 Cooperatives	25

2.3.9 Financial Services	25

2.4	Socio-Economic Situation	25

2.4.1 Life Expectancy	25

2.4.2 Poverty level	25

2.4.3 Literacy Rate	25

2.4.4 Local Economy Analysis	26

2.4.5 Livelihood patterns	26

2.4.6 Human Settlement Patterns	26

2.4.7 Productive Resources and Economic Activities	26

2.5	Social infrastructure and services	27

2.5.1 Health	27

2.5.2 Education	27

2.5.3 Water	28

2.5.4 Social Protection	28

2.5.6 Community Development	28

2.6	Environment Situation	29

2.6.1 Climate	29

2.6.2 Vegetation	29

2.6.3 Wetlands	30

2.6.4 Soils	30

2.6.5 Topography	31

2.7 Local Governance and Administration	31

2.8	Synthesis of development issues	31

CHAPTER THREE: LGDP STRATEGIC DIRECTION AND PLAN	33

3.1 District Vision and Mission	33

3.1.1 The District Vision	33

3.1.2 The District Mission	33

3.2 Summary of adopted NDPIV Strategic Direction and Strategies	33

3.2.1 The District Goal	33

3.2.2 Strategic objectives of the Plan	33

3.2.3  Programmes	33

3.2.4	Strategies	33

3.3 Key Development Results	34

3.4	Summary of Programme Results and Targets	38

CHAPTER FOUR: FINANCING FRAMEWORK AND RESOURCE MOBILISATION STRATEGY	93

4.1 Financing Framework	93

4.2 Costs of the Plan Period (2025/26-2029/30)	94

4.2.1 Cost Implementation Matrix	94

4.2.2  Projected allocation of funds to Programmes	94

4.2.3 Projected Funding Gap of the Plan	95

4.3 Resource mobilisation strategy	95

4.3.1 The Strategies for Resource Mobilisation	95

4.3.2. Roles and Responsibilities of various actors in Financing of the Plan	95

CHAPTER FIVE: INSTITUTIONAL ARRANGEMENTS FOR IMPLEMENTING THE PLAN	97

5.1 Implementation Arrangements	97

5.2	Institutional  Arrangements	97

5.3 Coordination and Partnerships Framework	99

5.4	Pre-Requisites for Successful Implementation of the Plan	100

5.5 Conditions for successful implementation	100

CHAPTER SIX: COMMUNICATION AND FEEDBACK STRATEGY	101

6.1 Communication Strategy	101

6.2 Feedback Mechanism	102

CHAPTER SEVEN: RISK MANAGEMENT AND MITIGATION	104

7.1 Risk Management and Anticipated Impacts	104

CHAPTER EIGHT: MONITORING, EVALUATION AND LEARNING	106

8.1 Monitoring and Evaluation (M&E) Frameworks	106

8.2 Monitoring and Evaluation Roles and Responsibilities of Key Actors	106

8.3 Major Monitoring and Evaluation Events	108

# List of Tables

Table 1: Recent Achievements in the Key service outcomes	16

Table 2: Population by selected age groups	23

Table 3: Summary of LGDPIV Objectives and Strategies	37

Table 4: Targets for Key Development Results	38

Table 5: Financing Framework (“000”ushs)	96

Table 6: Projected allocation of funds to Programmes for the period 2025/26 to 2029/2030	97

Table 7: Roles of the different institutional structures in the Local Government	100

Table 8: Other key stakeholders/ central Government institutions and their key roles	101

Table 9: Key Envisaged Risks and mitigation measures	107

Table10: M&E Stakeholders and Reporting Frameworks	109

List of Acronyms/ Abbreviation

| ANC | Antenatal Care |
| --- | --- |
| ART | Anti-Retroviral Treatment |
| CAO | Chief Administrative Officer |
| CARs | Community Access Roads |
| CSOs | Civil Society Organisations |
| DCDO | District Community Development officer |
| DEC | District Executive Committee |
| DEO | District Education Officer |
| DHO | District Health Officer |
| DLB | District Land Board |
| DSC | District Service Commission |
| DTPC | District Technical Planning Committee |
| DUCAR | District Urban and Community access Roads |
| EMIS | Education Management Information System |
| ENR | Environment and Natural Resources |
| ESIA | Environmental and Social Impact Assessment |
| FAL | Functional Adult Literacy |
| FY | Financial Year |
| GBV | Gender Based Violence |
| GoU | Government of Uganda |
| GROW | Growth Opportunities for Women |
| Ha | Hectare |
| HLG | Higher Local Government |
| HMIS | Health Management Information System |
| ICL | Integrated Community Learning |
| ICT | Information Communication Technology |
| Km | Kilometre |
| LC | Local Council |
| LG | Local Government |
| LGDP | Local Government Development Plan |
| LGPAC | Local Government Public Accounts Committee |
| LLG | Lower Local Government |
| M&E | Monitoring and Evaluation |
| MAAIF | Ministry of Agriculture, animal Industry and Fisheries |
| MDAs | Ministries, Departments and Agencies |
| MoFPED | Ministry of Finance, Planning and Economic Development |
| MoH | Ministry of Health |
| MoICT | Ministry of Information Communication Technology |
| MoPS | Ministry of Public Service |
| MoWE | Ministry of Water and Environment |
| MOWT | Ministry of Works and Transport |
| MSMEs | Micro, Small and Medium Enterprises |
| NA | Not Applicable |
| NDPIV | Fourth National Development Plan |
| NGO | Non Governmental Organisation |
| NITA-U | National Information Technology Authority of Uganda |
| NPA | National Planning Authority |
| NTDs | Neglected Tropical Diseases |
| OPD | Out Patient Department |
| OPM | Office of Prime Minister |
| OVCs | Orphans and Vulnerable Children |
| PDM | Parish Development Model |
| PDU | Procurement and Disposal Unit |
| PHRO | Principal Human Resource Officer |
| PLE | Primary Leaving Examinations |
| PWDs | Persons with Disabilities |
| SACCOs | Savings and Credit Cooperative Organisations |
| SAGE | Social Action Grant for Empowerment |
| SOPs | Standard Operating Procedures |
| TB | Tuberculosis |
| UBOS | Uganda Bureau of Statistics |
| UCC | Uganda Communications Commission |
| UDHS | Uganda Demographic and Health Survey |
| UGIFT | Uganda Intergovernmental Funds Transfer |
| UIA | Uganda Investment Authority |
| UNEB | Uganda Examinations Board |
| UPE | Universal Primary Education |
| URSB | Uganda Registration Services Bureau |
| USE | Universal Secondary Education |
| UWEP | Uganda Women Entrepreneurship Programme |
| VHT | Village Health Team |
| YLP | Youth Livelihood Programme |

# EXECUTIVE SUMMARY

This Fourth Five Year Local Government Development Plan was prepared in line with the requirements of Article 190 of The Constitution of the Republic of Uganda, 1995 (as amended) and section 35 of The Local Governments Act CAP 243 which provide for decentralized planning. The Plan has also been formulated within the context of the Comprehensive National Development Planning Framework, 2007 which provides a holistic framework for a coherent system of national development planning where short term interventions and activities are guided by long term development aspirations and objectives. The Plan is anchored by the Uganda Vision 2040 and the Fourth National Development Plan (NDPIV) for the period 2025/2026 to 2029/2030. The theme of this plan is “Sustainable Industrialisation for inclusive growth, Employment and Wealth Creation”.

## Development Goal, Objectives and Strategies

### The District Vision

A prosperous population with a good standard of living and functional skills for sustainable development.

### The District Mission

To serve the community through coordinated delivery of services focussing on National priorities and significant local needs in order to accelerate sustainable development in the District.

### The District Goal

In line with the goal for the NDP1V, the district goal is to achieve higher household incomes and employment for sustainable socio-economic transformation.

Strategic objectives of the Plan

In line with the NDPIV, the strategic objectives of the LGDP 1V are to;

- Sustainably increase production, productivity and value addition in agriculture, minerals, oil & gas, tourism, ICT and financial services.

- Enhance human capital development along the entire life cycle.

- Support the private sector to drive growth and create jobs.

- Build and maintain strategic sustainable infrastructure in transport, housing, energy water, industry and ICT.

## Strengthen good governance, security, and the role of the state in development.

## Targets for Key Development Results

- To reduce the percentage of Population below the poverty line from 9.8% to 7.0% by June 2030.

- To reduce the percentage of Household Population in subsistence economy from 27.0% to 22.0% by June 2030.

- To increase the Annual growth of marketed agricultural output from 79% to 88% by June 2030.

- To increase the Annual growth of farmer organization membership from 15% to 29% by June 2030.

- To increase the Annual growth of registered farmer contacts with extension staff from 20% to 29% by June 2030.

- To increase the Percentage of labourforce employed in Tourism from 1% to 4% by June 2030

- To increase the District reforestation rate from 5% to 10% by June 2030

- To increase area of wetlands demarcated and restored from 54 to 100 hectares by June 2030

- To Increase Internet penetration rate (internet users per 100 people) from 15% to 47% by June 2030

- To increase in the percentage of Land disputes settled from 20% to 60% by June 2030

- To increase the annual growth rate of the local business register from 40% to 65% by June 2030

- To maintain the percentage reduction of annual biomas demand at 2% between 2025/2026 to 2029/2030

- To increase the percentage of permanent buildings with approved plans from 20% to 40% by June 2030

- To increase the percentage of Feeder roads in fair-to-good condition from 89.5% to 95% by June 2030

- To increase the percentage of access roads in fair-to-good condition from 24% to 38% by June 2030

- To increase the percentage of urban roads in fair-to-good condition from 45% to 60% by June 2030

- To increase the Life expectancy at birth from 68.2 to 73 years by June 2030.

- To reduce the infant mortality rate from 42 deaths to 35 deaths per 1000 live births by June 2030.

- To reduce the Under five mortality rate from 60 deaths to 50 deaths per 1000 live births by June 2030.

- To increase the proportion of clients on ART with viral load suppression from 80 to 95 % by June 2030.

- To reduce the death rates associated with malaria from 4 to 2% by June 2030.

- To increase the proportion of TB cases detected and cured under DOTS from 84 to 95% by June 2030.

- To increase the proportion of deliveries conducted in government health facilities from 52 to 65% by June 2030.

- To increase the Literacy rate in primary education from 70 to 90% by June 2030.

- To increase the Numeracy rate in primary education from 68 to 90% by June 2030.

- To increase the Performance index in primary education from 92 to 96% by June 2030.

- To increase the Enrolment rate for primary education from 98.6 to 100% by June 2030.

- To increase the Enrolment rate for secondary education from 45.6 to 80% by June 2030.

- To increase the Performance index in secondary education from 96 to 100% by June 2030.

- To increase the completion rate in secondary education from 68 to 90% by June 2030.

- To increase the proportion of population within 1km of an improved water source from 70 to 75% by June 2030

- To increase the proportion of population with access to safe sanitation from 80 to 85% by June 2030

- To increase the percentage of population receiving direct income support from 0.04 to 0.06% by June 2030.

- To maintain the share of unqualified audit reports at 100% between 2025/2026 to 2029/2030.

- To increase the staffing level from 74 to 85% by June 2030.

- To increase the percentage of Local Revenue to the total District Budget from 2.3% to 3.4% by June 2030

- To increase the budget absorption rate from 91 to 93.2% by June 2030

- To increase the annual NDP compliance score from 65 to 75% by June 2030.

## LGDP IV Programmes

The District has prioritized the following 13 Programmes for the period 2025/2026 to 2029/2030:

- Agro-Industrialization;

- Tourism Development;

- Natural Resource, Environment, Climate Change, Land and Water Resources Management;

- Private Sector Development;

- Digital Transformation;

- Integrated Transport Infrastructure and Services;

- Sustainable Energy Development;

- Sustainable Urban and Housing Development;

- Human Capital Development;

- Governance and Security;

- Public Sector Transformation;

- Development Plan Implementation; and

- Legislature, Oversight and Representation

Projected Resource Envelope for the Plan

The Total Projected Resource Envelope for the Development Plan is Ushs 194,735,486,000 of which Ushs 173,370,406,000 is projected to be through the District Budget (on-budget) while Ushs 21,365,080,000 is planned to be off-budget contribution from the Development Partners, Civil Society Organisations and the Private Sector. Of the projected on-budget revenue, 97.4% is expected to be received from Central Government Transfers while local revenue and External Financing are expected to contribute 2.1% and 0.5% respectively. Thus, the district will by and large depend on central Government transfers.

# Summary of Projected Allocation of Funds to Programmes and Funding Gap

# The projected resource Envelope for the District Development Plan has been allocated to 13 Programmes adopted from NDP1V. Of the 13 adopted Programmes, the most important programmes for the District over the five years will be Human Capital Development (including Education, Health and Community Based services); Agro-Industrialization; Public Sector Transformation and; Integrated Transport Infrastructure and Services.

The projected total funding gap for the plan stands Ushs 885,498,000. Most of this funding gap is in the priority programmes namely; Human Capital Development (including Education, Health and Community Based services); Public Sector Transformation; Integrated Transport Infrastructure and Services and, Agro-Industrialization.

Strategies to Finance, implement and coordinate the Plan

- Promoting agro-industrialization

- Harnessing the tourism potential

- Providing a suitable fiscal, monetary and regulatory environment for the private sector to invest

- Institutionalising infrastructure maintenance

- Increasing access to reliable & affordable energy

- Leveraging urbanization for socio-economic transformation

- Improving access and quality of social services

- Enhancing skills and vocational Development

- Increasing access to social protection

- Promoting development-oriented mind-set

- Increasing government. participation in strategic sectors

- Enhancing partnerships with non-state actors for effective service delivery

- Re-engineering Public service to promote investments and;

- Increasing Resource Mobilization

# CHAPTER 1: INTRODUCTION

## 1.1 Background and Development Context

This Plan has been prepared in line with the requirements of Article 190 of The Constitution of the Republic of Uganda, 1995 (as amended) and section 35 of The Local Governments Act CAP 243 which provide for decentralized planning. The Plan has also been formulated within the context of the Comprehensive National Development Planning Framework, 2007 which provides a holistic framework for a coherent system of national development planning where short term interventions and activities are guided by long term development aspirations and objectives. The Plan has also been prepared within the context of vision 2040 and NDPIV for the period 2025/2026 to 2029/2030.

## 1.2 Key achievements from the previous Plan

Kibaale District was created in 1991 being curved out of Hoima District. During the previous Plan, the District has registered several achievements in the Key service outcomes as per Table 1 below:

# Table 1: Recent Achievements in the Key service outcomes

| Service Outcomes | Service Outcome Indicators | Status FY 2020/21 | Status FY 2021/22 | Status FY 2022/23 | Status FY 2023/24 | Status FY 2024/25 |
| --- | --- | --- | --- | --- | --- | --- |
| Rural water supply | % Of people within 1,000 m of an improved water source | 60 | 65 | 68 | 70 | 71 |
|  | % of rural water point source functional | 80 | 84 | 80 | 82 | 83 |
| Public health and safety | Access to safe sanitation [%] | 18 | 20 | 22 | 25 | 80 |
|  | Proportion of water sources tested for quality [%] | 20 | 20 | 20 | 20 | 20 |
|  | % of people with access to improved sanitation | 24.5 | 26.1 | 28.1 | 32 | 34 |
|  | Pupil to latrine/toilet stance ratio | 1:41 | 1:41 | 1:44 | 1:44 | 1:53 |
| Water resource management | % of water samples taken at the point of water collection, water discharge point that comply with national standards (Protected Rural Sources) | 20 | 20 | 20 | 20 | 20 |
| Primary education | Numeracy rate [%] | 67.1 | 67.3 | 69.3 | 68 | 68 |
|  | Literacy rate [%] | 58 | 61.2 | 62.3 | 70 | 70 |
|  | Enrolment rate [%] | 90.2 | 91 | 92.4 | 97.1 | 98.6 |
|  | Performance index [%] | 87.6 | 87.6 | 93.3 | 91 | 91 |
|  | Completion rate [%] | 51.2 | 53.1 | 55.3 | 69.9 | 69.9 |
| Secondary education | Proficiency scores (Proportion of students passing ‘O’ level) | 91 | 91 | 95 | 96 | 96 |
|  | Enrolment rate | 52.1 | 52.1 | 52.1 | 51.4 | 45.6 |
|  | Performance index | 91 | 91 | 95 | 96 | 96 |
|  | Completion rate [%] | 56 | 56 | 57 | 65 | 68 |
| Primary Health | OPD Utilization [%] | 55 | 56 | 58 | 59 | 60 |
|  | Diptheria Immunization coverage [%] | 88 | 90 | 94 | 86 | 89 |
|  | Proportion of villages with functional VHTs | 100 | 100 | 100 | 100 | 100 |
|  | Share of admissions successfully discharged | 99.2 | 99.5 | 99 | 99 | 99 |
| Epidemic Control (HIV/AIDS, Malaria & TB Services) | Share of population aged 15-24 years with comprehensive correct knowledge of HIV/AIDS | 8 | 10 | 45 | 53 | 55 |
|  | Share of population with advanced HIV infection with access to ARV drugs | 70 | 80 | 90 | 100 | 100 |
|  | Incidence and death rates associated with malaria | 24,467 | 25,467 | 35,927 | 18,869 | 17,653 |
|  |  | 21 | 13 | 9 | 5 | 4 |
|  | Proportion of TB cases detected and cured under DOTS | 122 | 144 | 185 | 246 | 370 |
|  |  | 63 | 68 | 70 | 73 | 84 |
| Maternal Health | Proportion of deliveries conducted in government health facilities | 48 | 51 | 52 | 53 | 54 |
|  | Average number of ANC visits | 29,671 | 28,705 | 29,375 | 30,046 | 31,706 |
| Reliable District Road network | Share of District roads in fair-to-good condition [%] | 50 | 50 | 75 | 80 | 80 |
|  | Share of community access roads in fair-to-good condition [%] | 15 | 17 | 18 | 20 | 23 |
|  | Share of Urban access roads in fair-to-good condition [%] | 20 | 23 | 25 | 25 | 26 |
| Agricultural Production | Annual growth of marketed agricultural output [%] | 68 | 71 | 73 | 78 | 79 |
|  | Annual growth of farmer organization membership [%] | 5 | 6 | 9 | 10 | 15 |
|  | Annual growth of registered farmer contacts with extension staff [%] | 10 | 12 | 15 | 17 | 20 |
| Enterprise Creation and Growth | Annual growth rate of the local business register [%] | 10 | 20 | 30 | 40 | 40 |
| Revenue generation | Share of locally generated revenue [%] | 1.7 | 0.8 | 1.8 | 2.2 | 2.2 |
|  | Budget absorption rate [%] | 89 | 87 | 91 | 91 |  |
| NDP compliant Plans & Budgets | Annual NDP compliance score [%] | 59.4 | No data | No data | No data | No data |
| Auditing | Share of unqualified audit reports [%] | 100 | 100 | 100 | 100 | 0 |
| Community Empowerment | Adult literacy rate [%] | 60 | 60 | 60 | 60 | 60 |
|  | Share of orphaned children [%] | 6.12 | 6.12 | 6.12 | 6.11 | 6.11 |
|  | Shared of population with disabilities [%] | 5.3 | 5.3 | 5.3 | 5.2 | 5.2 |
|  | Annual reported cases of child abuse [%] | 2.1 | 2.2 | 2.4 | 2.5 | 2.51 |
|  | Annual change in reported cases of domestic violence [%] | 9.5 | 9.6 | 9.7 | 9.6 | 9.65 |
| Good Governance | Annual change in the implementation gap of district resolution [%] | 100 | 100 | 100 | 100 | 100 |
|  | Annual growth of approved construction plans [%] | 0 | 0 | 0 | 0 | 0 |
| Staff Capacity | Share of LG establishment staffed [%] | 98 | 98 | 99 | 99 | 74 |
| Natural Resources Management | District reforestation rate [%] | 60 | 60 | 60 | 60 | 60 |
|  | Area (ha) of wetlands demarcated and restored | 11 | 11 | 11 | 54 | 60 |
|  | Proportion of Wetland Action Plans and regulations developed [%] | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 |
|  | Share of licensed polluters | 11 | 11 | 11 | 11 | 11 |
|  | Share of licensed water abstraction points [%] | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 |

## 1.3 Key outstanding development issues/challenges

- Low agricultural production and productivity: Subsistence agriculture is the major economic activity in the district employing 81% of the District labourforce. This is characterized by use of poor methods of farming and low levels of production and productivity. Low agricultural production and productivity is also due to pests and diseases and effects of climate change. This problem is exacerbated by the low levels of value addition for agricultural production in the district. The problem amounts to low income among the population and undermines the efforts for wealth creation in the district.

- Low quantity and quality of social services:  The service delivery indicators especially in Health, Education and water are still low in terms of quantity and quality. This is due to a multiplicity of service delivery constraints mainly caused by inadequate funding. The low service delivery indicators undermine the fight against poverty in the district.

- Poorly maintained road network: It is difficult to properly maintain the feeder road network in the district owing to the inadequate funding for road maintenance from the Central Government. More so, there are some areas that are poorly served especially Kyakazihire Sub county which requires affirmative action in this plan. The poor state of community access roads across the district is mainly due to low community participation in self help community Development activities.

- Inadequacies in the Governance and oversight function: The Governance and oversight function is faced with a set of challenges that hinder its effectivesness and efficiency. These include; inadequate funding for Council, Boards and Commissions, inadequate capacity of Councillors especially at LLGs and limited opportunities for exposure of councillors through study visits among others.

- Inadequacies in Public Sector Management: Public Sector Management has got a number of challenges that hamper its effecitiveness and efficiency. These include; inadequate facilitation of staff, limited opportunities for capacity Building of staff, inadequate means of transport for staff, lack of office accommodation especially at Lower Local Governments and inadequate office equipment among others.

- Slow implementation of the Development Plan: Development Plan implementation is faced with various challenges which hinder achievement of the set targets. The challenges include; low local revenue mobilsation, inadequate alignment of annual workplans to the Development Plan, weak LLG Technical Planning committees, non existent Parish Development committees coupled with inadequate capacity for monitoring and evaluation of the Development plan at the District and Lower Local Governments.

- High population growth rate: According to the 2024 Population and Housing Census, the district has got one of the highest population growth rates in the country standing at 5.9% per annum. This is caused by an influx of people from other areas in search of arable land and the high fertility rate of 6.0 children per woman (UBOS Census 2024; UDHS, 2021). The population growth rate is far above the rate of investment in service provision like water, Health, education, etc. More so, the population structure of the district is dominated by a young population with children below 18 years constituting about 57%. Such a structure undermines production and has worsened the dependency burden in the district. The percentage of population in subsistence economy is still high at 27.0% (UBOS Census 2024) although the percentage of poor peoplein the District has declined from 31.9% in 2021 (The Uganda Poverty Status Report 2021). This partly explains the low quality of population which cannot acceralate socio-economic transformation.

- Degradation of natural resources: Owing to the high population growth rate in the district, there is high degradation of natural resources especially forests on private land. The high rate of deforestation is mainly due to the need for arable land. This partly explains the micro climatic changes in the district leading to low agricultural production and productivity.

- Poor use of renewable energy: The energy situation in the district is that more than 95% of the Population uses biomass as their primary energy source for cooking, lighting and warming. For the rural communities, the use of firewood is almost 100%. The situation is worsened by the rudimental methods which are wasteful and also a health hazard considering the carbon emissions.

- Limited participation of marginalized groups in income generating projects: The number of beneficiaries from the ongoing community empowerment programmes is still very low owing to inadequate funding. The programmes are UWEP, YLP, SAGE and Special Programme for Persons with Disabilities.

- Gender imbalances: There are gender imbalances especially in production and social services which retard development in the district. For instance, gender imbalances in agricultural production are characterized by dominance of women and children in the downstream stages of production like tilling of land, planting, weeding and harvesting. Men are more involved in the upsteam stages of production like value addition and marketing and therefore control the proceeds from agriculture which is a disincentive to agricultural production among women. Such gender imbalances are mainly due to poor mindset and negative social and cultural beliefs.

- Limited use of Information Communication Technology: The utilization of ICT services in the district is still low due to limited network coverage, high cost of end user devices and services, inadequate ICT knowledge and skills, and limited innovation capacity. For instance, use of computers is mainly in institutions and especially used for less sophiscated work. There is need to boost use of ICTs for development e.g. through increased use of internet services for Business Process outsourcing, research and innovation.

- Weak and uncompetitive private Sector: The district has got a weak private sector characterized by weak coordination structures, low skills and inadequate capital outlay. This retards the capacity of the private sector to contribute towards the development of the district through Public Private Partnership.

- Low levels of Tourism Development in the District: There is low tourism development in the district. Most of the tourist attractions are not yet developed. These include; Kagombe Central Forest Reserve, several cultural sites (Egasani) which were burial grounds for Bunyoro Kings and St. Kirigwaijo martyrs shrine in Bubango subcounty among others. More so, the hospitality industry is not properly developed due to limited capital outlay and inadequate skills among the private sector. Development of the tourism potential in the district requires a concerted effort between the the Local Government and the Private Sector.

- Unplanned Rural Growth centres:  All upcoming Rural Growth centres in the district do not have approved physical plans. This is a disincentive to developers and has led to difficulties of zoning developments in these trading centres. It has also led to emergency of shunty Rural Growth centres. There is need for physical planning of these centres before more developments emerge in order to have organised developments and plan for future expansion of these centres.

## 1.4 Key lessons learnt from implementation of the previous Plan

Based on the review of the performance of the previous Plan, a number of major lessons have been considered while developing LGDPIV. These are:

- Improving staffing levels at the District and Lower Local Governments is a necessary but not a sufficient condition for improving performance of these levels. Improving the performance of the District and Lower Local Governments also calls for capacity building, improved facilitation, political support, retooling, implementing rewards and sanctions among others. These ingredients have been integrated into LGDP 1V.

- The performance of the one department largely depends on the performance of other departments. Therefore, there is need to break down the silo approach to planning, budgeting and implementation. Under LGDPIV, the programme-based approach to planning will be deepened. A total of 13 programmes have been designed to address the identified development challenges inhibiting growth. These programmes address the different aspects of an identified development challenge along the value chain and life cycle in a systematic and comprehensive manner.

- There are various Legal and Policy reforms from the centre that are being implemented at the Local Government levels. Coupled with the changing technological environment, there is need for continuous capacity building of staff at all levels of Local Government.

- The dwindling Local Revenue affects implementation of local priorities that are not funded by the Central Government or External Financing such as construction of administration blocks at sub county level. This plan intends to boost local revenue mobilization through non traditional sources like revitalizing income generating projects for the district namely; Kibaale Hotel, Kibaale Guest House among others.

- Regular communication and feedback with various stakeholders at the District and Lower Local Governments is key for improved coordination and implementation of development programmes and projects. This area is planned to be strengthened during LGDP 1V implementation.

- Continuous harmonization of interventions of the various CSOs operating in the District is essential for avoiding duplication of efforts of different players.

- In terms of spatial distribution of the CSOs and the private sector operating in the district, there is un even distribution. Thus, some sub counties like Bubango, Kasimbi, Karama and Nyamarwa are under served by the CSOs while other Lower Local Governments have got several CSOs. There is need to encourage CSOs to venture into relatively underserved Lower Local Governments.

- The level of private investment in the district is still below the optimal capacity of the district in terms resource endowment, market potential and the available quantity and quality of public utilities like electricity, roads, safe water among others. Therefore, there is need for the district leadership and other stakeholders at the various levels to attract local, National and Foreign investment into the district.

- Capacity building of farmers before delivery and distribution of improved technologies enhances survival rates of the inputs distributed to farmers.

- Timely delivery and distribution of improved agricultural technologies ensures optimal utilization of the rainy season.

- Demonstration sites set up at farmer level enhances adoption of improved technologies and uptake of recommended husbandry practices

- Regular support supervision, Monitoring and evaluation are essential ingredients to improved implementation of development programmes/projects and service delivery.

- Continuous community awareness is a catalyst for community participation in development programmes/projects which promotes community ownership of these programmes/projects and improves their sustainability.

## 1.5 Formulation Process and Approach

The plan formulation process at the District and Lower Local Governments was rigorously consultative and widely participatory. It started with the Chief Administrative Officer issuing the Planning Planning Call Circular on 22nd July 2024 advising the District and Lower Local Governments to undertake the planning process. From 22nd to 23rd July 2024, there was training of trainers that constituted Higher Local Government planning teams, District Technical Planning Committee and the Lower Local Government planning teams. In this training, there was issuance of the necessary planning tools by Planning Department to the Departments and Lower Local Government. Thereafter, there was training of Lower Local Government Planning Teams and data collection at village level from the fourth week of July 2024 to the first week of August 2024.

This was followed by data collection which was conducted by the parish chiefs and ward agents at village level for water facilities and roads, at schools for education data, at health facilities for health data and desk based for production data in consultation with the agricultural extension workers. This process was conducted during the second week of August 2024.

Village meetings were held to obtain village proposals and were chaired by the LC1 Chairpersons with technical support from parish chiefs and ward agents during the third and fourth week of August 2024. Parish prioritization meetings were also held and chaired by the LC11 Chairpersons with technical support from parish chiefs or ward agents and the Lower Local Government Planning team during the first and second week of September 2024. More so, Sub Counties / Town council convened prioritization meetings conducted by the Lower Local Government Planning teams with support from the District Planning team during the third and fourth week of September 2024.

Further still, Sub Counties / Town Council convened Budget Conferences chaired by the Lower Local Government Chairpersons with technical support from the Lower Local Government Planning team and the District Planning team a process that took place during the first and second week of October 2024. By 21st October 2024, the Lower Local Government accounting officers had submitted Lower Local Government priorities for integration into the District Development Plan proposals.

Lower Local Governments started drafting their Lower Local Government Development Plans which they presented to their Technical Planning Committees before the end of November 2024.This was followed by presentation of the draft plans to the Lower Local Government Executive Committee by 6th December 2024 and laying of the Lower Local Government draft plans before Council by 20th December 2024. The draft plans were then forwarded to the Lower Local Government standing committees for scrutiny, a process that lasted up to ………...

By ……….., the Lower Local Government Draft Plans were approved by their respective Councils and thereafter, they embarked on editing, printing and dissemination of the approved Lower Local Government Plans including submission of hard and soft copies to the District by ………...

At the Distric level, Heads of Department drafted Chapter Two of the LGDP i.e situation analysis guided by the Planning Call Circular between August and September 2024. In October 2024, Heads of Department drafted Chapter Three of the LGDP i.e., LGDP Strategic Direction informed by the Planning Guidelines, situation analysis, NDPIV strategic direction and LLG priorities for the LGDP.The Planning technical team was available to provide support to Departments.

A two- day Planning retreat was organised by the District on 28th to 29th October 2024 to discuss the Departmental proposals for the LGDP and the consultative document for the Planning.The District Planning Conference was then organized at Kibaale District Headquarters on the 1st November 2024. The Conference attracted a broad spectrum of stakeholders including District Council Members, District Technical Planning Committee members, Lower Local Government representatives, representatives of Civil Society Organisations, the private sector, Cultural and Religious Leaders.The Conference yielded a wish list of development interventions that informed the formulation of the plan.

After the Planning conference, the second Planning Retreat was organised by the District on 21st to 22nd November 2024 to complete drafting the Plan and was attended by the District Technical Planning Committee (made up of Heads of Department and section plus representatives of the Civil Society). During this stage, Heads of department / section responsible for mainstreaming of crosscutting issues like Gender, Population and Development, HIV/AIDS, Environment provided technical support to the drafting committee and ensured that cross cutting issues had been integrated into all Programmes. The draft Plans were then discussed by the District Executive Committee for input on 10th December 2024.

The input of the District Executive Committee was then incorporated into the draft plans by the drafting committee. The Plan was laid before Council on 20th December 2024 and was referred to all Standing Committees for scruitiny. The Standing committees scrutinised the Plan in …… 2025 and presented their recommendations to the District Council meeting on ……. during which the plan was approved under Minute …………..

After approval, the drafting team edited the plan to incorporate resolutions by the District Council after which the plan was printed and disseminated to various stakeholders within the District and at the central Government level. During the entire formulation process, there was continuous technical support and guidance from the National Planning Authority.

## 1.6 Structure of Plan

The plan is prepared in eight chapters.  Chapter one covers the introduction including the background and Development Context, Key achievements from the previous Plan, Key lessons learnt, key outstanding development issues/challenges and the Plan Formulation Process and Approach. The second chapter presents the Situation Analysis of the District in terms of the various aspects such as physical, environmental, demographic, socio-economic, Governance and administrative dimensions among others. It also presents a synthesis of development issues affecting the district.

Chapter three presents the Strategic Direction of the Plan in terms of the Vision, Goal, Strategic Objectives and adopted Programmes. It also presents the LGDP Development Results and Targets aligned to the NDP IV. Chapter Four gives the Financing Framework and Resource Mobilisation strategy. This chapter indicates the projected Resource Envelope for the Plan from all sources and the allocation projections to the adopted Prgrammes.

Chapter Five covers the Institutional arrangements for implementing the plan including role of key stakeholders, coordination and partnership framework, and prerequisites and conditions for successful implementation of the Plan. Chapter six presents the communication and feedback strategy. Chapter seven covers Risk Management and mitigation measures while Chapter eight handles Monitoring, Evaluation and Learning.

The plan has got three appendices namely; Project Profiles, Results Framework and the Cost Implemention matrix.

# CHAPTER 2: SITUATION ANALYSIS

## 2.1 Geographical Location, Land Area and Population

### 2.1.1 Geographical Location and Land Area

Kibaale District is located in the Mid-Western part of Uganda. The District is bordered by Kagadi District to the West and the North, Kakumiro District and Mubende District to the East, Kyegegwa District and Kyenjojo District to the South; it is approximately 215 Kms from Kampala, the Capital City of Uganda. It covers a total area of approximately 1,170 sq. kms. It is approximately located between latitude 70o 00’N,115o 00’N and longitude 30o 50’E,31o 00’E.

### 2.1.2 Population

### 2.1.2 (a) Population size and Structure

According to the 2024 Census, the district has got a total population of 237,649 with 113,255 (47.7 percent) males and 124,394 (52.3 percent) females. According to the 2024 Census, the population of Kibaale grew at a rate of 5.9 percent per annum which was much higher than the National average of 2.9 percent. The high population growth rate can mainly be attributed to the high fertility rate of 6.0 children per woman which is higher than the national fertility rate of 4.5 children per woman (UBOS, Census 2024). More so, the continued influx of migrants from other parts of the Country contributes to high population growth in the District.

The Population of Kibaale District is predominantly young which presents a high dependency burden and the need to prioritise human capital development. For instance, 54.0% of the population is aged 0-17. The population age structure of the district is shown in Table … as follows:

# Table 2: Population by selected age groups

| S/No | Age group | Population size | Percentage to total Population |
| --- | --- | --- | --- |
| 1 | Children (0-17 years) | 128,436 | 54.0 |
| 2 | Adults (18 years and above) | 109,213 | 46.0 |
| 3 | Youths (15-24 years) | 45,385 | 19.1 |
| 4 | Youths (18-30 years) | 51,186 | 21.5 |
| 5 | Working age (14-64 years) | 124,722 | 52.5 |
| 6 | Older persons (60 or more years) | 8,998 | 3.8 |

Source: UBOS, Census 2024

### 2.1.2 (b) Population density

The Population density of Kibaale District is 203 persons per sq.km. The Population is however unevenly distributed with some Sub Counties having high population densities namely; Bwamiramira, Mugarama, Nyamarwa, Kabasekende and Kibaale Town Council. Increase in population density implies increased pressure on natural resources like land, forests, and public utilities within the area.

### 2.1.2 (c) Household size

Kibaale District has a total number of 55,887 Households (UBOS, Census 2024), giving an average size of 4.2 persons per household. Most families are extended in nature leading to economic pressure on the head of the household.

### 2.1.2 (d) Urbanization

The 2024 census defined urban areas to include gazetted cities, Municipalities, and town councils. For Kibaale district, only population from Kibaale and Nyamarunda Town Councils (….%) is considered as urban. However, there are a number of Rural Growth centres in the District namely, Kabasekende, Hakasalaba, Kitutu, Kikaada, Kasimbi, Imara, Kasansa, Hakabaale (Kyamugema), among others.

### 2.1.2 (e) Migration

According to 2024 census, … percent of the population in Kibaale district were migrants from other districts and other parts of the world and …. percent of them were from Kabale District, followed by Kabarole (…. percent) and Kisoro (….. percent) while ….% were Non Ugandans.

2.1.2 (f) Religious Composition

According to the 2024 census, the majority of the population in the District were Roman Catholic (….%) followed by Anglican / Church of Uganda (…%), Pentecostal / Evangelicals (…%), Islam (…%), Seventh Day Adventist (…%), Orthodox …%, Traditional …%, Jehovah's witness…%, Other religion…% and no religion (…%). The Faith of Unity led by Owobusobozi Bisaka was categorized as part of the other religions.

### 2.1.2 (g) Citizenship and Ethnicity

According to the 2024 census,  …. percent of the population is Kibaale were Ugandans. The majority of the people in Kibaale were Banyoro (…..%) followed by Bakiga (….%), Bafumbira (…%), Bakhonzo (….%), Banyankole (…%), Batoro (…%) and other Ugandans  (…%).

### 2.1.2 (h) Mortality

According to the 2024 census, infant mortality rate for Kibaale declined from 63 deaths per 1000 live births in 2016 to 42 deaths per 1000 live births in 2024 i.e. 44 for every 1,000 male children born alive and 39 for every 1,000 female children born alive. However, this is higher than the National average of 34 out of 1,000 (male: 37 per 1,000 live births; female: 30 per 1,000 live births).

The Under-5 mortality rate stands at 60 deaths per 1,000 live births i.e. 62 for every 1,000 male children born alive and 57 for every 1,000 female children born alive. However, this is higher than the National average of 46 out of 1,000 live births (male: 50 per 1,000 live births; female: 41 per 1,000 live births).

Furthermore, according to the 2024 census, the maternal mortality ratio has greatly reduced from 336 deaths per 100,000 live Births in 2016 to 207 deaths per 100,000 live births in 2024. Of these deaths, 40.9% occurred at home, 50.3% at a health facility, 4.4% on the way to the Health facility while 4.4% occurred in other places.

More so, average Life Expectancy at birth in 2024 was 68.2 years, with 70.1 years for females and 66.9 years for males.

### 2.1.2 (i) Labour Force Analysis

According to the 2024 census, out of 55,887 households, 46,067 Households are employed in Agriculture representing 82.4%. Others are employed in education, Health and other social services, sale of foodstuffs, household and personal goods, construction, agro-processing of foods and beverages and quarrying, sale, maintenance and repair of machinery and parts, hotels and lodging, bars, restaurants and eating places, transport, telecommunication, banking and other economic activities.

However, it should be noted that only 16.4% of the Households in Kibaale District are food secure (Census, 2024). This is far the average for Bunyoro sub region of 37.3% and the National average of 46.0%. This calls for concerted efforts to boost agricultural production and productivity within emphasis to promoting food securing in the wake of producing for the market.

## 2.2 Potentials, Opportunities, Constraints and Challenges (POCC) Analysis

### 2.2.1 Potentials

- The bimodal climate and fertile soils are very conducive for agriculture.

- Improved road net work is a potential for agriculture and tourism

- The rich wild life endowment is a potential for tourism.

- The High population with diverse culture (traditions, food, dances, wear, etc) is a potential for toursim.

- Existence of various rock out crops is a potential for the mining industry. It is also anticipated that the district has a number of other valuable minerals but exploration studies are still ongoing.

### 2.2.2 Opportunities

- Existance of the District within Bunyoro Sub region – the Oil region is an opportunity for tourism, agriculture in order to meet the increasing market for food

- Existence of peace, unity, political stability and security in the district and the country at large is also an opportunity for agriculture and tourism

- The improving road network in the district is also an opportunity for agriculture and tourism

- The extension of Hydro Electric Power to rural areas is an opportunity for value addition especially in agriculture.

- Existence of piped water supply systems in two Town council and eight Rural Growth centres is an opportunity for value addition in Agriculture and Tourism

- Existence of Government Grants is an opportunity for agro- industrialization e.g. the financial inclusion pillar under PDM.

- Existence of other Development Partners like CSOs, Faith Based Organisations, the Private sector and Cultural Institutions is an opportunity for agro industrialization.

- The numerous FM Radio Stations are an opportunity for farmer mobilsation.

- Improvement in Information Communication Technology is an opportunity for linking farmers to markets for inputs and agricultural produce e.g. use of telephones.

- Existence ofinstitutions for Justice, Law and order sector is an opportunity for curbing crop and livestock thefs

- Availability of financial services e.g. Stanbic Bank Bwamiramira Branch, several bank agents for Stanbic and Centenary Banks and several mobile money points are an opportunity for agro industrialization and tourism.

- Abundant solar insollation is an opportunity for agriculture and tourism.

- The existence of Bunyoro Kitara Kingdom is a source of unity in diversity and an opportunity for tourism.

### 2.2.3 Constraints

- Poor infrastructure in terms of access and feeder roads, increases the cost of doing business especially in agriculture value chains

- Land fragmentation constrains agricultural production

- The high population growth rate of 5.9% per annum far exerts pressure on natural resources especially flora and fauna which reduces agricultural production and depletes the natural tourist attractions.

- Low literacy rate among the population of 68.3%. undermines participation in agriculture and tourism

- Existence of an unskilled and semi-skilled population with low incomes undermines the competitiveness and productivity of the district population in agriculture and tourism.

- Land conflicts constrain agricultural production

- Domestic violence also constrains agricultural production

- Poor mindset limits the participation of the population in agriculture and tourism.

- Existance of unplanned trading centres constrains tourism development

### 2.2.4 Challenges

- Negative cultural practices favouring early marriages, male chauvinism, gender imbalances in ownership and control of productive resources, decision making, gender roles, etc are a challenge to agricultural production

- High rate of environmental degradation in the district is a challenge to agricultural production and tourism

- Existence of a relatively weak Private Sector characterized by inadequate capital outlay, inadequate skills and weak coordination structures.

- Climate change characterized by prolonged dry spells, hailstorms among others is a challenge to agricultural production

- Lack of piped water supply system for other Rural Growth centres like Hakasalaba and Kasimbi among others is a challenge to agricultural production

- Outbreak of crop and livestock diseases is a challenge to agricultural production

- High interest rates charged by Commercial Banks and Micro Finance Institutions limits accessibility to credit by mcro, small and medium scale farmers.

- High cost of internet limits use of modern Information Communication Technologies like zoom; internet and website which is a challenge to agriculture.

- Low level of technology retards the exploitation of available minerals.

- The land tenure system (MailoLand) limits the level of investment on land in agro industrialization.

## 2.3	Economic Infrastructure and services

### 2.3.1 Transport and Connectivity

Over the past 5 years, the road infrastructure in the district has greatly improved. There has been tarmacking of Mubende – Kakumiro – Kibaale – Kagadi Road. The District has also got 181kms of feeder roads 87% of which are generally in fair-to-good condition. Further still, the district has got 53kms of urban roads 84% of which are in fair-to-good condition. More so, the district has got 1,149 kms of access roads but only 20% of which is in fair-to-good condition. The generally good feeder road network in the district has been enabled by the acquisition of two Road Units with support from Central Government.

Although the road network in the district is generally good, it is difficult to maintain owing to the inadequate funding. More so, there are some areas that are poorly served especially Kyakazihire subcounty which requires affirmative action in this plan. The poor state of community access roads across the district is mainly due to low community participation in self help community Development activities. Even where some access roads have been rehabilitated by the district and handed back to the communities, maintenance of such roads by the communities has not been forthcoming.

During the period under review, the District passed the Bulungi Bwansi ordinance aimed at supplementing government efforts in maintaining public infrastructure including Community access roads. However, there is need to further popularize this policy to improve its performance.

### 2.3.2 Energy

The energy situation in the district is that more than 95% of the Population uses biomass as their primary energy source for cooking, lighting and warming. For the rural communities, the use of firewood is almost 100%. other forms of energy in the District include: Solar energy, Hydro electricity power. The situation is worsened by the rudimental methods which are wasteful and also a health hazard considering the carbon emissions. The high population growth rate in the district of 5.9% per annum exerts pressure on the limited renewable energy sources. In a bid to increase productivity and household incomes, various socio-economic activities are being undertaken and these have had a significant impact on the state of natural resources and environment in the district. For instance, charcoal production, uncontrolled tree harvesting, conversion of forested areas for agricultural production and bush fires have aggravated biomass loss and poverty.

### 2.3.3 Urbanization, Housing and Physical Planning

The level of urbanization in the Distrcit stands at 4.6%. There are two Town Councils in the District called Kibaale Town Council and Nyamarunda Town council. However, there are a number of Rural Growth centres namely, Kabasekende, Hakasalaba, Kitutu, Kikaada, Kasimbi, Imara among others. Regarding solid waste management for KIbaale Town Council and Nyamarunda Town council, there are 2 refuse bunkers, 2 garbage trucks and one dumping site. However, the mechanism for solid waste management in Rural Growth centres is not yet developed.

Regarding Housing, there are no deliberate Government interventions to provide housing to the urban population since the level of urbanization is still very low. Therefore, housing needs for the urban and rural population are handled at household level. The percentage of permanent buildings with approved plans in the rural areas is 5% and in urban areas is 50%. Regarding physical Planning, there is no Town Council with a valid Structural and Physical Plan. There are no approved physical Plans for all the Rural Growth centres owing to inadequate funding. More so, the district has not yet prepared a Physical Development Plan owing to Financial and technical capacity constraints. However, Physical Planning Committees at the District and all Lower Local Governments have been formed and oriented about their roles which is expected to improve the situation of Physical Planning in the district during LGDPIV implementation.

### 2.3.4 Information Communication Technology

Regarding Information Communication Technology, utilization of its services in the district is still low due to limited network coverage and non connectivity to National Backborn Infrastructure, high cost of end user devices and services, inadequate ICT knowledge and skills, and limited innovation capacity. For instance, use of computers is mainly in institutions and mainly used for less sophiscated work. There is need to boost use of ICTs for development e.g. through increased use of digital services for business process out sourcing, collaboration, automation, research and innovation.

### 2.3.5 Water for Production

During implementation of LGDP111, great effort was made to promote water for production in the District. Government of Uganda through the MAAIF implemenbted the UGIFT micro scale irrigation programme in which a total of 400 acres have been put under irrigation which increased the area under irrigation from 10 to 400 acres. More so, the Ministry of Water and Environment has constructed two small scale irrigation systems in Kitedi in Mugarama subcounty and Kiguma in kyebando subcounty.

However, there is low uptake of micro scale irrigation services due to the inability of farmers to co-fund owing to low levels of income.

### 2.3.6 Commerce

Trade is mainly characterised by sale of foodstuffs (Maize, Beans, cassava, potatoes and vegetables) household and personal goods which employs 1.5% of the district labourforce. Recently, trading in traditional and non traditional cash crops like Coffee, Avacado, Onions has increased. Trade activities are mainly concentrated in the Urban areas and Rural Growth centres allover the district. Trading activities have also given rise to various daily and periodic markets which are a source of Local Revenue to the District. Both men and women are involved in trading activities but women traders dominate the daily and periodic markets while men dominate trade in agricultural produce. Most of the trade businesses operate as retail sole proprietors while few are both wholesalers and retailers owing to the limited capital outlay and a relatively small market.

The improved road network in the District has reduced the cost of doing business and attracted traders from wthin and outside the District (including those from outside the country). More so, there has beed construction of commercial bulking/ post harvest handling facilities in the District Like Agahikaine grains and Hess farm stores which have the capacity to improve the Quality and shelf life of agricultural produce especially maize grain.

### 2.3.7 Industry

Manufacturing in the district is characterised by the existence of small scale cottage industries mainly dealing in foods and bevarages and other light manufacturing. Manufacturing employs 1.2% of the District labourforce mainly dominated by male youths. Over the last 5 years, the rate of industrial growth in the district has increased mainly due to the ongoing rural electrification programme. Currently, 22% of the District is connected to Hydro electricity which has promoted establishment of small scale industries such as maize mills, coffee hullers, carpentry and Welding workshops among others. The level of industrial development in the district is generally low owing to the relatively small market, limited capital base and inadequate raw materials.

### 2.3.8 Cooperatives

There has been growth of cooperatives in the District. These cooperatives are mainly for farmers or traders. The major cooperatives in the District include; Mugarama coffee Growers cooperative in Mugarama Sub county, Kyebando Twesiime cooperative in Kyebando Sub county, Nyamarunda Traders cooperative in Nyamarunda Sub county, Mugarama Tugende Mumaiso cooperative in Mugarama Sub county and Rukenembe Foundation Farmers Organisation in Karama Sub county among others. Through these cooperatives, farmers are able to access extension services, mobilise own savings, access agricultural inputs, micro finance and carryout bulk marketing of their agricultural produce among other services.

Over the last three years, Government has promotred and financed 36 Emyooga SACCOS and 57 PDM SACCOS across the District which has improved access to credit.

### 2.3.9 Financial Services

There is availability of financial services in the district through commercial banks and SACCOs. For instance, there is Stanbic Bank Bwamiramira located in Kibaale Town Council. There are also agents of Centenary Bank within the District. During the last five years, 36 Emyooga SACCOs within the district obtained funding from the Micro Finance Support Centre amounting to UGX 1.8 billion as seed capital. Under PDM, by mid November 2024, UGX 11.7 billion had been disbursed to 57 SACCOS at parish level. More so, there are various small scale SACCOs at village level that are aimed at boosting internal savings and lending. These SACCOs are mainly dominated by women who have proved to be more committed and trustworthy than men. Some of the SACCOs at village level are informal while others are registered. This presents the need for continuous support supervision from the District Commercial Services for guidance about registration and sustainability.

In 2024, the Microfinance support centre opened up a satellite office at the District Headquarters to bring the Microfinance support services near the population.

However, although financial services are available, there is constrained access to Micro Finance among the population mainly due to the high interest rates in commercial banks and Micro Finance Institutions. More so, there is lack of collateral especially among women and the youths which limits their capacity to acquire investment finance. Furthermore, there is a poor saving culture among the population coupled with low recovery rates mainly attributed to inadequate financial literacy and negative mindset.

## 2.4	Socio-Economic Situation

### 2.4.1 Life Expectancy

According to the Uganda Bureau of Statistics Census 2024, life expectancy for Kibaale stands at 68.2 years (Male: 66.9 years; Female: 70.1 years). Males have got a lower life expectancy compared to their female counterparts. Between 2014 to 2024, there was a gain of 4.5 years in life expectancy which could be attributed to the improvement in the mortality rates.

### 2.4.2 Poverty level

According to the Uganda Bureau of Statistics Census 2024, 27.0% of the Households in Kibaale District are still are still in subsistence economy i.e. they have not yet joined the money economy. This is slightly above the National average of 33.1%.  There is need to promote all initiatives aimed at increasing Household income like the Parish Development Model, Emyooga, Youth Livelihood Programme and Uganda Women Enterprenuership Programme among others.

### 2.4.3 Literacy Rate

According to UBOS 2019 Statistical Abstract and Uganda National Household Survey, 2016/2017, in the district, the literacy rate for persons aged 10 years and above stands at 68.3 percent of (Males: 77.3 percent and Females:  60.3 percent).  The Government of Uganda introduced the Universal Primary Education and Universal Secondary Education programmes in 1997 and 2007 respectively in order to improve the education status of the population.

### 2.4.4 Local Economy Analysis

The District infrastructure has been improved such as road network in form of trunk roads, feeder roads and community access roads which has eased the transportation and linkage of agricultural produce to the market. Regarding Hydro electric power supply, the District has benefited from the on-going rural electrification programmes by the central Government and this has facilitated agro processing especially in the maize and coffee value chains, growth of small scale industries such as welding and carpentry, saloons which provide employment especially to the youths.

The presence of the banking institutions such as the commercial banks and micro financial institutions in the District has enabled the business community to access credit facilities in form of loans and other financial services that has led to growth of new business and expansion of the existing businesses and increased financial literacy within the population.

### 2.4.5 Livelihood patterns

Subsistence agriculture is the major economic activity in the district employing 82.4% of the Households in the District (UBOS, Census 2024). Major crops grown include maize, bananas, beans, coffee, ground nuts and cassava. Major Livestock kept include pigs, poultry, goats, cattle, and sheep. Other economic activities include Public service, education and Health (3.2%), other social services (1.5%), sale of foodstuffs, household and personal goods (1.5%), construction (0.8%), Manufacturing foods and beverages (0.4%), other manufacturing (0.8%), Mining and quarrying (0.1%), sale, maintenance and repair of machinery and parts (0.4%), hotels and lodging, bars, restaurants and eating places (0.6%), transport, posts and telecommunication, financial institutions (0.5%) and others economic activities (1%).

### 2.4.6 Human Settlement Patterns

The District has 3 settlement patterns namely; linear settlement, nucleated settlement and scattered/sparse settlement. These vary according to infrastructure, topography, soils, and vegetation. Linear settlement is common in areas which are well served with infrastructure such as roads and hydro electric power lines. Examples of areas with linear settlement in Kibaale include; parts of the District that are along Kibaale-Kagadi tarmac (trunk) road such as trading centres like Kabasekende and Hakasalaba among others.

Kibaale and Nyamarunda Town Councils have got nucleated settlement pattern because of urbanization. Some parts of Bubango, matale, Karama and Nyamarwa are characterized by a hilly land scape and have got sparse or scattered settlement pattern. Some areas in the Sub counties of Kyebando, Nyamarunda and Kasimbi have dense settlements due to fertile soils and a favourable terrain.

### 2.4.7 Productive Resources and Economic Activities

The forests on private land provide timber which contributes to local revenue of the District. Forests are also a habitat for wild life which is a potential for tourism industry in the District. For example, Kagombe forest reserve is a habitat for an estimated 80 chimps (Pan troglodytes) and host to Black and white Colobus (Colobus guereza). Kangombe forest also forms a diverse ecosystem with more than 18% of Uganda’s total tree and shrub species of which 9 species are of restricted range. More so, Kagombe Central Forest Resrve is rich in butterfly species with a total of 238 species of which 4 are considered uncommon/rare, it is also rich in birds with a high proportion of forest dependent species such as the Red-sided Broadbill. The Forest Reserve has been recommended by the District to the Central Government for upgrading to a National Park.

The wetlands act as water reservours which are used to improve water coverage in the District. Wetlands also provide raw materials for the hand craft industry, clay for brick making, sand for sand excavation for example the wetlands in Kyakasengura, Kikada and Ngangi. Rock out crops provide source for stone quarrying like the Mugarama Quary which is a source of construction materials. Soils are used for agricultural production which is the main source of livelihood for most of the population in the District.

## 2.5	Social infrastructure and services

### 2.5.1 Health

The status of Health indicators in the District is generally low. According to the UDHS, 2021 Infant Mortality rate stands at 42 per 1,000 live Births, Child mortality rate at 22/1000 live births while Maternal mortality rate stands at 207 per 100,000 live Births. Further more, the OPD utilization rate has reduced from 0.7%in 2019/20 to 0.6% in 2023/24. The DPT immunization coverage is high and stands at 89%. More so, 100% of the villages in the District have got functional VHTs.

Regarding HIV/AIDS services, 74% of the population with HIV/AIDS are aware of their status which is far below the National target of 90%.  More so, 100% of the population with advanced HIV infection have got access to ARV drugs which is above the National target of 90%.  Furthermore, 89% of the clients on ART have got viral load suppression slightly less than the National target of 90%.

The Incidence and death rates associated with malaria in the district has stagnated at 16% between 2019/20 to 2023/2024. This is mainly attributed to misuse of insecticide treated mosquito nets and inadequate awareness. The proportion of TB cases detected and cured under DOTS has also increased from 80% to 84% between 2019/20 to 2023/2024. Regarding maternal Health, the proportion of deliveries conducted in government health facilities has slightly improved from 47% to 52% during the period 2019/20 to 2023/2024. This is mainly attributed to limited access to Health centres, existence of Traditional birth attendants.  The average number of ANC visits in the district has steadily progressed from 51% to 55% between 2019/20 to 2023/2024. This is also attributed to limited access to Health centres, existence of Traditional birth attendants.

### 2.5.2 Education

Regarding Primary Education, there is high enrolment rate in the district which has increased from 92.4%to 98.6% between 2019/20 to 2023/2024. The high enrolment rate is mainly attributed to the ongoing UPE programme, increased access to education services and the continuous go back to school campaigns. The literacy rate has greatly improved from 58% in 2020/21 to 70% in 2023/2024. More so, there is slight decline of the numeracy rate in the district from 69.3% to 68% between 2019/20 to 2023/2024. The performance index for primary education is high but has stagnated at 91% in 2023/24. However, although the performance index for primary education is high, the percentage of P.7 candidates passing in Grade 1 is very low and has even slightly declined from 6.7% in 2019 to 6.0% in 2023. More over, 97.8% of the 1st Grades at PLE in the district are realized by Private schools while only 2.2% of Grade one results are achieved by Government aided Primary schools.

The completion rate for primary education is also low although it has improved from 51.2% in 2020/21 to 69.9% in 2023/24. More so, the completion rate for girls is lower than the one for boys mainly due to teenage pregnancies. In terms of access to primary education, 21% of the Parishes in the District do not have a Government aided primary school. The affected subcounties are Bubango, Bwamiramira, Kasimbi, Kyakazihire, Kayanja, Nyamarunda Town Council and Kyebando.  In terms of staffing in Education, the district has a high rate of staffing of 89.8%. Of the available staff, only 41.9% are females while 58.1% are males.

In terms of infrastructure and other facilities in Government aided Primary schools, the Pupil: Latrine stance ratio is high and has declined from 1:42 in 2020/21 to 1:50 in 2023/24. This situation increases drop out rates especially for the girl child at menstrual age. The classroom: pupil ratio for Government aided Primary schools in the district is very high at 1:81 compared to the National target of 1:54. The desk: pupil ratio for Government aided Primary schools is also high at 1:5 compared to the National target of 1:3. Further more, the Pupil: Textbook ratio in Government aided Primary schools in the district has greatly improved from 1:8 in 2019/2020 to 1:2 in 2023/2024. These indicators largely account for the low Education outcomes in the district especially in Government aided Primary schools.

Regarding Secondary Education, the proportion of students passing ‘O’ level is high although it has increased from 86.2% in 2019 to 96% in 2023 The Enrolment rate is very low although it has decreased from 52.1% in 2020 to 45.6% in 2024. The completion rate is also still low but has greatly improved from 56% in 2020 to 68% in 2024 In terms of access to Secondary education, 64.3% of the sub counties in the District do not have a Government aided secondary school. The affected subcounties are Bubango, Bwamiramira, Kasimbi, Karama, Kyakazihire, Kayanja and Matale.

Interms of infrastructure for secondary schools during the period under review, Government has constructed facilities at Nyamarwa SS, St. Mugaga SS, Kisaalizi Parents SS, St. John Baptist Kasimbi SS and Buyanja SS

Regarding Tirtiary Education, there is no Government aided vocational Training institution in the district. However, there are 3 private vocational Training institutions but which are poorly developed and with very low enrolment.

### 2.5.3 Water

The water services in the district are steadily improving. The percentage of people within 1km of an improved water source has increased from 60% in 2020/21 to 70% in 2024/25. The percentage of functional rural water point sources has also increased from 80% in 2020/21 to 83% in 2024/25. This unfunctionality of rural water sources is mainly attributed to unfunctional Water user committees whose rate stands at 65%. Furthermore, access to safe sanitation has greatly increased from 18% in 2020/21 to 80% in 2024/25. The proportion of water sources tested for quality is very low and has stagnated at 20% between 2020/21 to 2024/25. The poor performance for some of the  water and sanitation related indicators partly explains the high morbidity rate in the district due to water borne diseases especially among children, pregnant mothers and the elderly.

### 2.5.4 Social Protection

In terms of Child protection, the district has got a total of 28,323 Orphans and other vulnerable children which translates into 16.3% of children in the district. The composition of these OVCs is as follows: orphans (6.1%), child mothers aged 12-17 years (48.3%), child labourers (26.3%), Children out of School (19.5%), married children (4.8%), Children with disability (1%) and Children heading households (3%). The above analysis shows that some OVCs have got multiple vulnerabilities. The annual reported cases of child abuse have increased from 2.1% in 2020/21 to 2.5% in 2024/25. This is partly attributed to the increased community awareness about child rights and protection issues that has been supported by Development Partners. There is neither an orphanage home nor a child resettlement centre in the district.

In terms of gender based violence, the annual change in reported cases of gender based violence has slightly increased from 9.5% in 2020/21 to 9.7% in 2024/25. This implies that on average, two cases of GBV are reported in the district per day. However, there are other GBV cases that occur at Household level but are never reported due to inadequate awareness among the community regarding the nature and handling of GBV cases.

In terms of labour related cases ab total of 70 cases were reported in 2023/24 compared to the 30 cases registered in 2019/20 atributed to increased awareness to the community about the services being offered at the Districtt and increased government efforts to main stream social safeguards in all development projects and capacity building efforts by the development partners

### 2.5.6 Community Development

2.5.6 (a)Youths Empowerment

Kibaale is one of the Districts that started implementation of the YLP in FY 2014/15. Since then, a total of UGX 1,170230800 has been disbursed to 126 youth groups in Kibaale District. The beneficiary youth groups have established a wide range of projects for enhancement of their incomes for instance; Boda boda transport, carpentry and mechanical workshops, agriculture (mainly crop and livestock) projects, trade (especially in agricultural produce), hair and Beauty salons and tailoring among others. The programme covers the entire district. Regarding recoveries, a cumulative total of 343,507,300 has so been received representing an average recovery rate of only 28.9% of the expected amount.

2.5.6 (b) Women Empowerment

Kibaale is also one of the Districts that started implementation of the UWEP in FY 2015/16. Since then, the district has received a cumulative amount of UGX 1,079,684,607 which has benefitted 122 women groups. The beneficiary women groups have established a wide range of projects for enhancement of their incomes for instance; agriculture (mainly crop and livestock) projects, trade (especially in agricultural produce), hair and Beauty salons and tailoring among others. The programme covers the entire district. Regarding recoveries of UWEP funds, a cumulative total of UGX 593,826,533 has been received representing a recovery rate of 55% of the expected amount. There is need for continued follow up of groups that have not yet paid up their loans in order to improve the recovery rate.

In a bid to improve women access to affordable credit, the government has introduced GROW programme which will be offering women loans ranging from 4 to 200million.

2.5.6 (c) Support to Elderly

Kibaale is also one of the Districts that started implementation of the SAGE programme in FY 2016/17. On average, 670 older persons of 60 years and above have benefitted per year with an average funding of UGX 150 million per year translating into a total of UGX 1,404,000,000 since its inception. The programme covers the entire district.

Furthermore, the special enterprise grant for older persons was introduced by government with effect from 2021/22 and 7 older persons groups have benefited to a tune of 35 million

2.5.6 (d) Persons with Disability Programmes

The percentage of population with disabilities has remained almost constant at 5% over the past four years. During the LGDP 111 implementation the Special Grant for persons with disabilities was introduced by government. To date, 47 PWD groups have benefited with funding amounting to 235million

2.5.6 (e) Integrated Community Learning

The Integrated Community Learning in the district is generally fair but has stagnated at 62% between 2020/21 to 2024/25. The District has got 55 ICL classes, 47 ICL instructors and 618 ICL Learners. However, there is limited funding for ICL programmes in the district which has led to non functionality for most of the FAL classes. There is need to revitalize FAL Programmes in the district during LGDPIV implementation.

## 2.6	Environment Situation

### 2.6.1 Climate

Kibaale District has got a favourable climate.  It enjoys a bi-modal rainfall type which varies between 1000 mm-1500 mm per annum i.e moderate to high rainfall.  Rainfall comes in two peaks, one from March to May and the second from September to December. Temperatures are relatively high varying between 150c and 300c. This type of rainfall is conducive for rain fed agricultural production throughout the year and crops mainly grown include coffee, maize, beans, bananas, cassava, and tobacco.

However, there is a challenge of climate Change in the District manisfested by prolonged dry spells, increasing temperatures, floods, hailstorms and epidemics in crops and livestock among others. Climate change has led to low levels of agricultural production and productivity in the district. This situation calls for prioritizing interventions to increase community resilience to the effects of climate Change like Climate smart Agriculture, provision of sustainable sources of safe water, promotion of solar energy technologies and construction of climate resilient infrastructure at household and institutional levels among others.

### 2.6.2 Vegetation

There are three broad categories of vegetation in the district namely; the modified equatorial type, the wooded savannah mosaic and savannah grassland. The modified equatorial vegetation covers a greater part of the district especially in the sub counties of Bwamiramira, Kyebando, and Nyamarwa. This type of vegetation used to be equatorial in nature but has been modified as a result of human activity. The wooded savannah mosaic covers a greater part of the district and forms a transitional zone from the modified equatorial vegetation to open savannah grassland as commonly observed in the sub counties of Matale, Nyamarwa and parts of Nyamarunda. The natural forests especially those on private land have been continuously harvested for timber and this has posed a threat of environmental degradation since reforestation and afforestation are very limited.

In terms of forest cover, the District has got seven Central Forest Reserves covering a total area of 15,175.25 hectares namely; Kanaga, Kijuna, Muhunga, Nyabigoye, Nyabiku, Nyakarongo, Rukara and Kagombe. These forests act as catchment areas for wetland systems which act as water reservoirs that are used for water supply to the communities in form of piped water system, bore holes and shallow wells. For example, Kagombe forest reserve is one of the catchment areas for river Muzizi wetland system. There is high rate of deforestation in central Forest reserves (49.2%) due to enchroachment. More so, there are forests on private land and these forests are not yet registered. Thus, there is high level of degradation of forests on private land due to inadequate regulation. Furthermore, there has been increasing demand for wood products like plywood especially from eucalypyus which has escalated the deforestation rate in the District

Over the last 10 years, the District has been providing tree seedlings to farmers and this has increased the number of woodlots and tree plantations in the District. The species provided has been mainly eucalyptus and pine. In terms of value addition to the forestry products, there are few carpentry workshops in the district. Thus, most of the forestry products are sold to markets outside the District especially in Kampala. The forest products are mainly electricity poles and timber. Woodlots service the local demand for wood fuel at household and institutional levels. Also, there is increasing demand for wood fuel for brick making in the district especially by the male youths.

### 2.6.3 Wetlands

Wetlands cover 12.6% of the total District area. There are 3 wetland systems in the District namely the primary, secondary and tertiary wet land systems. Examples of primary wet land systems include Muzizi and Nkusi. Secondary wetland systems drain into the primary wet land systems example of which is Mbaya wetland. The tertiary wetland systems form the original catchment for all the other wet land systems. There are a number of such tertiary wet lands in the District namely; Kabuta in Kibaale Town Council, Kajubya and Kiri in Nyamarunda, Kijanibarora in Mugarama, Bagoya in Kasimbi, Jumambogo in Kasimbi and Rwebisarale in Bubango among others.

Wetlands act as water reservoirs that are sources for various safe water points in the District. More so, they are a basis for productive activities like brick making, sand excavation for construction and also provide raw materials for the handcraft industry that employ mainly the youth and the women. The District has experienced wetland degradation mainly as a result of cultivation of crops, tree planting especially eucalyptus, sand excavation and brick making for instance Nkusi and Muzizi wetland systems. More so, poor agricultural practices and road construction has led to degradation of wetlands in the District in form of sedimentation and silting of the water channels thus causing pollution of water sources used for domestic use.

There are ongoing efforts to restore degraded wetlands like boundary demarcation and restoration of critical wetland systems like Muzizi and Nkusi. However, the coverage is minimal.

### 2.6.4 Soils

The soils of the District are of ferrallitic type. Productivity of these soils largely depends on favourable rainfall, adequate depth and maintenance of the humic top soil. There are three soil mapping units in Kibaale district namely; Buwekula Catena, Buyaga Catena and Kamusenene series. Buwekula catena covers 90% of Buyanja County and comprises three major types of granitic soils namely; Shallow loams, red clay loams and brown gravelly clay loams. Shallow loams have Moderate acidity with moderate productivity and mainly support the growing of tobacco and tea.

The rich soil endowment provides an opportunity for growing of a variety of crops as already highlighted. However, there is evidence of loss of soil fertility through leaching especially where agricultural production is done in formerly forested areas. More so, the population pressure on land has negatively impacted on soils leading to soil exhaustion. More so, the poor methods of farming such as excessive use of herbicides has led to loss of soil fertility within the District.This is worsened by soil erosion since much of the landscape in the District is hilly coupled with poor methods of farming which leads to low agricultural productivity.

The Land tenure system in the district is predominantly mailo land comprising over 80%. Mailo land titles are owned by Absentee land lords. These titles were awarded by the British colonialists to Baganda Colonial agents at the advent of British imperialism in what used to be the lost counties of Buyaga and Bugangaizi (the current Kibaale, Kakumiro and Kagadi Districts). Government of Uganda through the Land Fund is undertaking the systematic Land demarcation aimed at compensating the absentee landlords and giving land titles to the bonafide occupants.

Notwithstanding the ownership of registrable interest on the land, there are gender imbalances in ownership and control of land among the bonafide occupants. Land is mainly owned by men although women have access to the resource in terms of utilising it. Consequently, men also control the proceeds from use of the land they own. This Socio-cultural rigidity affects decisions for development projects on the land.

### 2.6.5 Topography

The District is part of a central plateau with an altitudinal range of about 2000- 4000 ft. above sea level. The topography of the District is characterized by the hilly and rocky relief which presents challenges during construction and maintenance of roads, buildings and makes agricultural production difficult like through inducing soil erosion.

Rock outcrops provide quarry sites for construction materials, for example the quary site in Mugarama provided road gravel for the construction of Kibaale-Kagadi trunk (tarmac) road. However, the level of exploitation of this resource is still very low owing to low levels of technology in the district and the country at large.

## 2.7 Local Governance and Administration

The general staffing level in the district has greatly declined from 96% to 73.3% in 2023/2024 mainly due to the new staffing establishment for the Health department. However, there are constraints to staff performance for instance inadequate means of transport for staff, inadequate capacity, inadequate staff accommodation especially for teachers and health workers, salary disparities and inadequate enabling facilities/tools especially computers.

Service delivery has also been hampered by inadequate funding for recurrent operations like stationery, fuel, and duty facilitating allowances among others. This situation is more severe in the departments that do not receive and those that receive very little conditional grants for recurrent activities from the central Government namely; Statutory Bodies, Natural Resources, Community Based Services, Planning and Internal Audit.

In terms of administrative infrastructure, the situation at the District Headquarters is generally good for most of the departments although the buildings require renovation. However, the situation is bad for some Subcounties characterised by lack of administrative offices in 60% of the Subcounties and existence of dilapidated offices in 40% of the sub counties.

Regarding staff accommodation, the situation is no better either. The staff houses at the District Headquarters are dilapidated and require renovation. There is also inadequate staff accommodation in the existing Health facilities and the primary schools in remote areas.

## 2.8	Synthesis of development issues

- Low agricultural production and productivity: Subsistence agriculture is the major economic activity in the district employing 81% of the District labourforce. This is characterized by use of poor methods of farming and low levels of production and productivity. Low agricultural production and productivity is also due to pests and diseases and effects of climate change. This problem is exacerbated by the low levels of value addition for agricultural production in the district. The problem amounts to low income among the population and undermines the efforts for wealth creation in the district.

- Low quantity and quality of social services:  The service delivery indicators especially in Health, Education and water are still low in terms of quantity and quality. This is due to a multiplicity of service delivery constraints mainly caused by inadequate funding. The low service delivery indicators undermine the fight against poverty in the district.

- Poorly maintained road network: It is difficult to properly maintain the feeder road network in the district owing to the inadequate funding for road maintenance from the Central Government. More so, there are some areas that are poorly served especially Kyakazihire Sub county which requires affirmative action in this plan. The poor state of community access roads across the district is mainly due to low community participation in self help community Development activities.

- Inadequacies in the Governance and oversight function: The Governance and oversight function is faced with a set of challenges that hinder its effectivesness and efficiency. These include; inadequate funding for Council, Boards and Commissions, inadequate capacity of Councillors especially at LLGs and limited opportunities for exposure of councillors through study visits among others.

- Inadequacies in Public Sector Management: Public Sector Management has got a number of challenges that hamper its effecitiveness and efficiency. These include; inadequate facilitation of staff, limited opportunities for capacity Building of staff, inadequate means of transport for staff, lack of office accommodation especially at Lower Local Governments and inadequate office equipment among others.

- Slow implementation of the Development Plan: Development Plan implementation is faced with various challenges which hinder achievement of the set targets. The challenges include; low local revenue mobilsation, inadequate alignment of annual workplans to the Development Plan, weak LLG Technical Planning committees, non existent Parish Development committees coupled with inadequate capacity for monitoring and evaluation of the Development plan at the District and Lower Local Governments.

- High population growth rate: According to the 2024 Population and Housing Census, the district has got one of the highest population growth rates in the country standing at 5.9% per annum. This is caused by an influx of people from other areas in search of arable land and the high fertility rate of 6.0 children per woman (UBOS Census 2024; UDHS, 2021). The population growth rate is far above the rate of investment in service provision like water, Health, education, etc. More so, the population structure of the district is dominated by a young population with children below 18 years constituting about 57%. Such a structure undermines production and has worsened the dependency burden in the district. The percentage of population in subsistence economy is still high at 27.0% (UBOS Census 2024) although the percentage of poor peoplein the District has declined from 31.9% in 2021 (The Uganda Poverty Status Report 2021). This partly explains the low quality of population which cannot acceralate socio-economic transformation.

- Degradation of natural resources: Owing to the high population growth rate in the district, there is high degradation of natural resources especially forests on private land. The high rate of deforestation is mainly due to the need for arable land. This partly explains the micro climatic changes in the district leading to low agricultural production and productivity.

- Poor use of renewable energy: The energy situation in the district is that more than 95% of the Population uses biomass as their primary energy source for cooking, lighting and warming. For the rural communities, the use of firewood is almost 100%. The situation is worsened by the rudimental methods which are wasteful and also a health hazard considering the carbon emissions.

- Limited participation of marginalized groups in income generating projects: The number of beneficiaries from the ongoing community empowerment programmes is still very low owing to inadequate funding. The programmes are UWEP, YLP, SAGE and Special Programme for Persons with Disabilities.

- Gender imbalances: There are gender imbalances especially in production and social services which retard development in the district. For instance, gender imbalances in agricultural production are characterized by dominance of women and children in the downstream stages of production like tilling of land, planting, weeding and harvesting. Men are more involved in the upsteam stages of production like value addition and marketing and therefore control the proceeds from agriculture which is a disincentive to agricultural production among women. Such gender imbalances are mainly due to poor mindset and negative social and cultural beliefs.

- Limited use of Information Communication Technology: The utilization of ICT services in the district is still low due to limited network coverage, high cost of end user devices and services, inadequate ICT knowledge and skills, and limited innovation capacity. For instance, use of computers is mainly in institutions and especially used for less sophiscated work. There is need to boost use of ICTs for development e.g. through increased use of internet services for Business Process outsourcing, research and innovation.

- Weak and uncompetitive private Sector: The district has got a weak private sector characterized by weak coordination structures, low skills and inadequate capital outlay. This retards the capacity of the private sector to contribute towards the development of the district through Public Private Partnership.

- Low levels of Tourism Development in the District: There is low tourism development in the district. Most of the tourist attractions are not yet developed. These include; Kagombe Central Forest Reserve, several cultural sites (Egasani) which were burial grounds for Bunyoro Kings and St. Kirigwaijo martyrs shrine in Bubango subcounty among others. More so, the hospitality industry is not properly developed due to limited capital outlay and inadequate skills among the private sector. Development of the tourism potential in the district requires a concerted effort between the the Local Government and the Private Sector.

- Unplanned Rural Growth centres:  All upcoming Rural Growth centres in the district do not have approved physical plans. This is a disincentive to developers and has led to difficulties of zoning developments in these trading centres. It has also led to emergency of shunty Rural Growth centres. There is need for physical planning of these centres before more developments emerge in order to have organised developments and plan for future expansion of these centres.

# CHAPTER THREE: LGDP STRATEGIC DIRECTION AND PLAN

## 3.1 District Vision and Mission

### 3.1.1 The District Vision

A prosperous population with a good standard of living and functional skills for sustainable development.

### 3.1.2 The District Mission

To serve the community through coordinated delivery of services focussing on National priorities and significant local needs in order to accelerate sustainable development in the District.

## 3.2 Summary of adopted NDPIV Strategic Direction (Goal, Strategic Objectives and Programs) and Strategies

### 3.2.1 The District Goal

In line with the goal for the NDP1V, the district goal is to achieve higher household incomes and employment for sustainable socio-economic transformation.

### 3.2.2 Strategic objectives of the Plan

In line with the NDPIV, the strategic objectives of the LGDP1V are to;

i) Sustainably increase production, productivity and value addition in agriculture, minerals, oil & gas, tourism, ICT and financial services.

ii) Enhance human capital development along the entire life cycle.

iii) Support the private sector to drive growth and create jobs.

iv) Build and maintain strategic sustainable infrastructure in transport, housing, energy water, industry and ICT.

v) Strengthen good governance, security, and the role of the state in development

### 3.2.3  Programmes

The District has adopted 13 Programmes as follows:

- Agro-Industrialization;

- Tourism Development;

- Natural Resource, Environment, Climate Change, Land and Water Resources Management;

- Private Sector Development;

- Digital Transformation;

- Integrated Transport Infrastructure and Services;

- Sustainable Energy Development;

- Sustainable Urban and Housing Development;

- Human Capital Development;

- Governance and Security;

- Public Sector Transformation;

- Development Plan Implementation; and

- Legislature, Oversight and Representation

### Strategies

The Plan will be implemented through the strategies summarised in Table 3 as follows:

# Table 3: Summary of LGDPIV Objectives and Strategies

| S/No | Objectives | Strategies |
| --- | --- | --- |
| 1 | Sustainably increase production, productivity and value addition in agriculture, minerals, oil & gas, tourism, ICT and financial services | 1.1 Increase Production and Productivity in agriculture, tourism, ICT and financial services. 1.2 Increase Value Addition in agriculture, tourism, ICT and financial services |
| 2 | Enhance human capital development along the entire life cycle | 2.1 Improve access, equity, and quality of education at all levels, 2.2 Improve Access, Equity and Quality of Healthcare at all Levels 2.3 Rehabilitate, Equip and Construct Health Infrastructure at all levels 2.4 Enhance access to water, sanitation, and hygiene. 2.5 Promote Community Mobilization and Mindset change 2.6 Expand Social Protection Safety nets 2.7 Institutionalize Manpower Planning and Promote Industry-driven Skilling and Training 2.8 Promote empowerment and livelihood programmes for youth, women, children, elder persons, and People with Disabilities; 2.9 Promote decent employment opportunities 2.10 Leverage the culture and creative economy for employment and domestic resource mobilization; 2.11 Promote Games and Sports; 2.12 Promote better nutrition for all |
| 3 | Support the private sector to drive growth and create jobs | 3.1 Reduce the Cost of doing Business 3.2 Promote Local Content particularly for MSMEs 3.3 Increase Market Access and Competitiveness 3.4 Strengthen Public-Private Partnerships 3.5 Inculcate the entrepreneurship mindset and educate the population to invest in productive sectors like agriculture |
| 4 | Build and maintain strategic sustainable infrastructure in transport, housing, energy water, industry and ICT | 4.1 Prioritize Infrastructure Maintenance 4.2 Develop Inter-modal and Seamless Transport Infrastructure 4.3 Increase Access to Clean, Reliable and Affordable Energy 4.4 Increase Access to Reliable and Affordable ICT Services 4.5 Leverage Urbanization for Socio-economic Transformation |
| 5 | Strengthen good governance, security, and the role of the state in development | 5.1 Strengthen the Rule of law 5.2 Consolidate and Sustain Peace and Security 5.3 Increase Local Government Investment and Participation in Strategic Areas 5.4 Improve Capacity and Accountability for Implementation of Public Programmes 5.5 Leverage Capacity of the Non-State Actors to Implement the District Development Plan 5.6 Increase civic participation in the development process, decision making, democratic governance, and socioeconomic development 5.7 Sustain a suitable Fiscal and Regulatory Environment |

## 3.3 Key Development Results

At the strategic level, tracking progress made during the implementation of this plan will be done through a set of LGDPIV strategic level objective indicators, as defined in Table 4. These indicators cover all major areas of interest under the five strategic objectives. Targets to be achieved at the end of the five-year period have been set within the context of the Vision 2040 targets as well as the FY 2024/2025 baseline.

# Table 4: Targets for Key Development Results

| Results | Indicators | Baseline 2024/25 | LGDP Targets |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 |
| Household incomes | Population below the poverty line (percent) | 9.8 | 9.0 | 8.5 | 8 | 7.5 | 7.0 |
|  | Household Population in subsistence economy (percent) | 27.0 | 26.0 | 25.0 | 24.0 | 23.0 | 22.0 |
| Quality of life | Population growth rate (percent per annum) | 5.9 | 5.8 | 5.7 | 5.6 | 5.5 | 5.4 |
| Agro Industrialisation | Percentage of labourforce employed in subsistence agriculture | 82 | 79 | 76 | 70 | 68 | 65 |
|  | Annual growth of marketed agricultural output [%] | 79 | 80 | 81 | 82 | 84 | 88 |
|  | Annual growth of farmer organization membership [%] | 15 | 20 | 21 | 23 | 25 | 29 |
|  | Annual growth of registered farmer contacts with extension staff [%] | 20 | 23 | 25 | 26 | 28 | 29 |
| Tourism | Percentage of labourforce employed in Tourism | 1 | 2 | 2 | 3 | 3 | 4 |
| Natural Resources Management | District reforestation rate [%] | 5 | 6 | 7 | 8 | 9 | 10 |
|  | Area (ha) of wetlands demarcated and restored | 54 | 64 | 74 | 84 | 94 | 100 |
|  | Proportion of Wetland Action Plans and regulations developed | 20 | 30 | 40 | 50 | 60 | 70 |
| ICT | Internet penetration rate (internet users per 100 people) | 15 | 23 | 30 | 36 | 42 | 47 |
| Land | Percentage of Land disputes settled | 20 | 30 | 35 | 40 | 50 | 60 |
| Private sector growth | Annual growth rate of the local business register [%] | 40 | 45 | 50 | 55 | 60 | 65 |
| Energy | Percentage reduction of annual biomas demand | 2 | 2 | 2 | 2 | 2 | 2 |
| Urbanisation, Housing and Physical Planning | Urbanisation rate | 10 | 11 | 12 | 13 | 14 | 15 |
|  | Percentage of permanent buildings with approved plans | 20 | 22.5 | 25 | 30 | 35 | 40 |
| Roads | Share of District roads in fair-to-good condition [%] | 89.5 | 90 | 92 | 93 | 94 | 95 |
|  | Share of community access roads in fair-to-good condition [%] | 24 | 26 | 28 | 30 | 32 | 38 |
|  | Share of Urban access roads in fair-to-good condition [%] | 45 | 47 | 50 | 55 | 58 | 60 |
| Health | Life expectancy at birth (years) | 68.2 | 69 | 70 | 71 | 72 | 73 |
|  | Infant Mortality Rate/1000 | 42 | 42 | 40 | 39 | 38 | 35 |
|  | Under five Mortality Rate/1000 | 60 | 58 | 56 | 54 | 52 | 50 |
|  | Maternal Mortality Ratio/100,000 | 207 | 180 | 140 | 130 | 120 | 114 |
|  | Total Fertility Rate | 6 | 6 | 5 | 5 | 4 | 4 |
|  | OPD Utilization [%] | 60 | 60 | 70 | 80 | 90 | 100 |
|  | Diptheria Immunization coverage [%] | 89 | 90 | 91 | 92 | 93 | 95 |
|  | Proportion of villages with functional VHTS | 100 | 100 | 100 | 100 | 100 | 100 |
|  | Proportion of population with HIV/AIDS are aware of their status | 74 | 75 | 80 | 85 | 90 | 95 |
|  | Share of population with advanced HIV infection with access to ARV drugs | 100 | 100 | 100 | 100 | 100 | 100 |
|  | Proportion of clients on ART with viral load suppression | 80 | 85 | 87 | 90 | 92 | 95 |
|  | Incidence rates associated with malaria | 17,635 | 16,964 | 15,954 | 14,853 | 13,567 | 12,671 |
|  | Death rates associated with malaria | 4 | 4 | 4 | 3 | 3 | 2 |
|  | Proportion of TB cases detected and cured under DOTS | 84 | 84 | 88 | 91 | 93 | 95 |
|  | Proportion of deliveries conducted in government health facilities | 52 | 52 | 55 | 58 | 62 | 65 |
|  | Average number of ANC visits | 31,706 | 32,000 | 33,000 | 34,000 | 35,000 | 36,000 |
| Education (Primary) | Literacy rate [%] | 70 | 70 | 75 | 80 | 85 | 90 |
|  | Numeracy rate [%] | 68 | 70 | 75 | 80 | 85 | 90 |
|  | Performance index | 92 | 92 | 93 | 94 | 95 | 96 |
|  | Enrolment rate [%] | 98.6 | 98.6 | 98.6 | 98.6 | 99 | 100 |
|  | Toilet/ stance to pupil ratio | 1:55 | 1:53 | 1:50 | 1:48 | 1:45 | 1:40 |
|  | Desk to Pupil ratio | 1:5 | 1:4 | 1:4 | 1:3 | 1:3 | 1:3 |
|  | Classroom to pupil ratio | 1:83 | 1:80 | 1:75 | 1:70 | 1:65 | 1:55 |
|  | Text book to pupil ratio | 1:3 | 1:2 | 1:2 | 1:2 | 1:1 | 1:1 |
|  | Teacher to pupil ratio | 1:65 | 1:60 | 1:58 | 1:55 | 1:53 | 1:53 |
|  | Completion rate [%] | 69.9 | 70 | 74 | 78 | 80 | 90 |
| Education (Secondary) | Proficiency scores (Proportion of students passing ‘O’ level) | 96 | 96 | 97 | 98 | 99 | 100 |
|  | Enrolment rate | 45.6 | 50 | 55 | 60 | 70 | 80 |
|  | Performance index | 96 | 96 | 97 | 98 | 99 | 100 |
|  | Completion rate [%] | 68 | 70 | 75 | 80 | 85 | 90 |
| Water and Environment | % of water samples taken at the point of water collection, water discharge point that comply with national standards (Protected Rural Sources) | 20 | 26 | 30 | 35 | 35 | 40 |
|  | % of people within 1km of an improved water source | 70 | 71 | 72 | 73 | 74 | 75 |
|  | % of rural water point sources functional | 83 | 84 | 84 | 85 | 85 | 86 |
|  | Access to safe sanitation [%] | 80 | 81 | 82 | 83 | 84 | 85 |
|  | Proportion of water sources tested for quality [%] | 20 | 22 | 25 | 25 | 25 | 30 |
|  | % of people with access to improved sanitation | 32 | 35 | 40 | 45 | 50 | 60 |
|  | Hand washing (%) | 18 | 20 | 25 | 30 | 35 | 45s |
| Social Protection Coverage | Percentage of population receiving direct income support | 0.04 | 0.04 | 0.05 | 0.05 | 0.06 | 0.06 |
| Governance and Security | Share of unqualified audit reports [%] | 100 | 100 | 100 | 100 | 100 | 100 |
| Public Sector Transformation | Staffing level (%) | 74 | 76 | 78 | 80 | 82 | 85 |
| Development Plan implementation | Share of locally generated revenue [%] | 2.3 | 2.5 | 2.8 | 3.0 | 3.1 | 3.4 |
|  | Budget absorption rate [%] | 91 | 91.8 | 92 | 92.4 | 93 | 93.2 |
|  | Annual NDP compliance score | No data | 65 | 68 | 70 | 73 | 75 |

## Summary of Programme Results and Targets

Strategic Objective 1: Sustainably increase production, productivity and value addition in agriculture, minerals, oil & gas, tourism, ICT and financial services.

## Programme: Agro-industrialisation

Development Issue: Low agricultural production and productivity

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective (1): Sustainably increase production and productivity in agriculture | Outcome 1.1: Increased yield of priority agricultural commodities | Outcome Indicator 1: Percentage change in yield of priority agricultural commodities | 3% | 3.8% | 4.2% | 4.5% | 5% | Annual District production and Marketing report |
| Programme Objective (2): Improve harvesting, post-harvest handling and storage | Outcome 2.1: Reduced post-harvest handling losses | Outcome Indicator 1: Post harvest handling losses for priority agricultural commodities | 3% | 3.8% | 4.2% | 4.5% | 5% | Annual District production and Marketing report |
|  | Outcome 2.2: Increase processed agriculture products | Outcome Indicator 1: Agriculture value added as proportion of GDP | 2 | 4 | 5 | 6 | 8 | Annual District production and Marketing report |
|  | Outcome 2.3: Increase employment in agro-industry | Outcome Indicator 1: Number of jobs created in the agro-industrial value chain | 2000 | 2500 | 3000 | 4000 | 4500 | Annual District production and Marketing report |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme: (1) Agricultural Production and Productivity | Intermediate Outcome 1.1: Increased production volumes of priority agriculture commodities | Outcome Indicator 1: Production volumes of coffee (million 60-kg bag) | 0.048 | 0.049 | 0.052 | 0.054 | 0.057 | District Annual Statistical Abstract |
|  |  | Outcome Indicator 2: Production volumes of Maize (metric tones) | 19209.5 | 19939.46 | 20776.9 | 21711.86 | 22797.45 | District Annual Statistical Abstract |
|  |  | Outcome Indicator 3: Production volumes of milk (billion litres) | 0.0013 | 0.00137 | 0.00142 | 0.00149 | 0.00156 | Annual District production and Marketing report |
|  |  | Outcome Indicator 4: Production volumes of pork (Metric tones) | 1297.03 | 1346.3 | 1402.86 | 1465.99 | 1539.29 | Annual District production and Marketing report |
|  |  | Outcome Indicator 5: Production volumes of cocoa (Metric tones) | 251.32 | 260.09 | 271.82 | 284.06 | 298.26 | Annual District production and Marketing report |
|  |  | Outcome Indicator 6: Production volumes of fish (Metric tones) | 51.5 | 53.46 | 55.7 | 58.21 | 61.12 | Annual District production and Marketing report |
|  |  | Outcome Indicator 7: Production volumes of honey (Metric tones) | 16.62 | 17.25 | 17.98 | 18.79 | 19.72 | Annual District production and Marketing report |
|  |  | Outcome Indicator 8: Production volumes of goat meat (Metric tones) | 865.2 | 898.08 | 935.79 | 977.91 | 1026.8 | Annual District production and Marketing report |
|  | Intermediate Outcome 1.2: Increased adoption of agricultural technologies | Outcome Indicator 1: Proportion of farmers adopting improved agricultural technologies, % | 15 | 20 | 30 | 50 | 70 | Annual District production and Marketing report |
|  |  | Outcome Indicator 2: Percentage of farmers accessing (using) labour saving technologies by type (tractors, buldozers, chaff cutters, etc) | 5 | 10 | 15 | 20 | 40 | Annual District production and Marketing report |
|  |  | Outcome Indicator 3: No. of fish seed multiplication sites established | 1 | 1 | 2 | 3 | 3 | Annual District production and Marketing report |
|  | Intermediate Outcome 1.3: Reduced occurrence of crop pests, livestock vectors and diseases for crops, livestock and fisheries | Outcome Indicator 1: Prevalence of crop pest/ diseases | 20 | 15 | 14 | 12 | 10 | Annual District production and Marketing report |
|  |  | Outcome Indicator 2: Prevalence of Livestock vector/diseases | 20 | 15 | 14 | 12 | 10 | Annual District production and Marketing report |
|  |  | Outcome Indicator 3: Quarterly antimicrobial surveys undertaken | 4 | 4 | 4 | 4 | 4 | Annual District production and Marketing report |
|  |  | Outcome Indicator 4: Laboratoty turnaround time for diagnostic samples submitted (hours) | 12 | 8 | 6 | 5 | 4 | Annual District production and Marketing report |
|  |  | Outcome Indicator 5: Number of survaillance and outbreak investigations undertaken | 8 | 8 | 8 | 8 | 8 | Annual District production and Marketing report |
|  | Intermediate Outcome 1.4: Increase access to agriculture extension services | Outcome Indicator 1: Proportion of farming households accessing agricultural extension services, % | 20 | 25 | 30 | 35 | 40 | Annual District production and Marketing report |
|  | Intermediate Outcome 1.5: Increase farmer resilience to climate change | Outcome Indicator 1: Proportion of farmers adopting sustainable land management/climate smart practices | 10 | 15 | 20 | 25 | 30 | Annual District production and Marketing report |
|  | Intermediate Outcome 2.1: Increase adoption of recommended post-harvest handling practices | Outcome Indicator 1: Percentage of farmers adopting recommended post-harvest handling practices | 33 | 38 | 42 | 35 | 50 | Annual District production and Marketing report |
|  | Intermediate Outcome 2.2: Increase operational capacity of the agro-processing and value addition facilities | Outcome Indicator 1: Operational capacity of the agro-processing and Value addition facilities | 10 | 15 | 20 | 27 | 30 | Annual District production and Marketing report |
|  | Intermediate Outcome 2.3: Functional value addition infrastructure in place | Outcome Indicator 1: Completion status of the grain processing facility | 80 | 90 | 93 | 95 | 97 | Annual District production and Marketing report |
|  |  | Outcome Indicator 2: Completion status of the mini-dairy processing plants | 80 | 90 | 93 | 95 | 97 | Annual District production and Marketing report |
|  |  | Outcome Indicator 3: Number of domestic feed processors supported to produce quality fish feed | 5 | 10 | 15 | 20 | 25 | Annual District production and Marketing report |
|  | Intermediate Outcome 2.4: Value addition infrastructure and equipment Operationalised | Outcome Indicator 1: Semi-annual assessment report on agro processing and value addition facilities assessed and equipped | 2 | 2 | 2 | 2 | 2 | Annual District production and Marketing report |
|  |  | Outcome Indicator 2: Number of functional agro-processing and value addition infrastructure | 5 | 10 | 15 | 20 | 25 | Annual District production and Marketing report |
|  | Intermediate Outcome 2.5: Value chain actors supported with value addition equipment | Outcome Indicator 1: Number of value chain actors supported with value addition and agro processing equipment | 5 | 10 | 15 | 20 | 25 | Annual District production and Marketing report |
|  | Intermediate Outcome 2.6: Reduce subsistence farming | Outcome Indicator 1: Percentage of households dependent on subsistence Agriculture as the main source of livelihood | 25 | 20 | 15 | 10 | 5 | Annual District production and Marketing report |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention 1.1 (d) | Output 1.1.1: Fertilizer usage Promoted | Output Indicator 1: Number of bags of clean coffee produced per year | 800 | 816.66 | 866.67 | 900 | 950 | District Production Department |
|  |  | Output Indicator 2: Number of farmers receiving subsidies | 1,545 | 1604 | 1671 | 1746 | 1834 | District Production Department |
|  |  | Output Indicator 3: Number of fertilizer dealers and premises registered | 103 | 107 | 111 | 116 | 122 | District Production Department |
|  |  | Output Indicator 4: Number of MoUs with private sector actors signed | 5 | 5 | 6 | 6 | 6 | District Production Department; Private Sector |
| Intervention 1.2 (d) Produce, multiply and distribute quality seed and inputs | Output 1.2.1: Agricultural inputs on the market quality assured | Output Indicator 1: Number of crop compliance certificates issued (agro-chemicals dealers, premises) | 103 | 107 | 111 | 116 | 122 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of farmer groups provided with small scale irrigation equipment | 10 | 12 | 15 | 20 | 25 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Number of farmer groups provided with fish fingerlings | 28 | 29 | 30 | 31 | 33 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Number of farmer groups provided with coffee seedlings | 58 | 59 | 61 | 64 | 70 | District Production Department; MAAIF |
|  |  | Output Indicator 5: Number of farmer groups provided with Hass ovacado | 10 | 12 | 13 | 14 | 15 | District Production Department; MAAIF |
|  |  | Output Indicator 6: Number of farmer groups provided with goats, heifers, piglets, chicks, tissue cultured bananas | 10 | 11 | 12 | 14 | 16 | District Production Department; MAAIF |
|  |  | Output Indicator 7: Number of livestock compliance certificates issued | 5 | 10 | 15 | 20 | 22 | District Production Department |
|  | Output 1.2.2: Production of quality seed increased | Output Indicator 1: No. of exotic animal breeds introduced | 5153 | 5349 | 5574 | 5825 | 6087 | District Production Department; MAAIF |
|  |  | Output Indicator 2: No. of farming households trained on quality seed production | 5153 | 5349 | 5574 | 5825 | 6087 | District Production Department; MAAIF |
|  |  | Output Indicator 3: No. of fish ponds and attendant fish hatcheries established | 385 | 400 | 417 | 436 | 458 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Number of Coffee mother gardens established in the district | 4 | 5 | 6 | 7 | 8 | District Production Department; MAAIF |
|  |  | Output Indicator 5: Number of farmers trained in Zero grazing units establishment | 82 | 85 | 89 | 93 | 98 | District Production Department |
|  |  | Output Indicator 6: Number of coffee nursery operators trained | 4 | 5 | 6 | 7 | 8 | District Production Department |
|  | Output 1.2.3: Quality seed and agricultural inputs accessed | Output Indicator 1: No. of animal feed acreage planted | 618 | 641 | 669 | 699 | 734 | District Production Department |
|  |  | Output Indicator 2: No. of farming households supported with critical agricultural inputs for strategic priority crops | 7210 | 7484 | 7798 | 8149 | 8556 | District Production Department; MAAIF |
|  |  | Output Indicator 3: No. of farming households supported with critical agricultural inputs for strategic priority livestock | 7275 | 7493 | 7778 | 8105 | 8510 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Number of farmer field days/and agricultural shows organized | 58 | 60 | 63 | 66 | 69 | District Production Department; MAAIF |
|  |  | Output Indicator 5: Number of coffee farmers trained on Gender aware Plans | 6180 | 6415 | 6684 | 6985 | 7334 | District Production Department; MAAIF |
|  |  | Output Indicator 6; Number of smallholder households supported | 2060 | 2138 | 2228 | 2328 | 2444 | District Production Department; MAAIF |
| Intervention 1.3 (d): Strategically invest in the fisheries sub-sector and aquaculture development | Output 1.3.1: Quality assurance for aquaculture and capture fisheries | Output Indicator 1: Number of fish quality-related inspections and certifications made | 52 | 54 | 56 | 59 | 62 | District Production Department |
|  |  | Output Indicator 2: Number of cold chain trucks/tuktuks acquired for farmer groups/farmer cooperatives | 1 | 2 | 3 | 4 | 5 | District Production Department; MAAIF |
| Intervention 1.4 (d): Support to large scale commercial farming entities | Output 1.4.1: Production capacity of large scale commercial farmers expanded | Output Indicator 1: Number of solar powered irrigation demonstrations established | 6 | 8 | 10 | 12 | 14 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of tractors with assorted implements acquired | 2 | 3 | 4 | 5 | 6 | District Production Department; MAAIF |
|  |  | Output Indicator 3: No. of medium & large scale commercial farms supported | 2 | 4 | 6 | 8 | 10 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Number of large land owners supported to plant coffee | 5 | 7 | 9 | 11 | 14 | District Production Department; MAAIF |
| Intervention 1.5 (d): Increase access to and use of water for agricultural production | Output 1.5.1: Facilities, equipment and machinery managed and maintained | Output Indicator 1: Number of water for production facilities managed and maintained | 15 | 20 | 25 | 30 | 35 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of value addition and tractors managed and maintained | 5 | 5 | 6 | 7 | 8 | District Production Department; MAAIF |
|  | Output 1.5.2: On-farm water for production infrastructure established | Output Indicator 1: Number of solar powered small scale water for production systems for demonstration established | 10 | 12 | 14 | 16 | 18 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of valley dams constructed | 2 | 3 | 3 | 5 | 10 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Number of micro-irrigation systems established | 80 | 90 | 100 | 110 | 120 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Number of solar powered small-scale irrigation systems constructed | 10 | 12 | 14 | 16 | 18 | District Production Department; MAAIF |
|  |  | Output Indicator 5: Number of Rain water harvesting infrastructures established | 5 | 10 | 15 | 20 | 25 | District Production Department; MAAIF |
|  | Output 1.5.3: Research - Extension - Farmer linkages strengthened | Output Indicator 1: Number of extension staff retooled with new skills | 40 | 45 | 50 | 55 | 60 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of Parish level agricultural technology demonstrations established | 57 | 114 | 171 | 171 | 171 | District Production Department |
|  |  | Output Indicator 3: Number of Micro scale irrigation projects established and supported | 80 | 90 | 100 | 110 | 120 | District Production Department; MAAIF |
|  | Output 1.5.4: Sustainable land, water and soil management strengthened | Output Indicator 1: Kms of conservation structures constructed/ established by type | 10 | 20 | 30 | 40 | 50 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of demonstration sites established for soil and water conservation technologies and water catchment management across all the water for production facilities sites. | 100 | 120 | 120 | 120 | 120 | District Production Department; ,MAAIF |
|  |  | Output Indicator 3: Number of soil testing kits procured and distributed to extension staff | 14 | 14 | 14 | 14 | 14 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Number of extension staff trained in SLM technologies | 67 | 67 | 67 | 67 | 67 | District Production Department; MAAIF |
| Intervention 1.6 (d): Increase access to appropriate agricultural mechanization and farm power | Output 1.6.1: Agricultural mechanization services improved | Output Indicator 1: Acreage of bush cleared and ploughed (ha) for PDM beneficiary groups | 100 | 120 | 200 | 300 | 400 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of sets of tractors managed and maintained | 6 | 10 | 20 | 25 | 30 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Number of tractor users, operators and technicians trained | 6 | 10 | 20 | 25 | 30 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Number of dairy farmer groups/cooperatives supported with demonstration dairy machinery | 1 | 2 | 3 | 4 | 5 | District Production Department; MAAIF |
| Intervention 1.7 (d): Strengthen farmer organizations and cooperatives ecosystems | Output 1.7.1: Functionality and sustainability of farmer groups, MSMEs and cooperatives improved | Output Indicator 1: Number of farmer groups, MSMEs and cooperatives trained in post-harvest handling and value addition | 57 | 114 | 171 | 171 | 228 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of farmers trained on PDM enterprise selection and management | 2000 | 2200 | 2400 | 2900 | 3200 | District Production Department; MAAIF |
|  |  | Output Indicator 3: No. of farmer groups, MSME, Cooperatives supported with inputs (animal feed processing equipment, post-harvest handling and value addition equipment, water harvesting equipment, production enhancement equipment ) | 5 | 10 | 15 | 20 | 25 | District Production Department; MAAIF |
| Intervention 1.8 (d): Pest and disease control | Output 1.8.1: Pest, vector and disease diagnosis and control capacity enhanced | Output Indicator 1: Area (km²) freed from Tsetse infestation and Trypanosomiasis | 150 | 200 | 300 | 400 | 500 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Doses of the anti-tick vaccines procured (million doses) | 0.003 | 0.005 | 0.006 | 0.007 | 0.008 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Doses of the Foot and Mounth Disease vaccines procured (million doses) | 0.003 | 0.005 | 0.006 | 0.007 | 0.008 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Integrated pest and disease management packages | 200 | 300 | 400 | 500 | 600 | District Production Department; MAAIF |
|  |  | Output Indicator 5: Number of apiculture establishments inspected | 150 | 200 | 250 | 300 | 400 | District Production Department; MAAIF |
|  |  | Output Indicator 6: Number of Extension Staff trained in Integrated Pest, Vector and disease control | 70 | 75 | 75 | 75 | 75 | District Production Department; MAAIF |
|  |  | Output Indicator 7: Number of diagnostic kits, tools and equipment procured | 28 | 30 | 40 | 50 | 60 | District Production Department; MAAIF |
|  |  | Output Indicator 8: Number of Extension Staff trained in Integrated Pest, Vector and disease control | 70 | 75 | 75 | 75 | 75 | District Production Department; MAAIF |
|  |  | Output Indicator 9: Number of Households supported with pest, vector and disease control inputs | 70 | 100 | 150 | 200 | 400 | District Production Department; MAAIF |
|  |  | Output Indicator 10: Number of vacccine doses acquired (million doses) | 0.003 | 0.005 | 0.006 | 0.007 | 0.008 | District Production Department; MAAIF |
|  | Output 1.8.2: Pest, vector and disease diagnosis and control infrastructure established | Output Indicator 1: Completion status of the Laboratory infrastructure | 70 | 80 | 90 | 95 | 100 | District Production Department; MAAIF |
| Intervention 1.9 (d): Strengthen the agricultural extension system | Output 1.9.1: Agricultural extension system digitalized | Output Indicator 1: Number of mass media shows undertaken(Hold radio, Television talk shows and baraazas in delivery of specialised agriculture extension services for livestock, fishereis and crops) | 4 | 4 | 4 | 4 | 4 | District Production Department; MAAIF |
|  |  | Output Indicator 2: ICT-enabled extension supervision system enabled | 50 | 60 | 70 | 75 | 78 | District Production Department; MAAIF |
|  | Output 1.9.2: Farmers mobilised, sensitised and trained | Output Indicator 1: Number of farmers supported through the nucleus farms | 1000 | 105 | 115 | 120 | 125 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of hectares acquired | 100 | 200 | 300 | 400 | 500 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Number of Urban farmers supported | 10 | 15 | 20 | 25 | 30 | District Production Department; MAAIF |
| Intervention 1.10 (d): Promote climate adaptation and mitigation practices | Output 1.10.1: Climate smart agricultural practices undertaken | Output Indicator 1: Kilogrammes of cover crop seeds distributed | 500 | 1000 | 1500 | 2000 | 2500 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of of trees planted | 1000 | 1500 | 2000 | 2500 | 3000 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Number of dairy farmers trained | 30 | 40 | 50 | 60 | 70 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Number of dairy farmer linked to green financing institutions | 30 | 40 | 50 | 60 | 70 | District Production Department; MAAIF |
|  |  | Output Indicator 5: Number of farming households using biogas system | 15 | 20 | 25 | 30 | 35 | District Production Department; MAAIF |
|  |  | Output Indicator 6: Number of youth groups engaged in commercial fodder production and conservation | 5 | 10 | 15 | 20 | 25 | District Production Department; MAAIF |
|  |  | Output Indicator 7: Number of Environment Social Impact Assessments, Audits and compliance enforcements. | 10 | 15 | 20 | 25 | 30 | District Production Department; MAAIF |
| Intervention 2.1 (d): Provide appropriate harvest, post-harvest handling and storage technologies | Output 2.1.1: Harvest, post-harvest handling and storage technologies developed and promoted | Output Indicator 1: Number of farmers and other actors supported with appropriate post -harvest handling technologies | 1030 | 1068 | 1114 | 1164 | 1222 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of postharvest handling, processing and storage technologies developed | 31 | 32 | 33 | 35 | 36 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Number of agro-machinery procured | 10 | 11 | 12 | 13 | 15 | District Production Department; MAAIF |
|  | Output 2.1.2: Harvest, post-harvest handling and storage infrastructure established | Output Indicator 1: Completion status of the storage infrastructure | 75% | 80% | 85% | 90% | 100% | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of fish post-harvest handling facilities constructed or rehabilitated | 2 | 3 | 3 | 4 | 6 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Number of post-harvest handling and storage infrastructure established | 2 | 3 | 3 | 4 | 6 | District Production Department; MAAIF |
|  | Output 2.1.3: Value chain actors supported with post-harvest handling equipment | Output Indicator 1: Number of post-harvest handling and storage equipment distributed | 10,017 | 10,025 | 10,035 | 10,045 | 10,055 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of value chain actors supported with post-harvest handling equipment | 10,000 | 10,020 | 10,030 | 10,040 | 10,050 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Profile of existing storage facilities | 7 | 8 | 9 | 10 | 11 | District Production Department; MAAIF |
| Intervention 2.2 (d): Invest in appropriate agro-processing and value addition technologies | Output 2.2.1: Agro-processing and value addition technologies promoted | Output Indicator 1: Number of farmer groups and other actors supported with appropriate agro-processing and value addition technologies | 10 | 12 | 13 | 14 | 15 | District Production Department; MAAIF |
| Intervention 2.3 (d): Establish and maintain appropriate market infrastructure | Output 2.3.1: Marketing infrastructure established and maintained | Output Indicator 1: Number of slaughter facilities constructed | 2 | 2 | 3 | 4 | 5 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Kms of agricultural access roads constructed | 200 | 300 | 400 | 500 | 600 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Number of Livestock markets constructed | 1 | 1 | 1 | 1 | 1 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Number of livestock markets equipped with appropriate disease control infrastructure | 2 | 2 | 2 | 2 | 2 | District Production Department; MAAIF |
|  | Output 2.3.2: Increase access to agricultural insurance | Output Indicator 1: Proportion of farmers with access to agricultural finance(%) | 20 | 25 | 30 | 40 | 45 | District Production Department; MAAIF |
| Intervention 2.4 (d): Scale up agricultural Insurance | Output 2.4.1: Access and uptake of agriculture insurance increased | Output Indicator 1: Number of farmer interface (million farmers) | 0.0005 | 0.0003 | 0.0004 | 0.0005 | 0.0006 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of insured farmers | 0.0005 | 0.0003 | 0.0004 | 0.0005 | 0.0006 | District Production Department; MAAIF |
| Intervention 2.5 (d): Improve administrative infrastructure and human resource | Output 2.5.1: Agricultural research, training institutions and international offices strengthened | Output Indicator 1: District Production and marketing office functional | 100 | 100 | 100 | 100 | 100 | District Production Department; MAAIF |
|  | Output 2.5.2: Human resource management strengthened | Output Indicator 1: Number of agricultural staff trained | 70 | 70 | 70 | 70 | 70 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of staff trainings conducted | 70 | 70 | 70 | 70 | 70 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Percentage of the approved staff structure filled | 76.67% | 80 | 85 | 86 | 90 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Salaries for staff paid | 100 | 100 | 100 | 100 | 100 | District Production Department; MAAIF |
|  | Output 2.5.3: Improve the regulatory framework | Output Indicator 1: Percentage of policies with implementation frameworks | 10 | 20 | 23 | 23 | 24 | District Production Department; MAAIF |
| Intervention 2.6 (d): Improve policy, legal and institutional framework in agro-industry | Output 2.6.1: Administration, Governance and support services enhanced | Output Indicator 1: Administrative overheads managed | 75 | 80 | 85 | 90 | 95 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Annual disposal plan prepared | 100 | 100 | 100 | 100 | 100 | District Production Department; MAAIF |
|  | Output 2.6.2: Communication and public relations managed | Output Indicator 1: ICT systems maintained | 100 | 100 | 100 | 100 | 100 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of private sector dairy organizations supported | 2 | 4 | 6 | 8 | 10 | District Production Department; MAAIF |
|  | Output 2.6.3: Cross cutting issues mainstreamed in agro-industry | Output Indicator 1: Number of beneficiaries reached | 1000 | 1200 | 1300 | 1500 | 1700 | District Production Department; MAAIF |
|  | Output 2.6.4: Financial and accounting management enhanced | Output Indicator 1: An updated vote asset register in place | 100 | 100 | 100 | 100 | 100 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Quarterly and annual financial statements prepared | 100 | 100 | 100 | 100 | 100 | District Production Department; MAAIF |
|  | Output 2.6.5: Agro-Industrialization statistics strengthened | Output Indicator 1: Annual Agricultural Abstracts developed and disseminated | 100 | 100 | 100 | 100 | 100 | District Production Department; MAAIF |
|  | Output 2.6.6: Monitoring and evaluation enhanced | Output Indicator 1: Number of monitoring and evaluation reports compiled | 4 | 4 | 4 | 4 | 4 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of coordination meetings convened | 12 | 12 | 12 | 12 | 12 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Annual Review conducted | 100 | 100 | 100 | 100 | 100 | District Production Department; MAAIF |
|  | Output 2.6.7: Planning and budgeting enhanced | Output Indicator 1: Budget documents in place | 100 | 100 | 100 | 100 | 100 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of bankable development projects prepared | 2 | 2 | 2 | 2 | 2 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Annual work plans in place | 100 | 100 | 100 | 100 | 100 | District Production Department; MAAIF |
| Project 1: Improvement in the production and productivity of priority commodities project | Project Output: The production and productivity of priority commodities improved | Output Indicator 1: Number of bags of clean coffee produced per year | 800 | 816.66 | 866.67 | 900 | 950 | District Production Department; MAAIF |
|  |  | Output Indicator 2: Number of farmers receiving subsidies | 1,545 | 1604 | 1671 | 1746 | 1834 | District Production Department; MAAIF |
|  |  | Output Indicator 3: Number of fertilizer dealers and premises registered | 103 | 107 | 111 | 116 | 122 | District Production Department; MAAIF |
|  |  | Output Indicator 4: Number of Memorandum of understanding with private sector actors signed | 5 | 5 | 6 | 6 | 6 | District Production Department; MAAIF |
|  |  | Output Indicator 5: Number of crop compliance certificates issued (agro-chemicals dealers, premises) | 103 | 107 | 111 | 116 | 122 | District Production Department; MAAIF |
|  |  | Output Indicator 6: Number of farmer groups provided with small scale irrigation equipment | 10 | 12 | 15 | 20 | 25 | District Production Department; MAAIF |
|  |  | Output Indicator 7: Number of farmer groups provided with fish fingerlings | 28 | 29 | 30 | 31 | 33 | District Production Department; MAAIF |

Strategic Objective 1: Sustainably increase production, productivity and value addition in agriculture, minerals, oil & gas, tourism, ICT and financial services

## Programme: Tourism Development

Development Issue: Low levels of Tourism Development in the District

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective (1): Develop, conserve and diversify tourism products | Outcome 1.1: Increased tourism sector competitiveness; | Outcome Indicator 1: number quality services hospitality facilities | 5 | 5 | 5 | 5 | 7 | Reports from Commercial Department |
| Programme Objective (2): Develop a pool of skilled personnel along the tourism value chain | Outcome 2.1: Increased skilled personnel along the tourism value chain | Outcome Indicator 1: Number of Tourism service Providers trained. | 10 | 10 | 10 | 10 | 10 | Reports from Commercial Department |
|  |  | Outcome Indicator 2: Number of tourism campaigns conducted. | 1 | 1 | 1 | 1 | 1 | Reports from Commercial Department |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme: (1) Infrastructure, Product Development and Conservation | Intermediate Outcome 1.1: Increased tourist attractive sites. | Outcome Indicator 1: Number of tourism sites identified | 5 | 5 | 5 | 5 | 7 | Reports from Commercial Department |
|  |  | Outcome Indicator 2: Number of tourism sites profiled | 5 | 5 | 5 | 5 | 7 | Reports from Commercial Department |
| Sub Programme: (2) Regulation and Skills Development | Intermediate Outcome 1.1: Tourism service providers identified | Outcome Indicator 1: Number of service providers identified | 10 | 10 | 10 | 10 | 10 | Reports from Commercial Department |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention 1.1 (d) Mobilizing and sensitizing the public and private sectors about tourism activities | Output 1.1.1: Radio talk shows | Output Indicator 1: Number of radio talk shows conducted | 4 | 4 | 4 | 4 | 4 | District Commercial Department |
|  | Output 1.1.2: Awareness meetings | Output Indicator 1: Number of awareness meetings conducted | 4 | 4 | 4 | 4 | 4 | District Commercial Department |
|  | Output 1.1.3: Miss Kibaale Tourism Event organised | Output Indicator 1: Number of Miss Kibaale Tourism Event organised | 1 | 1 | 1 | 1 | 1 | District Commercial Department; Private Sector |
| Intervention 1.2 (d) Identifying and profiling of tourism sites | Output 1.2.1: Tourism sites identified | Output Indicator 1: Number of tourism sites identified | 5 | 5 | 5 | 5 | 7 | District Commercial Department; Private Sector |
|  | Output 1.2.2: Tourism sites profiled | Output Indicator 1: Number of tourism sites profiled | 5 | 5 | 5 | 5 | 7 | District Commercial Department; Private Sector |
| Intervention 2.1 (d) On-job Training of Tourism Service Providers | Output 2.1.1: Service Providers trained on - job | Output Indicator 1: Number of Service Providers trained on - job | 10 | 10 | 10 | 10 | 10 | District Commercial Department; Private Sector |
| Project 1: Not applicable | Project Output: Not applicable | Output Indicator 1: Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable |

Strategic Objective 4: Sustainably increase production, productivity and value addition in agriculture, minerals, oil & gas, tourism, ICT and financial services

Programme: Water, Climate Change and Environment and Natural Resource Management

Development Issues:

- Degradation of natural resources

- Low quantity and quality of social services

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective (1): Protect, restore and add value to forests and wetlands | Outcome 1.1: Increased forest and wetland cover for socio-economic and ecological benefits | Outcome Indicator 1: Percentage of land area covered by forests | 62 | 64 | 66 | 68,. | 70 | Reports from the District ENR Department |
|  |  | Outcome Indicator 2: Percentage of land area covered by wetlands | 7 | 7.5 | 8 | 8.5 | 9 | Reports from the District ENR Department |
| Programme Objective (2): To ensure a clean, healthy and productive environment | Outcome 2.1: Improved well-being, a sustainable and productive environment | Outcome Indicator 1: Number of green jobs | 20 | 20 | 20 | 20 | 20 | Reports from the District ENR Department |
| Programme Objective (3): To strengthen policy, legal, regulatory and coordination frameworks | Outcome 1.1: Increased attainment of sustainable results of the programme | Outcome Indicator 1: Number of programme outcomes achieved | 100 | 100 | 100 | 100 | 100 | Reports from the District ENR Department |
| Programme Objective (4): Strengthen land use management | Outcome 1.1: Improved land tenure security | Outcome Indicator 1: Proportion of total adult population with secure tenure rights to land, with legally recognized documentation | 10 | 20 | 30 | 35 | 50 | Reports from the District ENR Department |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme: (1): Environment and Natural Resources Management | Intermediate Outcome 1.1: Reduced area of degraded forests and landscapes | Outcome Indicator 1: Area (ha) of degraded forest and degraded landscapes restored | 100 | 100 | 100 | 100 | 100 | Reports from the District ENR Department |
|  | Intermediate Outcome 1.2: Reduced area of degraded wetlands | Outcome Indicator 2: Percentage reduction in area of degraded wetland | 40 | 35 | 30 | 25 | 20 | Reports from the District ENR Department |
|  | Intermediate Outcome 2.1:Increased environmentally sustainable technologies and practices for social economic transformation | Outcome Indicator: Percentage of ESIA certificate holders complying with ESIA conditions | 100 | 100 | 100 | 100 | 100 | Reports from the District ENR Department |
|  | Intermediate Outcome 3.1:Improved planning and implementation capacity | Outcome Indicator 1: Percentage of programme outputs achieved within the designated time frame | 100 | 100 | 100 | 100 | 100 | Reports from the District ENR Department |
| Sub Programme: (2): Land Management | Intermediate Outcome 2.1:Increased registration of land | Outcome Indicator 1: Land Surveyed (%) | 30 | 15 | 20 | 15 | 20 | Reports from the District ENR Department |
|  |  | Outcome Indicator 2: Land Registered (%) | 10 | 20 | 30 | 20 | 30 | Reports from the District ENR Department |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention 1.1 (d): Increasing forest and wetland cover for socio-economic and ecological benefits | Output 1.1.1: Degraded landscapes restored | Output Indicator 1: Area (ha) of degraded landscapes restored | 100 | 100 | 100 | 100 | 100 | District LLGs MoWE |
| Intervention 1.2 (d): Protect and increase the wetland cover | Output 1.2.1: Gender responsive wetland management plans and district wetland action plans developed and implemented. | Output Indicator 1: Area (ha) of wetlands under management plans | 5 | 5 | 5 | 5 | 5 | District LLGs |
|  | Output 1.2.2: Wetland alternative livelihood options promoted and supported | Output Indicator 1: Number of households supported with alternative livelihood options | 40 | 40 | 40 | 40 | 40 | District LLGs GoU |
|  | Output 1.2.3: Wetland boundaries surveyed and demarcated | Output Indicator 1: Length (Km) of wetlands boundaries demarcated. | 5 | 5 | 5 | 5 | 5 | District, LLGs MoWE |
|  | Output 1.2.4: Degraded wetlands and river banks restored | Output Indicator 1: Area (Ha) of wetlands and riverbanks restored | 10 | 10 | 10 | 10 | 10 | District LLGs MoWE |
| Intervention 1.3 (d): Undertake natural resource valuation and accounting to establish existing stocks, ecosystem values and future demands | Output 1.3.1: Interventions to halt degradation of wetland resources established and implemented | Output Indicator 1: Number of compliance and enforcement actions undertaken | 14 | 14 | 14 | 14 | 14 | District LLGs MoWE |
| Intervention 2.1 (d): Strengthen regulation and enforcement against environmental pollution and degradation | Output 2.1.1: Regulation and enforcement against environmental degradation strengthened | Output Indicator 1: Number of Projects screened, Environmental and Social Management Plan, environmental and social impact assessments processed | 25 | 25 | 25 | 25 | 25 | District MoWE |
|  |  | Output Indicator 2: Number environmental compliance monitoring and inspections carried out | 10 | 10 | 10 | 10 | 10 | District MoWE |
| Intervention 3.1 (d): Strengthen planning, supervision, monitoring, evaluation and human resource capacity of the Programme | Output 3.1.1: Human resource requirements and capacity development of the Programme undertaken | Output Indicator 1: Wages paid | 12 | 12 | 12 | 12 | 12 | District; MoPS; MoFPED |
|  |  | Output Indicator 2: Number of staff recruited to fill vacant positions | 1 | 0 | 0 | 0 | 0 | District; MoPS; MoFPED |
| Intervention 3.2 (d): Integrate crosscutting issues in the programme | Output 3.2.1: Crosscutting issues mainstreamed in the programme. | Output Indicator 1: Number of Gender mainstreaming interventions implemented. | 4 | 4 | 4 | 4 | 4 | DCDO; DNRO |
|  |  | Output Indicator 2: Number of HIV/AIDS mainstreaming interventions undertaken | 2 | 2 | 2 | 2 | 2 | DNRO DHO |
| Intervention 4.1 Undertake Land Tenure Security Enhancement Programmes | Output 1.1.1: Mass land registration programmes implemented | Output Indicator 1: Hectares of Government land titled | 5 | 5 | 5 | 5 | 5 | District MoWE |
| Project 1: Not applicable | Project Output: Not applicable | Output Indicator 1: Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable |

Strategic Objective 2: Enhance human capital development along the entire life cycle

Programme: Human Capital Development

Development Issues:

- Low quantity and quality of social services

- High population growth rate

- Limited participation of marginalized groups in income generating projects

- Gender imbalances

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective (1): Improve the foundation for human capital development | Outcome 1.1: Improved child wellbeing and development | Outcome Indicator 1: Infant Mortality Rate | 42 | 40 | 39 | 38 | 35 | Reports from Health Surveys |
|  | Outcome 1.2: Improved Health and wellbeing of the population | Outcome Indicator 1: % of Prevalence of stunting among children under 5 | 25 | 20 | 15 | 13 | 10 | Health survey reports |
|  |  | Outcome Indicator 2: Under Five Mortality Rate (per 1,000 live births) | 60 | 58 | 56 | 54 | 52 | Reports from Health Surveys |
|  |  | Outcome Indicator 3: Maternal Mortality Ratio (per 100,000 live births) | 207 | 180 | 140 | 130 | 120 | Reports from Health Surveys |
|  |  | Outcome Indicator 4: Unmet Need for Family Planning Services among currently married women (%) | 24 | 20 | 15 | 13 | 10 | Reports from Health Surveys |
|  |  | Outcome Indicator 5: Contraceptive Prevalence Rate | 46 | 52 | 60 | 70 | 80 | Reports from Health Surveys |
|  |  | Outcome Indicator 6: % of mortality rate attributed to cardiovascular disease, cancer, diabetes or chronic respiratory disease between 30 - 70 years | 7 | 6 | 5 | 4 | 3 | Reports from Health Surveys |
|  |  | Outcome Indicator 7: Mortality attributed to communicable diseases (Malaria, TB & HIV/AIDS) (%) | 10 | 8 | 6 | 4 | 2 | Reports from Health Surveys |
|  |  | Outcome Indicator 8: Teenage pregnancy rate (%) | 25 | 20 | 15 | 10 | 5 | HMIS |
|  |  | Outcome Indicator 9: Knowledge of HIV among the youth (%) | 74 | 79 | 85 | 90 | 95 | Reports from Health Surveys |
|  |  | Outcome Indicator 10: Number of new HIV infections per 1,000 susceptible population | 25 | 20 | 18 | 16 | 15 | HMIS |
|  |  | Outcome Indicator 11: Malaria Incidence (per 1,000 population at risk) | 500 | 400 | 300 | 200 | 100 | HMIS |
|  |  | Outcome Indicator 12: Tuberculosis incidence (per 100,000 population) | 115 | 102 | 89 | 76 | 50 | HMIS |
|  |  | Outcome Indicator 13: % of Population with access to basic sanitation (improved toilet) (Urban) | 65 | 70 | 75 | 80 | 100 | Reports from environmental Health |
|  |  | Outcome Indicator 14: % of Population with access to basic sanitation (improved toilet) (Rural) | 65 | 70 | 75 | 80 | 100 | Reports from environmental Health |
|  |  | Outcome Indicator 15: % of Population with access to improved hygiene - handwashing facilities with soap and water (Urban) | 10 | 15 | 20 | 30 | 50 | Reports from environmental Health |
|  |  | Outcome Indicator 16: % of Population with access to improved hygiene - handwashing facilities with soap and water (Rural) | 10 | 15 | 20 | 30 | 50 | Reports from environmental Health |
|  |  | Outcome Indicator 17: % of population with access to safe water | 68 | 69 | 69.5 | 70 | 70 | Environmental health and sanitation reports |
|  |  | Outcome Indicator 18: % of population with access to improved sanitation | 65 | 70 | 75 | 80 | 100 | Reports from environmental Health |
|  |  | Outcome Indicator 19: % of the population with access to basic hygiene services | 10 | 15 | 20 | 30 | 50 | Reports from environmental Health |
|  | Outcome 1.3: Improve access and quality of basic education | Outcome Indicator 1: Gross Enrolment rates at Primary (%) | 65 | 70 | 75 | 80 | 90 | UBOS and school inspection reports, EMIS |
|  |  | Outcome indicator 2: Net Enrolment Rates at Primary (%) | 60 | 65 | 70 | 75 | 85 | UBOS and school inspection reports, EMIS |
|  |  | Outcome Indicator 3: Transition rates from primary to lower secondary education (%) | 30 | 40 | 50 | 60 | 70 | UBOS reports School inspection reports UNEB reports |
|  |  | Outcome indicator 4: Completion Rates at P.7 (%) | 60 | 65 | 70 | 80 | 90 | UNEB reports School inspection reports |
|  | Outcome 1.4: Improved pupil/student learning outcomes | Out come indicator 1: Proportion of pupils achieving proficiency in literacy (%) | 72 | 73 | 75 | 80 | 90 | Inspection reports NAPE reports |
|  |  | Out come indicator 2: Proportion of learners achieving proficiency in numeracy (%) | 70 | 72 | 74 | 78 | 85 | Inspection reports NAPE reports |
|  |  | Out come indicator 3: Survival rates at Primary 7 (%) | 30 | 40 | 50 | 60 | 70 | Inspection reports EMIS; PLE reports/data |
| Programme Objective 2: To Promote Sports, Recreation and Physical Education | Outcome 2.1: Increased participation in sports, recreation and physical education | Outcome Indicator 1. Percentage increase in athletes participating in competitions | 65% | 70% | 75% | 80% | 85% | Activity reports |
| Programme Objective 3: To promote decent work and productive employment | Outcome 3.1: Improved productive employment and decent work for all | Outcome Indicator 1: Number of workplaces reporting Occupational injuries and diseases | 20 | 25 | 30 | 35 | 40 | Labour case register |
|  |  | Outcome Indicator 2: Number of inspected work places compliant with labour standards | 21 | 27 | 32 | 38 | 46 | Inspection Reports |
|  |  | Outcome Indicator 3: Proportion of children aged 5-17 years engaged in child Labour excluding household chores aggregated by sex, tribe and disability. | 250 | 200 | 150 | 100 | 50 | Inspection Reports |
| Programme Objective 4: Reduce vulnerability, gender inequality and inequity along the lifecycle | Outcome 4.1: Reduced vulnerabilities, inequity and gender inequality | Outcome Indicator 1: Average number of hours a week spent on un-paid care work by sex | 30 | 27 | 25 | 22 | 20 | findings from labour office |
| Programme Objective 5: To mobilize communities for increased participation in national development. | Outcome 5.1: Empowered and engaged Ugandan communities that actively address their social issues, promote equitable practices, and embrace positive behavioral changes for improved well-being and resilience | Outcome Indicator 1: Proportion of special interest groups (e.g. youth, women, PWDs, older persons) benefiting in national development initiatives i.e. PDM, YLP/UWEP, Emyooga, Bunyoro Micro projects support, GROW etc (%) | 15 | 20 | 25 | 30 | 35 | District Annual reports |
|  |  | Outcome Indicator 2: Perception that harmful practices (e.g. child marriage, domestic violence, GBV, etc) are socially acceptable within the community (%) | 40 | 35 | 20 | 25 | 20 | Case management records |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme 1: Population Health, Safety and Management | Intermediate Outcome 1.1: Improved utilization of health services | Per Capita OPD attendance | 0.6 | 0.7 | 0.8 | 0.9 | 1 | HMIS |
|  |  | Hospital (public & private) admission rate (per 1,000 population) | 50 | 55 | 60 | 60 | 65 | HMIS |
|  |  | Bed Occupancy Rate (%) | 50 | 60 | 70 | 72 | 73 | HMIS |
|  |  | HIV Viral Load Suppression rate among Persons Living with HIV/AIDS | 80 | 85 | 90 | 95 | 95 | HMIS |
|  |  | TB case notification rate/100,0000 | 80 | 85 | 90 | 95 | 95 | HMIS |
|  |  | DPTHibHep 3rd dose coverage (%) | 90 | 92 | 96 | 97 | 97 | HMIS |
|  |  | ANC 4th Visit Coverage (%) | 52 | 55 | 60 | 60 | 65 | HMIS |
|  |  | Deliveries in health facilities (%) | 52 | 55 | 58 | 62 | 65 | HMIS |
|  |  | Service availability and readiness index (%) | 45 | 50 | 55 | 60 | 65 | Health survey reports |
| Sub Programme 2: Education, Sports and Skills | Intermediate Outcome 2.1: Increased access to quality and inclusive pre-primary education | Outcome Indicator 1. Percentage increase in enrolment in Early Child Care and Education-ECCE | 10 | 20 | 30 | 40 | 50 | Inspection reports, enrolment data |
|  | Intermediate Outcome 2.2: Improved learning, instruction and learning environments at basic education | Outcome Indicator 1: Improved teacher pupil ratio | 1:65 | 1:62 | 1:58 | 1:55 | 1:53 | Inspection reports, Asset registers |
|  |  | Outcome Indicator 2: Improved learner to classroom ratio | 85:1 | 80:1 | 75:1 | 70:1 | 65:1 | Inspection reports, Asset registers |
|  |  | Outcome Indicator 3: Proportion of teachers of Primary School with the minimum required qualifications(%) | 30 | 40 | 50 | 60 | 70 | EMIS TMIS Inspection reports |
|  |  | Outcome Indicator 4: Percentage of classrooms equipped with adequate furniture | 40 | 50 | 60 | 70 | 80 | Inspection reports, Asset registers |
|  |  | Outcome Indicator 5: Improved pupil teacher ratio for blind, deaf learners and other disabilities | 100:1 | 90:1 | 80:1 | 70:1 | 60:1 | EMIS; Inspection reports |
|  | Intermediate Outcome 2.3: Enhanced talent development and professionalization in sports | Outcome Indicator 1: Number of athletes participating in competitions | 1000 | 1000 | 1000 | 1000 | 1000 | Reports on sports activities |
|  |  | Outcome Indicator 2: Number of sports federations adopting formal professional structures | 2 | 2 | 2 | 2 | 2 | Sports reports |
| Sub Programme 3: Labour and Employment Services | Intermediate Outcome 3.1: Employment opportunities, safety and Compliance to labour standards increased | Number of compensation cases followed up | 7 | 8 | 10 | 12 | 14 | Case management records |
|  |  | Sets of minutes for quarterly stakeholders’ meetings on labour related matters organized | 4 | 4 | 4 | 4 | 4 | Sets of minutes |
| Sub Programme 4: Gender and Social Protection | Intermediate Outcome 4.1: Increased Intermediate number of positions held by special interest groups (women, Older Persons, Persons with Disabilities (PWDs), Children& Youth, Ethnic minorities) in parliament, local governments and managerial positions in the formal sector | Outcome Indicator 1: Percentage of seats/positions held by special interest groups (women, Older Persons, Persons with Disabilities (PWDs), Children& Youth, Ethnic minorities) to parliament, local governments and managerial positions in the formal sector | 40 | 45 | 50 | 55 | 60 | Electoral Commission reports |
|  | Intermediate Outcome 4.2: Improved social protection systems by sex, distinguishing children, older persons, PWDs, work injury victims, the poor and vulnerable | Outcome Indicator 1: Proportion of the population covered by social protection systems by sex, distinguishing children, youth, older persons, PWDs, work injury victims, the poor, vulnerable and refugees (%) | 15 | 20 | 25 | 30 | 35 | District Annual reports |
| Sub Programme 5: Community Sensitization and Empowerment | Intermediate Outcome 5.1: Increased participation of the population in development initiatives | Outcome Indicator 1: Percentage of households benefiting in development initiatives | 40 | 45 | 50 | 55 | 60 | Field surveys and reports |
|  |  | Outcome Indicator 2: Proportion of households informed about national initiatives (%) | 50 | 54 | 60 | 65 | 80 | Field reports |
|  |  | Outcome Indicator 3: Percentage of households participating in village saving initiatives | 40 | 45 | 50 | 55 | 60 | Field reports |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention 1.1 (d): Promote optimal Maternal, Infant, Young child, Adolescent and Elderly Nutrition Practices | Output 1.1.1: Enabling environment for scaling up nutrition at all levels strengthened | Output Indicator 1: Number of Nutrition regulations, guidelines and SOPs developed |  | 1 |  |  |  | District Council |
|  |  | Output Indicator 2: % of Health facilities designated as mother-baby friendly (HC IVs and IIIs) | 80 | 80 | 80 | 85 | 90 | District Health Team, Partners |
|  | Output 1.1.2: Prevent and control micro-nutrient deficiencies | Output Indicator 1: Vitamin A second dose coverage for U5s (%) | 74 | 75 | 76 | 77 | 80 | District Health Team, Partners |
|  |  | Output Indicator 2: % of Pregnant women receiving Iron and Folic Acid supplementation on 1st ANC visit | 75 | 75 | 75 | 75 | 75 | District Health Team, Partners |
|  |  | Output Indicator 3: Number of Health workers oriented on micronutrient supplementation for the elderly | 80 | 85 | 86 | 90 | 92 | District Health Team, Partners |
|  | Output 1.1.3: Promote Food Safety along the food systems | Output Indicator 1: % of Eating places inspected | 70 | 75 | 76 | 78 | 80 | District Health Team |
|  |  | Output Indicator 2: % of Food handlers screened for Typhoid, TB | 65 | 68 | 72 | 73 | 75 | District Health Team |
|  | Output 1.1.4: Increase access to immunization against childhood diseases | Output Indicator 1: % of under 5 children dewormed in last 6 months | 75 | 78 | 85 | 90 | 95 | District Health Team |
|  |  | Output Indicator 2: Measles-Rubella 2nd dose Coverage | 46 | 50 | 55 | 70 | 90 | District Health Team, Partners |
|  |  | Output Indicator 3: % of Children under one year fully immunized | 70 | 75 | 80 | 85 | 90 | District Health Team, Partners |
|  |  | Output Indicator 4: % of children under 24 months immunized against malaria (malaria 4th dose coverage) | 0 | 0 | 50 | 75 | 90 | District Health Team, Partners |
|  |  | Output Indicator 5: % of sub counties with at least one health facility having a functional refrigerator for Extended Programme on Immunisation | 50 | 50 | 65 | 68 | 70 | District Health Team, Partners |
|  |  | Output Indicator 6: % of static Extended Programme on Immunisation facilities conducting outreaches | 65 | 68 | 75 | 85 | 90 | District Health Team, Partners |
|  |  | Output Indicator 7: Number of health workers trained in immunization practice in Uganda | 120 | 130 | 140 | 150 | 165 | District Health Team, Partners |
|  | Output 1.1.5: Promote adolescent and youth friendly health services | Output Indicator 1: % of LGs with DICAH (%) | 80 | 80 | 85 | 85 | 90 | District Health Team |
|  |  | Output Indicator 2: % of Health facilities providing adolescent friendly services | 22 | 30 | 35 | 40 | 45 | District Health Team, Partners |
|  |  | Output Indicator 3: Number of Adolescent and youth health campaigns conducted | 4 | 4 | 4 | 4 | 4 | District Health Team, Partners |
| Intervention 1.2 (d) Increase community ownership, access and utilization of health promotion, environmental health and community health services | Output 1.2.1: Integrated community health services package rolled out in all villages | Output Indicator 1: % of Parishes with at least 2 functional Community Health Extension Workers | 52 | 55 | 60 | 60 | 65 | District Health Team |
|  |  | Output Indicator 2: % of Villages with atleast 2 VHTs offering integrated community health service package | 52 | 55 | 58 | 62 | 65 | District Health Team, Partners |
|  |  | Output Indicator 3: % of Parishes with functional Parish Social Services Committees | 45 | 50 | 55 | 60 | 65 | District Health Team |
|  | Output 1.2.2: Strengthen enforcement of health/WASH-related legislation | Output Indicator 1: Mortality rate from unsafe WASH (Diarrhea, Typhoid, Dysentery & Cholera), per 100,000 population | 5 | 4 | 3 | 3 | 2 | District Health Team, Partners |
|  |  | Output Indicator 2: % of Households using a hand washing facility with soap and water | 5 | 6 | 10 | 20 | 30 | District Health Team, Partners |
|  |  | Output Indicator 3: % of Households with access to an improved water source | 68 | 69 | 69.5 | 70 | 70 | District Health Team, Partners |
|  |  | Output Indicator 4: % Households with improved sanitation facilities | 65 | 70 | 75 | 80 | 100 | District Health Team, Partners |
|  |  | Output Indicator 5: Number of Health/WASH related By-laws passed | 5 | 5 | 5 | 5 | 5 | District Health Team, LLG Councils |
|  |  | Output Indicator 6: % of Sub counties conducting monthly community sanitation days | 35 | 39 | 44 | 49 | 50 | District Health Team |
|  |  | Output Indicator 7: % of Vermin and vector control interventions carried out in high endemic areas every quarter | 65 | 70 | 75 | 80 | 100 | District Health Team |
|  |  | Output Indicator 8: LGs oriented on the revised healthcare waste management guidelines | 5 | 6 | 10 | 13 | 14 | District Health Team |
|  | Output 1.2.3: Climate resilient health system built | Output Indicator 1: % of LGs with health staff oriented in climate adaptation and mitigation capacity (%) | 10 | 15 | 20 | 22 | 25 | District Health Team, Partners |
|  |  | Output Indicator 2: % of Health facilities with climate resilient infrastructure (Solar Energy, incinerators, WASH) | 20 | 25 | 30 | 35 | 50 | District Health Team, Partners |
|  | Output 1.2.4: Health/Nutrition promotion and education interventions scaled up | Output Indicator 1: % of Planned health/Nutrition promotion and disease prevention events held | 35 | 39 | 44 | 49 | 50 | District Health Team, Partners |
|  |  | Output Indicator 2: % of Health facilities (HC III and above) providing integrated management of acute malnutrition | 35 | 39 | 44 | 49 | 50 | District Health Team, Partners |
|  |  | Output Indicator 3: % of OPD clients who had the nutritional status assessed | 35 | 39 | 44 | 49 | 50 | District Health Team, Partners |
| Intervention 1.3 (d) Reduce the burden of communicable diseases with focus on high burden diseases (Malaria, HIV/AIDS, TB, Neglected Tropical diseases, Hepatitis), epidemic prone diseases across all age groups emphasizing Primary Health Care Approach | Output 1.3.1: Access to malaria prevention and treatment services improved | Output Indicator 1: % of sick children seen by VHT and treated within 24 hours for fever | 15 | 20 | 20 | 23 | 25 | District Health Team, Partners |
|  |  | Output Indicator 2: % of Population who slept under an Insecticide Treated Net the night before the survey | 56 | 60 | 65 | 66 | 70 | District Health Team, Partners |
|  |  | Output Indicator 3: Intermittent Presumptive Treatment for Malaria in Pregnancy 3rd dose coverage (%) | 45 | 50 | 55 | 56 | 60 | District Health Team, Partners |
|  | Output 1.3.2: Access to HIV/AIDs prevention, control and treatment services improved | Output Indicator 1: Number of HIV/AIDS Care and prevention strategies and guidelines developed (Number) | 2 | 2 | 2 | 2 | 2 | District Health Team, Partners |
|  |  | Output Indicator 2: % of Population who know 3 methods of HIV prevention | 65 | 75 | 85 | 90 | 95 | District Health Team, Partners |
|  |  | Output Indicator 3: ART Retention rate at 12 months (%) | 75 | 79 | 85 | 90 | 95 | District Health Team, Partners |
|  |  | Output Indicator 4: % of HIV positive Pregnant women initiated on ART | 85 | 90 | 94 | 94 | 95 | District Health Team, Partners |
|  |  | Output Indicator 5: % of HIV exposed infants with 2nd DNA/PCR within 9 months | 60 | 70 | 80 | 90 | 95 | District Health Team, Partners |
|  |  | Output Indicator 6: Number of Safe male circumcisions conducted | 500 | 500 | 600 | 650 | 650 | District Health Team, Partners |
|  | Output 1.3.3: Access to prevention, treatment and control of TB and leprosy services improved. | Output Indicator 1: NTB/L Prevention and Control Strategy developed and disseminated | 2 | 2 | 2 | 2 | 2 | District Health Team, Partners |
|  |  | Output Indicator 2: TB treatment coverage rate (%) | 80 | 84 | 88 | 92 | 95 | District Health Team, Partners |
|  |  | Output Indicator 3: TB treatment success rate (%) | 80 | 84 | 88 | 92 | 95 | District Health Team, Partners |
|  |  | Output Indicator 4: % of Leprosy cases with grade 2 disability | 0 | 0 | 0 | 5 | 5 | District Health Team, Partners |
|  |  | Output Indicator 5: Number of CAST+ campaigns conducted | 4 | 4 | 4 | 4 | 4 | District Health Team, Partners |
|  | Output 1.3.4: Access to NTDs Services improved | Output Indicator 1: Number of people (millions) requiring interventions against NTDs(leprosy, schistosomiasis, trachoma, sleeping sickness, Lymphatic Filariasis, soil transmitted helminths, taenia solium, onchocerciasis, Visceral Leishmaniasis, Buruli Ulcer, podoconiosis, rabies, tungaisis (jiggers), scabbies) | 2 | 2 | 2 | 2 | 2 | District Health Team, Partners |
|  |  | Output Indicator 2: % of Planned mass drug administration for NTDs conducted | 35 | 35 | 35 | 40 | 40 | District Health Team, Partners |
|  |  | Output Indicator 3: Number of Health workers oriented on NTD management | 10 | 10 | 10 | 10 | 10 | District Health Team, Partners |
|  | Output 1.3.5: Hepatitis Prevention and control strategy implemented | Output Indicator 1: Viral Hepatitis B birth dose coverage | 21 | 25 | 35 | 55 | 70 | District Health Team, Partners |
|  |  | Output Indicator 2: % of Health Facilities (HC IV and above) with diagnostics for Hepatitis | 42 | 45 | 50 | 55 | 60 | District Health Team, Partners |
|  |  | Output Indicator 3: % of Health facilities with staff trained in viral hepatitis management | 42 | 45 | 50 | 55 | 60 | District Health Team, Partners |
| Intervention 1.4 (d) Prevent and control Non-Communicable diseases with specific focus on cancer, cardiovascular, genetic, renal, endocrine, mental, trauma and malnutrition across all age groups. | Output 1.4.1: Establish Centres of excellence in provision of onchology, cardiovascular and trauma services at both National and Regional Levels and foster regional integration | Output Indicator 1: Population aged 15 - 49 years diagnosed with diabetes who are on treatment (%) | 20 | 25 | 30 | 33 | 50 | District Health Team, Partners |
|  |  | Output Indicator 2: % of Women 25 - 49 years screened for cervical cancer | 35 | 45 | 55 | 65 | 75 | District Health Team, Partners |
|  |  | Output Indicator 3: % of Men 40+ years screened for prostate cancer | 20 | 25 | 30 | 33 | 50 | District Health Team, Partners |
|  |  | Output Indicator 4: HPV 2nd dose coverage for girls at 10 years | 20 | 50 | 55 | 70 | 90 | District Health Team, Partners |
|  | Output 1.4.2: Strengthen multi-sectoral & health sector capacity in NCDs & injury prevention and control | Output Indicator 1: Alcohol Abuse Rate (%) | 30 | 20 | 15 | 9 | 5 | District Health Team, Partners |
|  |  | Output Indicator 2: Road traffic injury mortality rate (per 100,000 population) | 20 | 15 | 10 | 9 | 5 | District Health Team, Partners |
|  |  | Output Indicator 3: % of MDAs with Non communicable Disease prevention and control workplace policies | 30 | 35 | 40 | 45 | 60 | District Health Team, Partners |
|  |  | Output Indicator 4: Number of health workers trained in substance abuse management and rehabilitation | 30 | 40 | 50 | 60 | 70 | District Health Team, Partners |
|  | Output 1.4.3: Strengthen nutrition promotion and malnutrition rehabilitation services | Output Indicator 1: Prevalence of wasting among children under 5 (%) | 15 | 10 | 8 | 6 | 4 | District Health Team, Partners |
|  |  | Output Indicator 2: Prevalence of obesity among women (%) | 10 | 8 | 6 | 4 | 2 | District Health Team, Partners |
|  |  | Output Indicator 3: Prevalence of obesity among men (%) | 6 | 5 | 4 | 3 | 2 | District Health Team, Partners |
|  |  | Output Indicator 4: Prevalence of obesity among Children under 5 (%) | 5 | 4 | 3 | 2 | 1 | District Health Team, Partners |
|  |  | Output Indicator 5: % of children under 5 screened for malnutrition (under / over malnutrition) at OPD | 50 | 60 | 70 | 80 | 90 | District Health Team, Partners |
|  |  | Output Indicator 6: Number of health workers trained in malnutrition screening and IMAM | 10 | 15 | 25 | 30 | 30 | District Health Team, Partners |
|  | Output 1.4.4: Improve maternal, neonatal, child and adolescent health services at all levels of care | Output Indicator 1: % of under 5 illnessess attributed to diarrhoeal diseases | 6 | 5 | 4 | 3 | 2 | District Health Team, Partners |
|  |  | Output Indicator 2: % of deliveries in health facilities | 52 | 55 | 60 | 65 | 70 | District Health Team, Partners |
|  |  | Output Indicator 3: % of HC IVs that are fully functional (Offering blood Transfusion and Cesearian Section) | 100 | 100 | 100 | 100 | 100 | District Health Team, Partners |
|  | Output 1.4.5: Invest in appropriate neonatal careservices at all levels | Output Indicator 1: Institutional perinatal mortality rate per 1,000 births | 22 | 21 | 15 | 12 | 10 | District Health Team, Partners |
|  |  | Output Indicator 2: % of perinatal deaths reviewed | 80 | 85 | 90 | 95 | 100 | District Health Team, Partners |
|  |  | Output Indicator 3: % of HC IVs with functional Level II new born care units | 80 | 80 | 80 | 85 | 85 | District Health Team, Partners |
|  |  | Output Indicator 4: Number of health workers trained in specialized neonatal care | 5 | 5 | 6 | 6 | 10 | District Health Team, Partners |
| Intervention 1.5 (d) Access to Sexual and Reproductive Health (SRH) information and services increased | Output 1.5.1: Increased demand and uptake of reproductive health services | Output Indicator 1: Couple years of protection | 20 | 25 | 27 | 29 | 30 | District Health Team, Partners |
|  |  | Output Indicator 2: Prevalence of positive syphilis serology in pregnant women (%) | 15 | 12 | 9 | 6 | 4 | District Health Team, Partners |
|  |  | Output Indicator 3: Prevalence of anaemia in pregnancy (%) | 10 | 8 | 6 | 4 | 2 | District Health Team, Partners |
|  |  | Output Indicator 4: % of obstetric & gynaecologic admissions due to abortion | 12 | 8 | 6 | 3 | 1 | District Health Team, Partners |
|  |  | Output Indicator 5: % of pregnant women attending ANC who test HIV positive | 5 | 4 | 3 | 2 | 1 | District Health Team, Partners |
|  | Output 1.5.2: Medical Laboratory and diagnostic imaging services strengthened | Output Indicator 1: Average turnaround time for routine tests | 10 | 6 | 4 | 2 | 1 | District Health Team, Partners |
|  |  | Output Indicator 2: % of HC laboratories that have been ISO accredited | 10 | 20 | 30 | 40 | 50 | District Health Team, Partners |
|  |  | Output Indicator 3: Number of health workers at Community Hospitals/HC IVs trained in sonography | 4 | 5 | 6 | 6 | 10 | District Health Team, Partners |
|  |  | Output Indicator 4: Radiology and imaging units accredited (ISO 151892022) | 1 | 1 | 2 | 2 | 1 | District Health Team, Partners |
|  | Output 1.5.3: Improved adequacy of Human Resources for health, health infrastructure, medical equipment, vaccines, medicines, supplies and health technologies | Output Indicator 1: Health worker population ratio (Number of doctors, nurses and midwives per 10,000 population) | 1548 | 1450 | 1200 | 1100 | 965 | District Health Team, Partners |
|  |  | Output Indicator 2: Number of physicians (doctors) per 10,000 population | 47689 | 47600 | 47000 | 35000 | 25000 | District Health Team, Partners |
|  |  | Output Indicator 3: Population living within 5km of a public health facility (%) | 60 | 55 | 50 | 45 | 40 | District Health Team, Partners |
|  |  | Output Indicator 4: Constituencies with a functional HC IV / Community Hospital | 50 | 50 | 100 | 100 | 100 | District Health Team, Partners |
|  |  | Output Indicator 5: % of Subcounties/TCs with a Public HC III and above | 57 | 57 | 58 | 59 | 60 | District Health Team, Partners |
|  |  | Output Indicator 6: Basic Medical Equipment functional (%) | 60 | 65 | 69 | 70 | 70 | District Health Team, Partners |
|  |  | Output Indicator 7: Average availability of the basket of tracer commodities (50) at all reporting facilities (%) | 70 | 75 | 80 | 83 | 85 | District Health Team, Partners |
|  |  | Output Indicator 8: Service availability and readiness index (%) | f | 65 | 70 | 72 | 75 | District Health Team, Partners |
| Intervention 1.6 (d) Improve the functionality of the health system to deliver quality and affordable preventive, promotive, curative and palliative healthcare services. | Output 1.6.1: Adequate and well trained human resources for health at all levels in place | Output Indicator 1: % of approved posts filled in public health facilities | 28 | 30 | 35 | 40 | 45 | CAO, DSC |
|  |  | Output Indicator 2: Human Resource for Health Development Plan 2025/26 - 2029/30 developed | 1 |  |  |  |  | District Health Team, District Council |
|  | Output 1.6.2: Health Infrastructure improved | Output Indicator 1: Number of health facilities rehabilitated / expanded to increase scope of services | 1 | 1 | 1 | 1 | 1 | District, GOU Partners |
|  |  | Output Indicator 2: Number of staff houses constructed/rehabilitated | 1 | 1 | 1 | 1 | 1 | District Health Team, Partners |
|  |  | Output Indicator 3: Number of X-ray machines procured and installed | 1 |  |  | 1 |  | District Health Team, Partners |
|  |  | Output Indicator 4: Number of Ultrasound scans procured and installed | 1 | 1 | 1 | 1 | 1 | District Health Team, Partners |
|  |  | Output Indicator 5: % of Health facilities with adequate clean energy (solar) source | 0 | 5 | 7 | 8 | 9 | District Health Team, Partners |
|  | Output 1.6.3: Expand geographical access | Output Indicator 1: Number of HC IVs established |  | 1 |  |  |  | District, GOU Partners |
|  |  | Output Indicator 2: Number of HC IIIs established | 1 | 2 | 1 | 1 | 1 | District, GOU Partners |
|  | Output 1.6.4: Increase availability of affordable medicines and health supplies including promoting local production of medicines.(including complementary medicine) | Output Indicator 1: % of health facilities with 95% availability of the 50 basket of EMHS | 50 | 55 | 58 | 61 | 65 | District Health Team, Partners |
|  |  | Output Indicator 2: Availability of the tracer public health emergency commodities - examination gloves, coveralls, surgical masks, 70% alochol, vacutainer tubes, IV Ringer's lactate, sodium hypochlorite & aprons) (%) | 50 | 55 | 58 | 61 | 65 | District Health Team, Partners |
|  |  | Output Indicator 3: % of health facilities with a SPARS (Supervision, Performance, Assesement, Recognition, Strategy) score of 75% and above (%) | 45 | 48 | 51 | 54 | 57 | District Health Team, Partners |
|  |  | Output Indicator 4: % of health facilities ( HC IVs & IIIs) with functional Logistics Management Information System | 46 | 47 | 49 | 51 | 55 | District Health Team, Partners |
|  | Output 1.6.5: Promote digitalization of the health information system | Output Indicator 1: Health Information and Digital Health Strategy in place | 1 | 1 | 1 | 1 | 1 | District Health Team, Partners |
|  |  | Output Indicator 2: % of HC III’s and HC IVs with functional Electronic Medical Record System | 40 | 45 | 49 | 50 | 55 | District Health Team, Partners |
|  |  | Output Indicator 3: % of LGs with functional Electronic Community Health Information System | 40 | 45 | 49 | 50 | 55 | District Health Team, Partners |
|  |  | Output Indicator 4: Number of health workers trained in EMRs use | 10 | 20 | 30 | 50 | 50 | District Health Team, Partners |
|  |  | Output Indicator 5: Number of health workers trained in telemedicine application | 5 | 10 | 15 | 16 | 20 | District Health Team, Partners |
| Intervention 1.7 (d) Improve access and equity of pre-primary education | Output 1.7.1: Improved access to equitable ECCE | Output Indicator 1: Number of under resourced ECCE centers provided with textbooks and instructional materials in underserved parishes | 30 | 40 | 50 | 60 | 70 | District Education Department, GOU |
|  |  | Output Indicator 2: Number of ECCE pupils enrolled in underserved ECCE | 500 | 1000 | 1500 | 2000 | 2500 | District Education Department |
|  |  | Output Indicator 3: Number of ECCE centers established in underserved parishes | 10 | 15 | 20 | 25 | 30 | District Education Department, MoES |
| Intervention 1.8 (d): Enforce the regulatory and quality assurance system for provision of ECCE | Output 1.8.1: Improved regulatory and quality assurance system for ECCE | Output Indicator 1: Number of ECCE centers registered | 10 | 20 | 30 | 40 | 50 | District Education Department, MoES |
|  |  | Output Indicator 2: Number of ECCE centers licensed | 20 | 25 | 30 | 35 | 40 | District Education Department, MoES |
|  |  | Output Indicator 3: Number of CMCs trained | 30 | 40 | 50 | 60 | 70 | District Education Department, MoES |
|  |  | Output indicator 4: Number of ECCE centers inspected at least once per term | 90 | 90 | 90 | 150 | 150 | District Education Department, MoES |
| Intervention 1.9 (d): Equip all lagging schools to meet BRMS | Output 1.9.1: Lagging public primary schools constructed, renovated, equipped with required infrastructures and staffed | Output Indicator 1: Number of schools constructed in each gazetted parish | 1 | 1 | 1 | 1 | 1 | DEC, District Council, CAO, DEO |
|  |  | Output Indicator 2: Number of exclusive public special needs schools adequately rehabilitated, equipped, expanded and staffed | 1 | 1 | 1 | 1 | 1 | DEC, District Council, CAO, DEO |
|  |  | Output Indicator 3: Number of parishes with a public primary school | 46 | 47 | 48 | 49 | 50 | DEC, District Council, CAO, DEO |
|  |  | Output Indicator 4: Number of teachers recruited | 30 | 50 | 50 | 50 | 50 | DEC, District Council, CAO, DEO |
|  |  | Output Indicator 5: Number of permanent classrooms in public primary schools constructed or rehabilitated | 6 | 6 | 6 | 6 | 6 | DEC, District Council, CAO, DEO |
|  |  | Output Indicator 6: Number of dilapidated existing public primary schools renovated and expanded. | 1 | 1 | 1 | 1 | 1 | DEC, District Council, CAO, DEO |
|  |  | Output indicator 7: Number of classroom furniture (desks, tables, chairs) provided in primary schools | 600 | 600 | 600 | 600 | 600 | DEC, District Council, CAO, DEO |
|  |  | Output indicator 8: Number of teacher houses constructed in rural public primary schools | 1 | 1 | 1 | 1 | 1 | DEC, District Council, CAO, DEO |
| Intervention 1.10 (d): Strengthen support services (Guidance and counselling, child protection etc) to enable retention and completion at all levels. | Output 1.10.1: Schools provided with existing support services (guidance and counselling) | Output Indicator 1: Number of schools supported with these support services | 56 | 56 | 56 | 56 | 56 | DEC, District Council, CAO, DEO |
| Intervention 1.11 (d): Adopt ICT in teaching, learning and decision making through the digital agender strategy | Output 1.11.1: Increased adoption of ICT in teaching, learning and decision making through the digital agender strategy | Output indicator 1: Number of rural primary and secondary schools connected to power supply | 10 | 10 | 10 | 10 | 10 | DEC, District Council, CAO, DEO |
|  |  | Output indicator 2: EMIS statistical abstract produced | 1 | 1 | 1 | 1 | 1 | DEC, District Council, CAO, DEO |
|  |  | Output indicator 3: Number of secondary and primary schools connected to internet | 10 | 10 | 10 | 10 | 16 | DEC, District Council, CAO, DEO |
|  |  | Output indicator 4: Number of Primary and Secondary Schools that have fully operationalized TELA | 56 | 57 | 57 | 57 | 5 | DEC, District Council, CAO, DEO |
| Intervention 1.12 (d): Enforce regulatory and quality assurance system of primary and secondary schools | Output 1.12.1: Improved regulatory and quality assurance system for primary and secondary schools | Output indicator 1: Number SMCs trained in leadership and management | 51 | 51 | 51 | 51 | 51 | DEC, District Council, CAO, DEO |
|  |  | Output indicator 2: Number of trainings conducted for Heads of Institutions on developing and implementing SIPs | 1 | 1 | 1 | 1 | 1 | DEC, District Council, CAO, DEO |
|  |  | Output indicator 3: Number of inspectors of schools trained in e-inspection system twice per year | 7 | 7 | 7 | 7 | 7 | DEC, District Council, CAO, DEO |
|  |  | Output indicator 4: Number of Primary Schools with updated annual SIPs | 51 | 51 | 51 | 51 | 51 | DEC, District Council, CAO, DEO |
|  |  | Output indicator 5: Number of public primary schools inspected at least once per term | 51 | 51 | 51 | 51 | 51 | DEC, District Council, CAO, DEO |
|  |  | Output indicator 6: Number of private schools inspected at least once per term | 70 | 70 | 70 | 70 | 70 | DEC, District Council, CAO, DEO |
| Intervention 2.1 (d): Develop and implement framework for institutionalizing talent identification, development and professionalisation | Output 2.1.1: Framework for institutionalizing talent identification, development and professionalization | Output indicator 1: Number of schools with creative Arts and Physical Education (CAPE) implementation plans | 51 | 51 | 51 | 51 | 51 | Sports Officer, DEO, Head teachers |
|  |  | Output indicator 2: Number of sports officers trained to organize, manage and administer sports activities | 1 | 1 | 1 | 1 | 1 | Sports Officer |
|  |  | Output indicator 3: Number of government aided primary schools established and equipped as centers of sports excellence | 5 | 5 | 5 | 5 | 5 | Sports Officer, DEO, Head teachers |
|  |  | Output indicator 4: Number of teachers trained in talent identification | 50 | 50 | 50 | 50 | 50 | Sports officer Games teacher |
|  |  | Output indicator 5: Number of government aided Secondary schools established and equipped as centers of sports excellence | 1 | 1 | 1 | 1 | 1 | Sports Officer, DEO, Head teachers |
| Intervention 2.2 (d): Develop and implement professional sports club structures to promote formal sports participation | Output 2.2.1: Enhanced professional sports and participation | Output indicator 1: Number of sports associations registered | 2 | 2 | 2 | 2 | 2 | Sports Officer |
| Intervention 3.1: Strengthen compliance with labour standards and rights | Output 3.1.1: Compliance with labour laws, Policies ,Guidelines and standards | Output Indicator 1: Number of workers, employers, training institutions and recruitment agencies sensitized on labour Policies, laws, regulations and guidelines | 200 | 250 | 300 | 350 | 400 | Labour Officer, Gender Officer, Development Partners |
| Intervention 3.2: Develop and implement programs for job rich growth | Output 3.2.1: Safe, Orderly and Regular labour migration promoted | Output Indicator 1: Number of awareness campaigns conducted of safe labour migration to promote uptake of decent employment opportunities abroad. | 4 | 4 | 4 | 4 | 4 | DCDO |
| Intervention 4.1: Expand scope and coverage of livelihood enhancement and economic empowerment programmes for Youth, Women, Older Persons, PWDs and ethnic minorities | Output 4.1.1: Youth, Women, Older Persons, PWDs, indigenous ethnic minorities and refugees livelihood and empowerment programmes implemented | Output Indicator 1: Number of youth in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 50 | 60 | 70 | 80 | 90 | District, GOU |
|  |  | Output Indicator 2: Number of women in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 60 | 80 | 100 | 120 | 140 | District, GOU |
|  |  | Output Indicator 3: Number of Older Persons Supported in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 700 | 750 | 800 | 850 | 900 | District, GOU |
|  |  | Output Indicator 4: Number of PWDs Supported in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 50 | 60 | 70 | 80 | 90 | District, GOU |
| Intervention 4.2: Promote Women’s economic empowerment, leadership and participation in decision making through investment in entrepreneurship programmes, business centres | Output 4.2.1: Youth, Women, Older Persons, PWDs, indigenous ethnic minorities and refugee’s livelihood and empowerment programmes implemented | Output Indicator 1: Number of youths in livelihood and empowerment programs aggregated by nationality, refugee status and disability. | 50 | 60 | 70 | 80 | 90 | District, GOU |
|  |  | Output Indicator 2: Number of women in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 60 | 80 | 100 | 120 | 140 | District, GOU |
|  |  | Output Indicator 3: Number of Older Persons Supported in livelihood and empowerment programs aggregated by nationality, refugee status and disability. | 700 | 750 | 800 | 850 | 900 | District, GOU |
|  |  | Output Indicator 4: Number of PWDs Supported in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 80 | 100 | 120 | 140 | 160 | District, GOU |
| Intervention 4.3: Promote gender equality and equity responsive planning, budgeting and implementation | Output 4.3.1: Gender and equity compliance assessments conducted | Output Indicator 1: Percentage of LLGs complying with gender and equity responsive planning and budgeting. | 100 | 100 | 100 | 100 | 100 | DCDO |
|  |  | Output Indicator 2: Number of LLGs implementing gender and equity commitments | 14 | 14 | 14 | 14 | 14 | DCDO |
|  |  | Output Indicator 3: Percentage of private entities implementing gender and equity guidelines | 30 | 45 | 55 | 60 | 75 | DCDO |
|  | Output 4.3.2: Scale up Gender Based Violence and Violence against Children prevention and response interventions at all levels | 0utput indicator1.Number of GBV cases reported | 430 | 350 | 255 | 200 | 150 | DCDO, CDOs |
|  |  | 0utput indicator 2. Percentage of children aged 13-17 who experienced sexual abuse aggregated by age, type of violence, gender, nationality, refugee status and disability | 15 | 12 | 10 | 8 | 6 | DCDO, CDOs |
|  |  | 0utput indicator 3.Number of vulnerable persons including victims of Violance against Children and GBV provided with psychosocial support services (aggregated by age and sex) | 300 | 320 | 345 | 500 | 550 | DCDO, CDOs |
| Intervention 5.1: Promote community mobilization, sensitization and awareness creation for demand and uptake of development initiatives | Output 5.1.1: Increased awareness and capacity of community members to participate in and influence national development processes | Output Indicator 1: Number of community duty bearers (Civil servants, community leaders, religious leaders, parish chiefs) trained on CMMC. | 80 | 100 | 120 | 150 | 200 | DCDO, CDOs and Gender Officer |
|  |  | Output Indicator 2: Percentage of villages sensitized on the negative social and cultural practices (Teenage pregnancies, child labour, child marriage, children on the move, VAC, SGBV, etc) | 60 | 70 | 80 | 90 | 100 | Labour Officer, probation Officer and CDOs |
|  |  | Output Indicator 3: Number of youths, women, PWDs and older persons sensitized on business formalization | 300 | 450 | 500 | 600 | 750 | CDOs and programme Focal Persons |
| Intervention 5.2: Build capacities and equip community institutions at local government and non-state actors | Output 5.2.1: Institutional capacity for local government, political leaders and non-state actors in the implementation of CMMC strengthened | Output indicator 1: Number of stakeholders at local government level capacity developed | 80 | 110 | 145 | 170 | 200 | CDOs |
|  |  | Output Indicator 2: Number of committee/ council meetings for special interest groups (PWD, Elderly, Women, Youth, Children ) conducted | 20 | 20 | 20 | 20 | 20 | DCDO and Focal Persons for special interest groups |
|  |  | Output Indicator 3: Number of monitoring visits and support supervision conducted | 4 | 4 | 4 | 4 | 4 | DEC, DTPC |
| Project 1: Health Improvement Project | Project Output 1: HC IIIs constructed | Output Indicator 1: Number of HCIIIs constructed | 2 | 1 | 1 | 1 | 1 | District, GOU Partners |
|  | Project Output 2: Health facilities rehabilitated | Output Indicator 1: Number of Health facilities rehabilitated | 1 | 1 | 1 | 1 | 1 | District, GOU Partners |
| Project 2: School Infrastructure development for improved access and quality of basic education | Project Output 1: Classrooms constructed | Output Indicator 1: Number of classrooms constructed | 6 | 6 | 6 | 6 | 6 | DEC, District Council, CAO, DEO |
|  | Project Output 2: Latrines constructed | Output Indicator 2: Number of latrine stances constructed | 20 | 20 | 20 | 20 | 20 | DEC, District Council, CAO, DEO |
|  | Project Output 3: Classroom desks procured for needy schools | Output Indicator 3: Number of classroom desks procured | 700 | 700 | 700 | 700 | 700 | DEC, District Council, CAO, DEO |

Strategic Objective 3: Support the private sector to drive growth and create jobs

Programme: Private Sector Development

Development Issue: Weak and uncompetitive private Sector

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective (1): Strengthen the organizational and institutional capacity of the private sector to drive growth | Outcome 1.1: Conducive environment for private sector investment is created, firms are competitive and meet District, national, regional and international standards | Outcome Indicator 1: Growth in Private sector credit (%) | 20 | 40 | 60 | 80 | 100 | Credit Disbursments from PDM, Emyooga |
|  |  | Outcome Indicator 2: Competitiveness index (%) | 100 | 100 | 100 | 100 | 100 | District Investment Profile |
|  |  | Outcome Indicator 3: Percentage of the informal sector | 70 | 50 | 30 | 20 | 10 | Kibaale District Statistical Abstract |
|  |  | Outcome Indicator 4: Savings as a percentage of the District Gross Domestic Product (%) | 20 | 40 | 60 | 80 | 100 | District Investment Profile, Credit Disbursments from PDM, Emyooga |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme: (1): Strengthening Private Sector Institutional and Organizational Capacity | Intermediate Outcome 1.1: Access to affordable finance | Outcome Indicator 1: Growth in private sector credit (%) | 20 | 40 | 60 | 80 | 100 | Credit Disbursments from PDM, Emyooga |
|  | Intermediate Outcome 1.2: Increasing long time financing for key growth Sectors in the District | Outcome Indicator 1: Percentage point change in lending rate | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | Commercial Banks; SACCOs |
|  |  | Outcome Indicator 2: Insurance Penetration (%) | 10 | 15 | 20 | 30 | 40 | Kibaale District Statistical Abstract |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention 1.1 (d): Support MSMEs to attain certification, testing and calibration of services | Output 1.1.1: MSMEs clustered, Profiled and supported | Output Indicator 1: Number of MSMEs in priority value chains profiled, clustered and supported | 200 | 200 | 200 | 200 | 200 | UIA District |
|  | Output 1.1.2: Industrial Business Parks Greened in line with ESG guidelines | Output Indicator 1 Percentage of Industrial Business Parks Greened in line with ESG guideline | 10 | 20 | 50 | 80 | 100 | UIA District |
| Intervention 1.2 (d): Increase access to short term finance | Output 1.2.1: Emyooga SACCOs and other client institutions offered credit and grant financing | Output Indicator 1: Value of financing (credit and grant) to women, youth and PWDs (million Uganda shilling) | 500 | 600 | 700 | 800 | 900 | 1,000 |
|  |  | Output Indicator 2: Number of Emyooga SACCOs offered grant financing | 200 | 200 | 200 | 200 | 200 | Micro Finance Support Centre; District |
|  | Output 1.2.2: Increased public awareness and understanding of capital markets, Insurance and other financial services | Output Indicator 1: Growth in insurance subscriptions disaggregated by Village (%) | 10 | 20 | 50 | 80 | 100 | District Commercial Department |
|  |  | Output Indicator 2: Percentage of financially included adults (=16 years and above) | 20 | 40 | 60 | 80 | 100 | District Commercial Department |
| Project 1: Not applicable | Project Output: Not applicable | Output Indicator 1: Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable |

Strategic Objective 4: Build and maintain strategic sustainable infrastructure in transport, housing, energy water, industry and ICT.

Programme: Integrated Transport Infrastructure and Services

Development Issue: Poorly maintained road network

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective (1): To reduce the cost of transport infrastructure development and maintenance | Outcome 1.1: Reduced cost of transport infrastructure development and maintenance | Outcome Indicator 1: Average Unit cost of rehabilitation/ maintenance of unpaved district roads | 7,000,000 | 7,500,000 | 8,000,000 | 8,50,000 | 9,000,000 | Reports from District Engineering Department |
|  |  | Outcome Indicator 2: Average Unit cost of maintenance of unpaved urban roads | 6,500,000 | 7,000,000 | 7,500,000 | 8,500,000 | 9,000,000 | Reports from District Engineering Department |
|  |  | Outcome Indicator 3: Average Unit cost of rehabilitation/ maintenance of unpaved Community access roads | 7,500,000 | 7,850,000 | 7,875,000 | 8,200,000 | 9,000,000 | Reports from District Engineering Department |
|  |  | Outcome Indicator 5: Average Unit cost of construction of transport infrastructure Ugx Million/Km (Unpaved urban roads) | 14,000,000 | 14,500,000 | 15,000,000 | 15,500,000 | 16,000,000 | Reports from District Engineering Department |
|  |  | Outcome Indicator 4: Average Unit cost of construction of transport infrastructure Ugx Million/Km (Unpaved community access roads) | 14,000,000 | 14,500,000 | 15,000,000 | 15,500,000 | 16,000,000 | Reports from District Engineering Department |
| Programme Objective (2): To develop an inter-modal and seamless transport infrastructure and services. | Outcome 1.1 Increased access to services | Outcome Indicator 1: Rural accessibility index. | 60 | 62 | 64 | 70 | 80 | Reports from District Engineering Department |
| Programme Objective (3): To strengthen transport asset management | Outcome 3.1: Longer service life of transport infrastructure | Outcome Indicator 1: Average Service life of transport infrastructure (first class marrum roads yrs) | 1 | 1 | 1 | 1 | 1 | Reports from District Engineering Department |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme: (1): Transport Infrastructure and Services Development | Intermediate Outcome 1.1: Reduced Cost variations in projects | Outcome Indicator 1: Average Percentage cost variation | 12 | 13 | 13 | 10 | 12 | Reports from District Engineering Department |
|  |  | Outcome Indicator 2: Average time spent between designs and contract awards (in months) | 2 | 2 | 3 | 3 | 2 | Reports from District Engineering Department |
|  | Intermediate Outcome 2.1: Reduced travel time | Outcome Indicator 1: Average Travel time min/km (District Roads) | 4 | 4 | 3.8 | 3.8 | 3.8 | Reports from District Engineering Department |
|  |  | Outcome Indicator 2: Average Travel time min/km (Urban Roads) | 4 | 4 | 3.8 | 3.8 | 3.8 | Reports from District Engineering Department |
|  | Intermediate Outcome 3.1: Improved condition of transport infrastructure | Outcome Indicator 1: % of DUCAR in fair to good condition | 60 | 65 | 70 | 75 | 80 | Reports from District Engineering Department |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention 1.1 (d): Construct and upgrade strategic transport infrastructure; | Output 1.1.1: Implement cost-efficient technologies for provision of transport infrastructure and services | Output Indicator 1: Number of km of medium volume roads sealed. | 0 | 0 | 0.5 | 0.5 | 0.7 | CAO; District Engineer |
|  |  | Output Indicator 2: Number of km of low volume roads sealed. | 0 | 0 | 0.5 | 0.5 | 1 | CAO; District Engineer |
|  | Output 1.1.2: Capacity of local construction industry strengthened | Output Indicator 1: Percentage of construction works carried out by local contractors | 80 | 75 | 70 | 80 | 75 | CAO; District Engineer, District PDU |
|  |  | Output Indicator 2: Number of local contractors trained | 12 | 15 | 17 | 20 | 23 | CAO; District Engineer, District PDU |
|  | Output 1.1.3: Roads Cost Estimation and Monitoring System (CEMS) established. | Output Indicator 1: Number of agencies using Cost Estimation and Monitoring System | 1 | 1 | 1 | 1 | 1 | CAO; District Engineer |
|  | Output 2.1.1: Strategic road transport infrastructure constructed and upgraded | Output Indicator 1: Number of km of roads upgraded | 0 | 0 | 24.5 | 26 | 28 | MoWT; CAO; District Engineer |
|  |  | Output Indicator 2: Number of Concrete Bridges constructed on the DUCAR network Bridges on DUCAR network | 0 | 1 | 1 | 2 | 1 | MoWT; CAO; District Engineer |
|  |  | Output Indicator 3: Km of swamp crossings constructed on the DUCAR network | 2 | 3 | 3 | 4 | 4 | CAO; District Engineer |
| Intervention 2.1 (d): To strengthen transport system resilience to climate change and natural disasters with compliance to environmental and social safeguards. | Output 2.2.1: Resilience and climate change adaptation and mitigation strengthened | Output Indicator 1: Number trees planted along roads per km | 14 | 16 | 18 | 20 | 24 | District Engineer; District ENR Department |
|  | Output 2.2.2: Strategic Social safeguards mainstreamed and Monitored | Output Indicator 1: Number of sensitization meetings held | 0 | 1 | 1 | 1 | 1 | District Engineer; District ENR Department |
|  |  | Output Indicator 2: Number of boxes of condoms distributed | 2 | 4 | 5 | 5 | 6 | District Engineer; DHO, DCDO |
| Intervention 3.1 (d): Rehabilitate and maintain transport infrastructure | Road Transport infrastructure Maintained | Output Indicator 1: Km of district roads Maintained routine manual unpaved | 181 | 181 | 181 | 181 | 181 | CAO; District Engineer |
|  |  | Output Indicator 2: Km of district roads Maintained routine mechanised unpaved | 150 | 155 | 160 | 170 | 180 | CAO; District Engineer |
|  |  | Output Indicator 3: Km of CARs maintained Routine Manual (Bulungi Bwansi) | 300 | 350 | 400 | 500 | 500 | CAO; District Engineer |
|  |  | Output Indicator 4: Km of Urban roads sealed | 0 | 0 | 0.3 | 0.4 | 0.5 | CAO; District Engineer |
|  |  | Output Indicator 5: km of Community Access Roads Rehabilitated | 30 | 35 | 40 | 45 | 50 | CAO; District Engineer |
| Intervention 3.2 (d): Strengthen mechanical engineering services | Output 3.2.1 Mechanical engineering services strengthened | Output Indicator 1: Number of salvageable tools, machines and equipment repaired and/or upgraded | 24 | 26 | 30 | 34 | 40 | CAO; District Engineer |
|  |  | Output Indicator 2: Number of field supervision and monitoring vehicles purchased | 0 | 0 | 1 | 0 | 0 | CAO; District Engineer |
|  |  | Output Indicator 3: percentage of road construction equipment rehabilitated | 70 | 75 | 75 | 80 | 85 | CAO; District Engineer |
| Project 1: Road rehabilitation and maintenance | Project Output 1: Routine manual maintenance of feeder roads carried out | Output Indicator 1: Number of kms maintained | 191.3 | 191.3 | 191.3 | 191.3 | 191.3 | Roads and Engineering Department |
|  | Project Output 1: Routine mechanised maintenance of feeder roads carried out | Output Indicator 1: Number of kms maintained | 205.7 | 205.7 | 205.7 | 205.7 | 205.7 | Roads and Engineering Department |

Strategic Objective 4: Build and maintain strategic sustainable infrastructure in transport, housing, energy water, industry and ICT.

Programme 2: Sustainable Urban and Housing Development

Development Issue: Unplanned Rural Growth centres

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective (1): Develop and maintain urban infrastructure in line with physical development plans | Outcome 1.1: Improved mobility and accessibility in Urban areas | Outcome Indicator 1: Number of Urban centres with Detailed Physical Development Plans | 1 | 1 | 1 | 1 | 1 | Reports from ENR Department |
| Programme Objective (2): Strengthen land use management | Outcome 2.1: Iimproved land tenure security | Outcome Indicator 1: Proportion of total adult population with secure tenure rights to land, with legally recognized documentation | 30 | 35 | 40 | 45 | 50 | District Land Board records |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme: (1) Physical Planning and Urbanization | Intermediate Outcome 1.1: Improved urban Infrastructure | Outcome Indicator 1: Percentage of permanent buildings with approved plans | 75 | 76 | 77 | 78 | 79 | Reports from ENR Department |
|  | Intermediate Outcome 2.1: Increased registration of land | Outcome Indicator 1: Land Surveyed (%) | 30 | 35 | 40 | 45 | 50 | District Land Board records |
|  |  | Outcome Indicator 2: Land Registered (%) | 30 | 35 | 40 | 45 | 50 | District Land Board records |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention 1.1 (d): Develop lower level Physical Development Plans to operationalise the National Physical Development Plan | Output 1.1.1: Lower level Physical and detailed plans developed and implemented | Output Indicator 1: Number of urban roads named | 5 | 5 | 5 | 5 | 5 | Reports from ENR Department |
|  |  | Output Indicator 2: Number of Detailed Physical Development Plans developed | 1 | 1 | 1 | 1 | 1 | Reports from ENR Department |
|  |  | Output Indicator 3: % permanent buildings with approved plans | 75 | 76 | 77 | 78 | 79 | Reports from ENR Department |
| Intervention 2.1 (d): Undertake Land Tenure Security Enhancement Programmes | Output 2.1.1: 200 beneficiaries allocated public land | Output Indicator 1: Number of beneficiaries allocated land | 50 | 50 | 50 | 50 | 50 | DLB; Surveyors; Secretary DLB |
|  | Output 2.1.2: District Land Board meetings held | Output Indicator 2: Number of meeting held | 04 | 04 | 04 | 04 | 04 | DLB; Secretary DLB |
|  | Output 2.1.3: Reports submitted to Council and line Ministries | Output Indicator 3: Number of reports submitted | 04 | 04 | 04 | 04 | 04 | Secretary DLB; Speaker; Clerk to Council |
|  | Output 2.1.4: Sensitization meetings conducted | Output Indicator 4: Number of meetings conducted | 04 | 04 | 04 | 04 | 04 | DLB; Secretary DLB |
|  | Output 2.1.5: Land disputes settled | Output Indicator 5: Number of disputes settled | 80 | 80 | 80 | 80 | 80 | DLB; Secretary DLB |
| Project 1: Not applicable | Project Output: Not applicable | Output Indicator 1: Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable |

Strategic Objective 4: Build and maintain strategic sustainable infrastructure in transport, housing, energy water, industry and ICT.

## Programme: Sustainable Energy Development

Development Issue: Poor use of renewable energy

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective (1): Promote utilization of energy efficient practices and technologies | Outcome 1.1: Reduction of annual biomass demand | Outcome Indicator 1: Percentage reduction of annual biomass demand | 3 | 5 | 7 | 10 | 12 | Reports from the District ENR Department |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme: (1) Energy Efficiency | Intermediate Outcome 1.1: Adoption of clean energy technologies | Outcome Indicator 1: Percentage of population using clean energy technologies | 13 | 15 | 17 | 18 | 20 | Reports from the District ENR Department |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention 1.1 (d): Promote use of new renewable energy solutions (solar water heating, solar drying, solar cookers, wind water pumping solutions, solar water pumping solutions) | Output 1.1.1: Renewable energy technologies community sensitization/training meetings held in 11 LLGs | Output Indicator 1: Number of training reports | 14 | 14 | 14 | 14 | 14 | District ENR Department; Development Partners |
|  | Output 1.1.2: households supported to acquire alternative clean energy options for cooking and lighting | Output Indicator 1: Number of households supported | 200 | 200 | 200 | 200 | 200 | District ENR Department; Development Partners |
| Project 1: Not applicable | Project Output: Not applicable | Output Indicator 1: Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable |

Strategic Objective 4: Build and maintain strategic sustainable infrastructure in transport, housing, energy water, industry and ICT.

## Programme: Digital Transformation

Development Issue: Limited use of Information Communication Technology

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Increase ICT connectivity across the district | Outcome 1.1: Increased citizen participation in the digital governance and economy | Outcome Indicator 1: Proportion of ICT related jobs created (%) | 0 | 10 | 20 | 35 | 40 | UBOS, UCC, NITA – U, MoICT, MoH |
|  |  | Outcome Indicator 2: Proportion of population using e- government services (%) | 15 | 25 | 33 | 38 | 47 | UBOS, UCC, NITA – U, MoICT |
|  |  | Proportion of ICT related enterprises/businesses as a percentage of the total enterprises (URSB)- (%) | 05 | 08 | 10 | 15 | 25 | URSB |
|  |  | District broadband coverage with minimum speed of 8 Mbps, (%) | 0 | 25 | 30 | 33 | 42 | UCC, NITA – U, MoICT |
|  | Outcome 1.2: digitalization of records. | Outcome Indicator 1: Digital data repository (%) | 20 | 30 | 40 | 50 | 60 | IT office, Human Resource office, Records office and website |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme: (1) ICT support services | Citizen and staff advisory and capacity built | Proportion of population trained (%) | 15 | 27 | 37 | 43 | 50 | Education department, trade and commerce, IT section, administration department |
|  |  | Frequency of support sessions and outreaches | 10 | 20 | 30 | 45 | 60 | IT section |
| Establish a robust IMS | Maintenance | Proportion of ICTs well maintained (%) | 30 | 40 | 50 | 65 | 70 | Admin department planning unit, and respective cost centers |
|  | Securing systems | Proportion of ICTs secured (%) | 40 | 55 | 67 | 77 | 85 | Admin department planning unit, and respective cost centers |
| Increasing ICT enabled and skilled human resource | Trainings | Percentage of population accessing capacity training in modern IT technologies | 15 | 25 | 37 | 45 | 55 | Administration department, Planning Department, and respective cost centers |
| Expansion of network connectivity | LAN | Percentage of offices in LLGs connected, schools and health Units with networks established | 10 | 27 | 39 | 50 | 64 | Administration department, Planning Department, and respective cost centers |
| Automating Processes | Designing, Developing , deploying and enhancing enabling applications | Proportion of government based services in the district automated or digitized (%) | 15 | 28 | 37 | 46 | 58 | Administration department, Planning Department, and respective cost centers |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention: 1.1 Extend broadband ICT infrastructure coverage district wide | Output 1.1.1: District service delivery units connected to the Broadband infrastructure | Output Indicator 1: Number of Kilometres of Optic Fibre Cable layed | 1/2 | 1 | 3 | 4 | 6 | NITA – U, IT Section , Administration Department |
|  |  | Output Indicator 2: Number of wireless hotspots in parishes and Tourism sites established | 3 | 4 | 5 | 6 | 8 | NITA – U, IT Section |
| Intervention 1.2 Digitalize district services | Output 1.2.1: district services automated, integrated and rolled out | Output Indicator 1: Proportion of district services automated and rolled out (%) | 20 | 30 | 40 | 50 | 70 | Administration , IT Sector |
|  |  | Output Indicator 2: Number of district aided and private institutions utilising the district Data Sharing and Integration Platform | 1 | 3 | 10 | 20 | 30 | IT Sector, Education department |
|  | Output 1.2.2: Digital shared services deployed across Kibaale LG | Output Indicator 1: Number of sub counties utilising digital shared services | 0 | 2 | 6 | 10 | 14 | IT Sector, Administration Department, Cost centres |
| 1.3 Support local innovation and commercialization of homegrown products | Output 1.3.1 Support development and marketing of local innovations | Number of local products developed | 0 | 10 | 25 | 35 | 40 | Administration Department, IT Sector, Moict |
|  | Output 1.3.2 Conduct assessment on ICT innovations | Percentage of local products commercialized (%) | 0 | 20 | 30 | 40 | 50 | Administration Department, MoICT, IT Sector |
|  | Output 1.3.3 Support Development and commercialisation of local Audio-visual products | Percentage of Audio Visual Productions developed and commercialized | 0 | 20 | 25 | 35 | 45 | ICT Sector, Administration Department |
| Project 1: Not applicable | Project Output: Not applicable | Output Indicator 1: Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable |

Strategic Objective 4: Strengthen good governance, security, and the role of the state in development

## Programme: Governance and Security

Development Issue: Inadequacies in the Governance and oversight function

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective (1): To increase effectiveness and efficiency in legislative process | Outcome 1.1: Improved legal frame work for national development | Outcome Indicator 1: Percentage of bills/motions passed against those presented | 83 | 83 | 83 | 83 | 83 | District Council records |
| Programme Objective (2): Strengthen Accountability, Transparency for Effective Governance | Outcome 2.1: Improved transparency, accountability and public trust.in service delivery | Outcome Indicator 1: Improved service delivery | 75 | 80 | 80 | 80 | 85 | Assessment reports |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme: (1): Legislature and over Sight | Intermediate Outcome 1.1: Enhanced scrutiny and quality of legislation | Outcome Indicator 1: Percentage of Bills withdrawn against Bills presented | 4 | 0 | 4 | 4 | 4 | District Council records |
|  |  | Outcome Indicator 2: Percentage of legislation challenged in court within six months | 0 | 0 | 0 | 0 | 0 | District Council records |
| Sub Programme: (2): Anti-Corruption and Accountability | Intermediate Outcome 2.1: Improved compliance to accountability laws and regulations. | Outcome Indicator 1: Reduced number of internal audit queries | 40 | 30 | 30 | 30 | 30 | Audit records |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention 1.1 (d): Fast track legislative business at plenary and Committee level | Output 1.1.1: Council meetings conducted | Output Indicator 1: Number of meetings held and sets of minutes in place | 6 | 6 | 6 | 6 | 6 | District Council records |
|  | Output 1.1.2: Standing committee sittings held | Output Indicator 1: Number of meetings held and sets of minutes in place | 30 | 30 | 30 | 30 | 30 | District Council records |
|  | Output 1.1.3: Business committee sittings held | Output Indicator 1: Number meetings held and set of minutes in place. | 06 | 06 | 06 | 06 | 06 | District Council records |
|  | Output 1.1.4: Staff and full time Political Leaders salaries paid | Output Indicator 1: Number of months paid | 12 | 12 | 12 | 12 | 12 | District Council records |
|  | Output 1.1.5: Emoluments of political leaders paid | Output Indicator 1: Number of leaders paid | 654 | 654 | 660 | 660 | 660 | District Council records |
|  | Output 1.1.6: Government programmes monitored | Output Indicator 1: Reports | 4 | 4 | 4 | 4 | 4 | District Council records |
|  | Output 1.1.7: Study tours conducted | Output Indicator 1: Number of tours conducted | 1 | 1 | 1 | 1 | 1 | District Council records |
| Intervention 2.1 (d): Strengthening audit function and internal controls | Output 2.1.1: Internal Audit reports prepared | Output Indicator 1: Number of Internal Audit reports prepared and submitted | 4 | 4 | 4 | 4 | 4 | Internal Audit reports |
|  | Output 2.1.2: Financial reports prepared | Output Indicator 1: Number of financial reports prepared and submitted to relevant authorities | 4 | 4 | 4 | 4 | 4 | Audit department |
|  | Output 2.1.3: Staff salaries paid | Output Indicator 1: Number of Monthly staff salaries paid | 12 | 12 | 12 | 12 | 12 | Human resource reports |
|  | Output 2.1.4: Human resource audit | Output Indicator 1: Number of human resource reports prepared and submitted | 4 | 4 | 4 | 4 | 4 | Internal Audit reports |
|  | Output 2.1.5: Motor vehicle procured | Output Indicator 1: Number of Transport means procured and maintained | 1 | 1 | 1 | 1 | 2 | Internal Audit Department |
|  | Output 2.1.6: Desktop computer procured | Output Indicator 1: Number of Desk tops procured and maintained | 1 | 1 | 2 | 1 | 1 | Internal Audit Department |
|  | Output 2.1.7: Monitoring of government programs and projects | Output Indicator 1: Number of Government programs and projects such as YLP, UWEP, UPE, PDM, Emyooga and USE monitored | 4 | 4 | 4 | 4 | 4 | Internal Audit reports |
| Project 1: Not applicable | Project Output: Not applicable | Output Indicator 1: Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable |

Strategic Objective 4: Strengthen good governance, security, and the role of the state in development

## Programme: Public Sector Transformation

Development Issue: Inadequacies in Public Sector Management

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective (1): Strengthen human resource management for improved service delivery | Outcome 1.1: Improved quality of Public Service | Outcome Indicator 1: Level of Citizen satisfaction with service delivery (%) | 50 | 55 | 65 | 70 | 75 | Survey Reports |
| Programme Objective (2): Strengthen accountability for results | Outcome 2.1: Increased transparency and accountability in provision of public services | Outcome Indicator 1: Pecentage of the population satisfied with their last experience of public services | 50 | 55 | 65 | 70 | 75 | Survey Reports |
|  |  | Outcome Indicator 2: Percentage of population knowledgeable about public services | 60 | 70 | 80 | 90 | 100 | Survey Reports |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme: (1): Human Resource Management | Intermediate Outcome 1.1: Improved staffing in the District | Outcome Indicator 1: Staffing levels in the District | 80 | 85 | 85 | 90 | 100 | Reports from Human Resource Management Unit |
| Sub Programme: (2): Strengthening Accountability | Intermediate Outcome 2.1: Increased trust and uptake of public services | Outcome Indicator 1: Percentage of the population accessing public services by sector (education, water, roads, extension services. | 50 | 60 | 70 | 80 | 90 | Survey Reports |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention 1.1 (d): Strengthen recruitment and management of human resource | Output 1.1.1: Staff appointed | Output Indicator 1: Number of Staff appointed | 40 | 40 | 40 | 40 | 40 | CAO; PHRO; DSC |
|  | Output 1.1.2: Staff promoted | Output Indicator 1: Number of Staff promoted | 10 | 10 | 10 | 10 | 10 | CAO; PHRO; DSC |
|  | Output 1.1.3: Staff confirmed in service | Output Indicator 1: Number of Staff confirmed in service | 40 | 40 | 40 | 40 | 40 | CAO; PHRO; DSC |
|  | Output 1.1.4: Staff granted study leave | Output Indicator 1: Number of Staff granted study leave | 05 | 05 | 05 | 05 | 05 | CAO; PHRO; DSC |
|  | Output 1.1.5: Disciplinary cases handled and concluded | Output Indicator 1: Number of Disciplinary cases handled and concluded | 02 | 02 | 02 | 02 | 02 | PHRO, DSC |
|  | Output 1.1.6: DSC reports prepared and submitted to council and line ministries | Output Indicator 1: Number of DSC reports prepared and submitted to council and line ministries | 04 | 04 | 04 | 04 | 04 | Secretary DSC |
|  | Output 1.1.7: Newly appointed members of the commission inducted | Output Indicator 1: Reports on induction |  | 01 |  | 01 |  | Ministry of Public Service |
|  | Output 1.1.8: Job adverts placed | Output Indicator 1: Number of Job adverts placed | 02 | 02 | 02 | 02 | 02 | DSC, CAO |
| Intervention 2.1 (d): Enforce compliance to Laws, regulations, guidelines and processes | Output 2.1.1: Audit reports reviewed | Number of reports reviewed | 04 | 04 | 04 | 04 | 04 | LGPAC ; Principal Internal Auditor; Clerk to Council |
|  | Output 2.1.2: LGPAC reports submitted to District Chairperson and CAO Ministry of Local Government for action. | Number of reports submitted | 04 | 04 | 04 | 04 | 04 | Clerk to Council; CAO |
|  | Output 2.1.3: Number of field verification visits carried out | Number of field visits carried out | 04 | 04 | 04 | 04 | 04 | LGPAC ; CAO; Clerk to Council |
| Project 1: Not applicable | Project Output: Not applicable | Output Indicator 1: Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable |

Strategic Objective 4: Strengthen good governance, security, and the role of the state in development

## Programme: Development Plan Implementation

Development Issue: Slow implementation of the Development Plan

| Programme: (a) | Outcome (a) | Indicator | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective (1): Strengthen Capacity for Evidence Based Development Planning across Government | Outcome 1.1: Enhanced Capacity for evidence based planning | Outcome Indicator 1: District Annual Performance Assessment score (%) | 75 | 77 | 80 | 83 | 85 | Annual Local Government Performnace Assessment Report |
|  |  | Outcome Indicator 2: LLG average Annual Performance Assessment score (%) | 87 | 88 | 89 | 90 | 91 | Annual Local Government Performnace Assessment Report |
|  |  | Outcome Indicator 3: Annual NDP Compliance Assessment score (%) | 67 | 70 | 72 | 75 | 78 | Annual Compliance Assessment |
| Programme Objective (2): Strengthen Oversight, Coordination and M&E across Government | Outcome 1.1: Improved delivery of the Plan | Outcome Indicator 1: Percentage of DDP IV results on target | 70 | 72 | 75 | 78 | 80 | Annual Reports |
| Programme Objective (3): Enhance domestic revenue mobilization through sustainable tax revenue policy and administration | Increased domestic revenue | Increased domestic revenue (millions Uganda Shillings) | 660 | 666 | 732 | 785 | 885 | Annual Financial statements, Assessment tools/guidelines |
| Sub Programme: (a) | Intermediate Outcome (b) | Indicator (c) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | Data Source |
| Sub Programme: (1) Development Planning, Research, Evaluation and Statistics | Intermediate Outcome 1.1: Improved alignment of Plans to NDP | Outcome Indicator 1: % alignment score of the annual work plan to NDP | 65 | 67 | 70 | 72 | 75 | Annual Compliance Assessment |
|  | Intermediate Outcome 1.2: Increased use of research and statistics for development policy and planning across government and key private sector players | Outcome Indicator 2: Percentage of DDP IV results informed by official statistics at goal and objective level | 70 | 75 | 78 | 82 | 85 | DDP annual, Mid- term and final reviews |
|  |  | Outcome Indicator 3: Proportion of National Standard indicators (NSI) with up-to-date data | 70 | 75 | 78 | 82 | 85 | NSI Annual Reports |
|  | Intermediate Outcome 2.1: Enhanced coordination for the implementation of DDP IV | Outcome Indicator 1: Functionality of the DDP IV coordination architecture | 70 | 80 | 90 | 100 | 100 | Annual Reports |
| Sub Programme: (2) Resource Mobilization and Budgeting | Outcome 3.1: Government own source revenue growth | Percentage increase in own source revenue | 10 | 10 | 10 | 10 | 10 | Financial statements |
|  |  | Share of Non tax revenue to total revenue (%) | 2.5 | 2.8 | 3.0 | 3.1 | 3.4 | Financial statements |
|  |  |  | Time frame and output target |  |  |  |  | Actors |
| Intervention | Key Output | Indicator (f) | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |
| Intervention 1.1 (d): Focus economic policy towards growth and employment creation | Output 1.1.1: Evidence based research for economic policy formulation | Output Indicator 1: Number of studies/surveys conducted | 1 | 1 | 1 |  |  | Planning Department |
|  |  | Output Indicator 2: Number of Annual Statistical Abstracts | 1 | 1 | 1 | 1 | 1 | District Statistics Committee |
|  |  | Output Indicator 3: Number of Plans for Statistical Development prepared | 1 |  |  |  |  | District Statistics Committee |
|  | Output 1.1.2: Updated National Standard Indicator (NSI) Framework | Output Indicator 1: Proportion of National Standard Indicators with updated data | 70 | 75 | 78 | 82 | 85 | District Statistics Committee |
| Intervention 1.2 Build capacity in development planning and project formulation at all levels of government | Output 1.2.1: Gender and equity responsive plans | Output Indicator 1: Proportion of LLGs with Gender and Equity responsive plans | 100 | 100 | 100 | 100 | 100 | Planning and Community Departments |
|  | Output 1.2.2: DDP V formulated | Output Indicator 1: Proportion of LLGs with the 5th LG Development Plans formulated |  |  |  |  | 100 | Planning Department |
|  |  | Output Indicator 2: The 5th District Development Plan formulated |  |  |  |  | 1 | Planning Department |
| Intervention 2.1 : Strengthen Intra and Inter-Programme coordination. | Output 2.1.1: Functional DDP coordination architecture | Output Indicator 1: Proportion of DDP PWGs (%) that are fully functional | 70 | 80 | 90 | 100 | 100 | PWG members |
|  |  | Output Indicator 2: % of departmental staff salaries paid | 100 | 100 | 100 | 100 | 100 | HRM, Planning and Finance Departments |
|  |  | Output Indicator 3: % of monthly DTPC meetings held | 100 | 100 | 100 | 100 | 100 | DTPC members |
|  |  | Output Indicator 4: Number of Planning/Budget Conferences held | 1 | 1 | 1 | 1 | 1 | District Chairperson, CAO and Planning Department |
| Intervention 2.2 Improved M&E Performance across government | Output 2.2.1: Mid Term Review of DDP IV and End term evaluation conducted | Output Indicator 1: No. Mid Term Review reports of DDP IV in Place |  |  | 1 |  |  | Planning Department |
|  |  | Output Indicator 2: No. End Term Review reports of DDPIII in Place | 1 |  |  |  |  | Planning Department |
|  | Output 2.2.2: Quarterly Monitoring and evaluation conducted | Output Indicator 1: Number of Quarterly Joint monitoring Reports prepared | 4 | 4 | 4 | 4 | 4 | Planning Department |
|  |  | Output Indicator 2: Number of Quarterly Physical and financial Progress Reports prepared | 4 | 4 | 4 | 4 | 4 | Planning and Finance Departments |
|  | Output 2.2.3: Internal Assessment conducted | Output Indicator 1: LLG Internal Assessment Report prepared | 1 | 1 | 1 | 1 | 1 | Internal Assessment Team |
|  |  | Output Indicator 2: HLG Mock Assessment Report prepared | 1 | 1 | 1 | 1 | 1 | Internal Assessment Team |
| Intervention 3.1 Develop LG revenue enhancement plans | Output 3.1.1: LG enhancement plan formulated | Output Indicator 1: Number of LG enhancement plans | 1 | 1 | 1 | 1 | 1 | District; LLGs |
| Intervention 3.2: Strengthen the capacity of public institutions to collect Non-Tax Revenue | Output 3.1.2: Non-Tax Revenue contribution to total revenue increased | Output Indicator 1: Percentage contribution of Non-Tax Revenue to total revenue | 10 | 10 | 10 | 10 | 10 | District; LLGs |
| Intervention 3.3: Local revenue allocated to community development Community | Output 3.3.1: Strengthen Local Revenue Collection System. | Output Indicator 1: Percentage of Local revenue invested in community Services | 2 | 2.5 | 3 | 3 | 3.5 | District; LLGs |
|  | Output 3.3.2: Monitor and Output 3.3.3: Evaluate LR enhancement and contribution to Local service delivery and Local development | Output Indicator 1: Number of reports | 4 | 4 | 4 | 4 | 4 | District; LLGs |
|  | Output 3.3.4: Engage Communities in LR Budget Planning. | Output Indicator 1: Number of budgets formulated | 1 | 1 | 1 | 1 | 1 | District; LLGs |
|  | Output 3.3.5: Procurement of motorcycles | Output Indicator 1: Number of motorcycles procured | 2 | 0 | 0 | 0 | 0 | District |
| Intervention 3.4: Financial Management undertaken | Output 3.4.1: Prepare LG financial reports | Output Indicator 1: Number of financial reports prepared and submitted to relevant authorities | 4 | 4 | 4 | 4 | 4 | District |
| Project 1: N/A | Project Output: N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |

# CHAPTER FOUR: FINANCING FRAMEWORK AND RESOURCE MOBILISATION STRATEGY

## 4.1 Financing Framework

# Table 5: Financing Framework (“000”ushs)

| Source of Financing | Total Contributions FY1 | Total Contributions FY2 | Total Contributions FY3 | Total Contributions FY4 | Total Contributions FY5 | Total Contributions | %age share by source of financing | Off Budget Contribution |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Locally raised revenue | 660,000 | 693,000 | 727,650 | 764,033 | 802,234 | 3,646,917 | 2.1 | 0 |
| Central Government Transfers | 30,557,423 | 32,085,294 | 33,689,559 | 35,374,037 | 37,142,739 | 168,849,052 | 97.4 | 0 |
| Development Partners: |  |  |  |  |  |  |  |  |
| 1.United Nations Children Fund (UNICEF) | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 500,000 |
| 2. Global Fund for HIV, TB & Malaria | 13,363 | 13,363 | 13,363 | 13,363 | 13,364 | 66,817 |  | 250,000 |
| 3. Global Alliance for Vaccines and Immunization (GAVI) | 140,150 | 142,150 | 145,150 | 147,150 | 150,150 | 724,750 |  | 2,500,000 |
| 4. Transformed for Life (Nyamarwa) | 0 | 0 | 0 | 0 | 0 | 0 |  | 1,194,000 |
| 5. St. James Kibbuse Foundation | 0 | 0 | 0 | 0 | 0 | 0 |  | 1,500,000 |
| 6. EMESCO Development Foundation | 0 | 0 | 0 | 0 | 0 | 0 |  | 7,500,000 |
| 7. Hoima CARITAS Development Organisation | 0 | 0 | 0 | 0 | 0 | 0 |  | 866,817 |
| 8. Kitara Civil Society Organization Network. | 0 | 0 | 0 | 0 | 0 | 0 |  | 260,000 |
| 9. Baylor Uganda | 16,574 | 16,574 | 16,574 | 16,574 | 16,574 | 82,870 |  | 2,650,000 |
| 10. LDC Initiative for Effective adaptation and Resilience (LIFE AR) | 0 | 0 | 0 | 0 | 0 | 0 |  | 3,420,000 |
| 11. National Union of Disabled Persons of Uganda (NUDIPU) | 0 | 0 | 0 | 0 | 0 | 0 |  | 320,000 |
| 12. Uganda Rural Development andTraining Programme (URDT) | 0 | 0 | 0 | 0 | 0 | 0 |  | 261,263 |
| 13. Rural People in Action for Development | 0 | 0 | 0 | 0 | 0 | 0 |  | 143,000 |
| Total | 31,387,510 | 32,950,381 | 34,592,296 | 36,315,157 | 38,125,061 | 173,370,406 | 100 | 21,365,080 |

The Total Projected Resource Envelope for the Development Plan is Ushs 194,735,486,000 of which Ushs 173,370,406,000 is projected to be through the District Budget (on-budget) while Ushs 21,365,080,000 is planned to be off-budget contribution from the Development Partners, Civil Society Organisations and the Private Sector. Of the projected on-budget revenue, 97.4% is expected to be received from Central Government Transfers while local revenue and External Financing are expected to contribute 2.1% and 0.5% respectively. Thus, the district will by and large depend on central Government transfers.

## 4.2 Costs of the Plan Period (2025/26-2029/30)

### 4.2.1 Cost Implementation Matrix

## In the cost implementation matrix, the Programme outcomes, outputs and Targets have been costed. The costs are presented annually for all projected sources of funding namely; Government of Uganda, Donor (External Financing), Local Revenue, Non-Governmental Organisations and the Private Sector as per the Cost Implementation Matrix given in Appendix 3 of the Plan.

### 4.2.2  Projected allocation of funds to Programmes

The funds that will be implemented directly through the District Budget are projected to be allocated as per the following Table:

# Table 6: Projected allocation of funds to Programmes for the period 2025/26 to 2029/2030

| Programme | Total amount of on-budget funds allocated ("000" Ushs) | Percentage allocation |
| --- | --- | --- |
| 1. Agro-Industrialization | 25,350,000 | 14.55 |
| 2. Tourism Development | 130,000 | 0.07 |
| 3. Natural Resource, Environment, Climate Change, Land and Water Resources Management | 7,863,226 | 4.51 |
| 4. Private Sector Development | 640,000 | 0.37 |
| 5.Digital Transformation | 236,000 | 0.14 |
| 6. Integrated Transport Infrastructure and Services | 13,476,965 | 7.73 |
| 7.Sustainable Energy Development | 1,050,000 | 0.60 |
| 8. Sustainable Urban and Housing Development | 80,000 | 0.05 |
| 9. Human Capital Development | 98,552,303 | 56.56 |
| 10. Governance and Security | 595,415 | 0.34 |
| 11. Public Sector Transformation | 19,546,942 | 11.73 |
| 12. Development Plan Implementation | 3,085,725 | 1.77 |
| 13. Legislature, Over Sight and Representation | 2,763,830 | 1.59 |
| Total | 173,370,406 | 100 |

The projected resource Envelope for the District Development Plan has been allocated to 13 Programmes adopted from NDP1V. Of the 13 adopted Programmes, the most important programmes for the District over the five years will be Human Capital Development (including Education, Health and Community Based services); Agro-Industrialization; Public Sector Transformation and; Integrated Transport Infrastructure and Services as indicated in Table 6 above.

### 4.2.3 Projected Funding Gap of the Plan

The projected total funding gap for the plan stands Ushs 885,498,000. Most of this funding gap is in the priority programmes namely; Human Capital Development (including Education, Health and Community Based services); Public Sector Transformation; Integrated Transport Infrastructure and Services and, Agro-Industrialization.

## 4.3 Resource mobilisation strategy

### 4.3.1 The Strategies for Resource Mobilisation

In order to actualize the resources required for implementation of the plan, a number of strategies will be used including the following:

- Adherence to reporting requirements set by the central Government and Development Partners: The District and Lower Local Governments will continue to comply with the budgeting and reporting requirements of the Central Government and Development partners in order to continue attracting funds from these institutions.

- Identifying new sources of Local revenue: The District will continue to explore avenues for identifying more sources of local revenue owing to the prevailing rich local revenue potential. This will be done in a consultative process at Lower Local Government and the central Government.

- Promoting Local Economic Development: The District will continue to promote private sector projects for increased employment and revenue generation. It will also sustain investment into its income generating projects like the Forest Plantations, Kibaale Hotel and Kibaale Guest House among others so as to boost local revenue.

- Other Resource mobilisation strategies: These will include; carrying out project proposal writing, improving performance in the Annual Local Government Performance assessment, improving resource-use efficiency, fostering better accountability and transparency, and sustaining high level of funds absorption.

### 4.3.2. Roles and Responsibilities of various actors in Financing of the Plan

| Actors | Roles and Responsibilities |
| --- | --- |
| MoFPED | - Provide conditional Grants to the Local Government on behalf of the central Government. - In conjunction with line Ministries, Departments and Agencies, issue Policy Guidelines for use of conditional grants by the Local Government - Receive annual Budget Framework Papers, Draft Performance contracts, detailed annual budgets and quarterly progress reports - Sign annual Performance contracts with the Accounting Officer of the District Local Government |
| Ministries, Departments and Agencies | - Issue Policy Guidelines for use of conditional grants by the Local Government - Provide other Government transfers to the Local Government - Receive and review work plans and reports from the district |
| District Council | - Approve annual budgets and work plans - Approve new sources of revenue - Lobbying and advocacy for improved funding from the central Government and Development Partners |
| District Chairperson | - Receive quarterly reports from the Local Government Public Accounts Committee and provide synthesis reports to Council - Lobbying and advocacy for improved funding from the central Government and Development Partners |
| Standing Committees | - Review Quarterly progress reports - Propose other sources of revenue for approval by Council |
| District Executive Committee | - Play oversight function on behalf of council - Review quarterly Financial Progress reports - Propose policies for improved revenue collection and management |
| Chief Administrative Officer | - Ensure efficient use of available funds in a transparent and accountable manner |
| District Technical Planning Committee | - Propose policies for improved revenue collection and management for presentation to the District Executive Committee |
| Heads of Department and Section | - Propose new sources of revenue; use of available funds in a transparent and accountable manner |
| Development Partners, CSOs and Private Sector | - Make on- budget and off- budget support towards realisation of the projected resource envelope; Issue Guidelines for access and use of funds under the on- budget support; Avail periodic information on the projects implemented using the off – budget and on- budget support for capture into the Local Government quarterly and annual reports. |
| Media | - Disseminate reports about use of public funds in the Local Government |

# CHAPTER FIVE: INSTITUTIONAL ARRANGEMENTS FOR IMPLEMENTING THE PLAN

## 5.1 Implementation Arrangements

- In line with the National Development Plan, a quasi market approach, which includes a mix of government investments in strategic areas and private sector market driven actions, will be pursued. The Private sector will remain the engine of growth and development, while the local Government, in addition to undertaking the facilitating role through the provision of a conducive policy, regulatory and institutional framework, will also actively promote and encourage Local Economic Development and Public – private partnerships in a rational manner. The District will also pursue out ward oriented policies by encouraging investors from outside the district on top of promoting investors within the district.

- In order to bring together all district development stakeholders to achieve common goals and objectives, in line with the National Development Plan, a “business approach” will be adopted in the implementation of the District Development Plan. The fundamental basis of this approach is that successful District development requires the public and private sectors to adhere to the perception of the district as a “corporate” or a “business entity”, jointly owned by both sectors and working in tandem in pursuit of a common vision.

- In order to operationalise the aforementioned concept, several reforms will be implemented including: improving the public service delivery system and deepening and strengthening the consultative machinery between the public and private sectors.

## Institutional  Arrangements

    - Roles of the different institutional structures in the Local Government

The Plan will be implememted within the context of the existing Local Government structures in the district. The following table lists the different institutional structures in the Local Government and their roles.

# Table 7: Roles of the different institutional structures in the Local Government

| S/No | Institution/stakeholder | Key roles/responsibilities |
| --- | --- | --- |
| 1 | District Council | Approval of the LGDP, Annual workplans and Budgets Approval of Ordinances and bye laws to operationalize the Plan Provide oversight for implementation of the LGDP |
| 2 | District Executive Committee | Formulation of Policies for implementation of the LGDP Continuous monitoring of implementation of the District Development Plan |
| 3 | Standing Committees | Scruitinise Policy proposals for LGDP formulation and implementation on behalf of Council Monitoring of implementation of the Plan on behalf of Council |
| 4 | Statutory Boards and Commissions | Handle recruitment and retention of staff on behalf of Council Handle procurement and disposal of assets on behalf of Council Handle Land management on behalf of Council Provide oversight on utilization of public resources on behalf of Council |
| 5 | District Road Committee | Participate in formulation of annual work plans and Budgets for road works Monitoring of road works |
| 6 | Management | Ensure implementation of the approved LGDP |
| 7 | Technical Planning Committee | Ensure coordinated implementation of the District Development Plan by all actors |
| 8 | Budget Desk | Propose allocation of funds to Programmes in line with the approved LGDP |
| 9 | District Statistics Committee | Formulation of the District Annual Statistical Abstract to provide data for monitoring the progress of implementation of the LGDP |
| 10 | School Management committees and Boards of Governors | Approval of School Budgets and workplans Oversee the implementation of School Budgets and workplans on behalf of the District and Ministry of Education and Sports |
| 11 | Health Unit Management Committees, | Approval of Health Unit Budgets and workplans Oversee the implementation of Health Unit Budgets and workplans on behalf of the District and Ministry of Health |
| 12 | Water user committees | Ensure ownership and sustainability of water facilities |
| 13 | Physical Planning Committees | Ensure proper physical Planning in rural and urban areas for sustainable housing and urban Development |
| 14 | Parish Development Committees | Responsible for coordination of all Development interventions in the Parish e.g. the Parish Development Model |
| 15 | Councils and Committees for Special Interest Groups (Women, Youths, PWDs, Elderly and Child Protection Committees) | Planning, implementation and oversight for interventions and affirmative action for special interest groups |
| 16 | HIV/AIDS Coordination committees | Coordination and oversight of HIV/AIDS interventions in line with the LGDP |
| 17 | Local Environment Committees | Coordination and oversight of Environment interventions in line with the LGDP |
| 18 | Local Revenue Enumeration and assessment Committees | Conduct realistic enumeration and assessment of local revenue to implement the LGDP |
| 19 | Nutrition Coordination committees | Coordination and oversight of Nutrition interventions in line with the LGDP |
| 20 | Disaster Preparedness and Management Committees | Formulation of Disaster Preparedness and Management Plans Coordinate emergency response in the event of disasters in liason with Office of The Prime Minister and other State and Non state Actors |

    - Role of other Key Stakeholders

- There are external stakeholders who will also play a role in implementing the LGDP. The following table lists the other key stakeholders and their key roles in the implementation of the Plan.

# Table 8: Other key stakeholders/ central Government institutions and their key roles

| S/No | Institution/stakeholder | Key roles/responsibilities |
| --- | --- | --- |
| 1 | National Planning Authority | Monitoring effectiveness of Programme Implemetation Action Plans and strategic plans through issuance of Certificate of Compliancy. |
| 2 | Office of the President | Take overall leadership and oversight of implementation of the NDP to ensure its attainment. Timely communication of cabinet decisions Mobilizing the population towards achievement of the plan |
| 3 | Office of the Prime Minister | Offering leadership to the programmes Coordination of overall implementation and monitoring |
| 4 | Ministry of Finance, Planning and Economic Development | Providing financial resources Providing technical guidance and mentoring on budgeting for implementation of plans and budgets Monitoring utilization of resources disbursed for strategic plan implementation |
| 5 | Uganda Bureau of Statistics | Providing reliable data for planning, Giving technical advice and capacity building in data collection and management |
| 6 | Development Partners | Provide technical support to MDAs in planning and implementation of plan interventions Providing Financial resources Integrating some aspects of the plans into their programming. |
| 7 | Lower Local Governments | Providing input into the LGDP Aligning their plans to the LGDP Implementing relevant aspects of the LGDP. |
| 8 | Civil society and private sector organizations | Participating in Programme Working Group activities as co-opted members Providing information about their on-going and planned development activities to the LG for input into the strategic plans Contributing to the implementation of the LGDP Participating in Monitoring and Evaluation of LGDP. |

## 5.3 Coordination and Partnerships Framework

The District will continue coordinating the efforts of all actors in the implementation of the Development Plan. This will ensure that there is no duplication of interventions by the various actors. The LGDP implementation will take advantage of the following platforms for enhanced coordination and Partnership:

5.3.1 Kitara Civil Society Organisation Network

This is the umbrella body for all Civil Society Organisations operating in the District. All Civil Society Organisations will on an basis during the Plan horizon be required to share their workplans and Budgets with the District to confirm alignment with the LGDP, integration into District Annual workplan and budget and to avoid duplication of efforts.

5.3.2 District Budget Conference

This is an annual event during which the various stakeholders including state and non state actors meet to review the progress of implementation of the interventions by various players and to consult about the proposals for the Budget and Workplan of the ensuing Financial Year. This platform will continue to be one of the avenues for strengthening coordination and partnership with the various actors in the District.

5.3.3 Monthly District Technical Planning Committee meetings

This is a platform that is attended by all Heads of Department, representatives of Lower Local Governments, Civil Society Organisations and the Private Sector. Its main role is to initiate workplans and budgets in line with the LGDP, monitor and evaluate implementation of the interventions by the various actors with a view of avoiding duplication of interventions. This plaform shall continue to apply during the LGDP horizon.

5.3.4 Periodic Coordination meetings on Thematic Areas

There also platofrms for periodic coordination meetings on thematic areas like HIV/AIDS, Nutrition, Environment and Gender among others. These meetings attract State and non state stakeholders who are actors in the specific thematic areas and they usually meet on a Quartelry basis for instance the District HIV/AIDS Coordination Committee. Such platforms shall continue to anchor coordination and partnership efforts for LGDP implementation in the district.

5.3.5 Monthly Departmental meetings

Every department will hold monthly meetings to discuss the progress of implementation of the annual work plans that will have been obtained from the District Development Plan. These meetings will be held within the first week of the month and will be attended by all staff members within the department. The minutes of this meeting will be shared with the Chief Administrative Officer by every 7th of the month for prompt follow up of the recommendations made.

5.3.6 Monthly District Executive Committee meetings

The District Executive Committee meetings will continue sitting monthly. During these meetings, the Chief Administrative Officer will present the consolidated monthly briefs showing activities implemented in the district by all stakeholders during the previous month. The monthly briefs will also indicate the cumulative achievements by all stakeholders during the course of the Financial Year.

5.3.7 Quarterly Standing Committee meetings

The District will continue holding quarterly standing committee meetings for consideration of integrated progress reports from departments. These reports will also indicate the cumulative progress by the department during the course of the Financial Year in line with the annual work plan.

5.3.8 District Council meetings

The District Council will continue to sit at least once a quarter. During the Council sessions, the Chairpersons of the Standing Committees will present recommendations regarding improved implementation and coordination of the annual work plans derived from the District Development Plan. The Council will continue to be attended by the various stakeholders including state and non state actors.

## Pre-Requisites for Successful Implementation of the Plan

5.4.1 Continuous Capacity Building of staff

There is need for continuous capacity building of staff in order to match with the contemporary requirements for improved service delivery in the district. However, this will call for formulation of a comprehensive district capacity building Strategy for the medium term and preparation of annual Capacity Building Plans to operationalize it.

5.4.2 Team Work

The district will continue to promote team work among all players for example team work within the programmes, team work between programmes, team work between the technical and Political Leadership, team work between the district and Lower Local Governments, and, team work between the district and Civil Society organizations and Private Sector.

5.4.3 Sustained coordination between actors

The District will continue coordinating the efforts of all actors in the implementation of the Development Plan. This will ensure that there is no duplication of interventions by the various actors.

5.4.4 Sustaining the Existing Peace and unity in the District

There is need for all players to ensure that the peace and unity prevailing in the district is sustained without which no development can be realized. The District will continue to ensure that the existing peace and unity are sustained. The District will also promote civil society efforts for promotion of peace and unity in the district.

## 5.5 Conditions for successful implementation

5.5.1 Sustained funding from the Central Government

Over 90% of the Development plan will be financed by the central Government Transfers. The District will fulfill the Local Government obligations for accessing the central Government transfers for example timely reporting and accountability for the funds received, adherence to the conditions related to specific grants like School Facilities Grant and, timely procurement of goods, services and works

5.5.2 Enhanced Local Revenue collection

The District intends to boost local collection through implementation of the Local Revenue Enhancement Plan for the period 2020/2021 to 2024/2025. Improved local revenue collection will enable the district implement the local needs that are neither funded by the Central Government nor the Development Partners.

5.5.3 Partnership with other players

The District will continue to provide a conducive environment for other players like the Civil Society Organisations and the private sector in order to complement district efforts in the delivery of the District Development Plan aspirations.

# CHAPTER SIX: COMMUNICATION AND FEEDBACK STRATEGY

## 6.1 Communication Strategy

### 6.1.1 Purpose of the Communication Strategy

- Dissemination of local government programmes/ projects and their progress reports to inform/create awareness amongst the local government population.

- Creation of awareness on the expected roles of the stakeholders in the implementation of the local government programmes, including LLGs, CSO, and community members

- Effective management of people’s expectations with regard to public services of the local government.

- Strengthening the relationships between the people involved in the planning, implementation and Monitoring and Evaluation processes.

- Strengthening public ownership of the LG plans

- Enhance accountability and transparency in the implementation of the LG plans.

### 6.1.2 Target Audiences

- Central Government

The Local Government Development Plan is a tool for operationalisation and domestication of the NDP. Through quarterly and annual reports to the centre, the district will be responsible for reporting on progress of and achievement of planned outputs. This will involve reporting on the process of implementation focusing on implementation challenges/constraints with possible recommendations for improved performance.

- District Local Government

Quarterly and annual reports will be presented to and discussed by the DTPC meetings, DEC meetings, Standing Committee meetings and the District Local Council. Annual reviews will also be organized at the district level.

- Lower Local Governments

Progress reports will be shared with LLGs. LLG representatives will also be invited to participate in the annual review meetings at the district level. Quarterly coordination meetings for some programmes like PDM, Emyooga, UWEP, YLP, etc will also be organized at the district level and will also attract LLG representatives. These reviews will feed into quarterly and annual progress reports.

- Civil Society Organisations and other Development Partners

The CSOs and other Development Partners operating in the district are involved in activities that contribute towards the achievement of the set goals and objectives of the plan. Therefore, the communication strategy seeks to strengthen partnerships with CSOs and other Development Partners in the district. CSOs and other Development Partners will be required to make monthly briefs to DTPC meetings and to submit quarterly and annual reports to the district for integration into the district progress report. Similarly, the district will be sharing consolidated reports with the CSOs and other Development Partners.

- The Media

The media are both a target audience and a channel of communication. Both electronic and print media will be utilized in order to lead to dissemination of information regarding progress of implementation of the LGDP to the public and other stakeholders. The Local FM Stations like Karuguuza Development Radio, Kagadi Kibaale Community Radio, Emambya FM, Kakumiro FM, etc will be very instrumental in this endeavour.

- The Community

These are the primary beneficiaries of the interventions reflected in the Plan. A package of communication channels will be used to reach out to the community on regular basis to update them on the progress of the Plan implementation and the roles of the various stakeholders in the implementation, monitoring and evaluation of the plan.

### 6.1.3 Information dissemination channels

A multi media approach will be used to disseminate the information. The choice of the communication channel and message theme will be determined by the target audience and their role. The following channels will be used:

- Briefs (weekly and monthly)

- Progress reports (quarterly, annual and midterm)

- Meetings (monthly, quarterly, annual and midterm)

- Radio programmes (e.g. live talk shows that induce feedback from the listeners)

- Workshops

- Website

- Social media Platforms

- Email

- News Paper Pull out

- Press conferences and Press briefing

- Barazas

- Television programmes

- Bulletin

- Quarterly News Letters

- Brochures

### 6.1.4 Review of information communication channels

There will be annual reviews of the dissemination channels whose findings will be used to inform the revision of the strategy to make it more appropriate for the implementation of the LGDP.

## 6.2 Feedback Mechanism

6.2.1 Purpose of the Feedback Mechanism

In order to ensure effective communication with the various stakeholders, the District will adapt a robust feedback mechanism. The feedback mechanism will be useful for implementation of the LGDP in the following ways:

- Assessing progress of the LGDP from the stakeholders’ lense, as well as offering lessons for development and informing decision-making.

- Sharing experiences and information between the recipients of the LGDP interventions and the District Local Government, other implementing agencies and Development Partners.

- It will provide a channel to amplify voices of the beneficiaries to the District Local Government, other implementing agencies and Development Partners.

- It will provide an opportunity for improvement of LGDP performance through learning from the stakeholder feedack.

6.2.2 Feedback Channels

Feedback will be collected through a diverse range of channels either solicited or unsolicited by the District Local Government, other implementing agencies, Development Partners and the Private Sector. The feedback channels will include meetings, workshops, group discussions, Budget Conferences, field visits, social media, reviews/evaluations, Barazas, call-in Radio Programmes (Live talk shows) among others.

6.2.3 Anticipated Feedback

During implementation of the LGDP, the District will be open to any form of feedback whether positive or negative. The following feedback is anticipated from the various stakeholders:

- Response: The stakeholders may respond to the information shared by the District Local Government, other implementing agencies, Development Partners and the Private Sector.

- Opinion: The stakeholders may express their views about the LGDP implementation whether it is on course or otherwise.

- Idea: The stakeholders may make suggestions for improvement of LGDP implementation to the District Local Government, other implementing agencies, Development Partners and the Private Sector.

- Comment: The stakeholders may make remark or observation regarding the implementation of the LGDP.

- Advice: The stakeholders may give guidance for improvement of LGDP implementation to the District Local Government, other implementing agencies, Development Partners and the Private Sector.

- Result: The stakeholders may conduct and share their independent evaluation regarding the performance of the LGDP i.e. whether it is on –truck, off-truck, behind schedule or on-schedule. This will also include Assessment Reports from MDAs for instance the Local Government Management and Service Delivery Assessment conducted by OPM, Certificate of Compliance Assessment by NPA, Gender and Equity Compliance Assessment by Equal Opportunities Commission among others. The results from these assessments will be taken in good faith and used as an avenue for continuous improvement.

- Rating: The stakeholders will be at liberty to conduct and share their independent evaluation and ranking regarding the performance of the LGDP in relation to other Local Governments within the sub region and the country at large. This ranking will be valuable to the District in estimating its performance in relation to other Local Governments with a view of improving performance of LGDP results.

# CHAPTER SEVEN: RISK MANAGEMENT AND MITIGATION

## 7.1 Risk Management and Anticipated Impacts

The District is exposed to a variety of risks related to development and implementation of the LGDP thus hindering fulfilment of the strategic objectives. Therefore, the district has designed its risk management strategy to effectively ensure that the LG’s objectives are being achieved. The Risk Assessment was performed based on Impact and Likelihood ratings in line with The Government of Uganda Risk Management Strategy (RMS).

The LGDP identifies, analyses various potential risks and prescribes possible mitigation, continuous monitoring and management measures during the plan period. These will be embedded throughout all the strategic and operational levels and work planning during the implementation of LGDP.

A risk matrix has been used to compile and systematically describe all the risks properly, including how they affect the achievement of the desired objectives as well as potential mitigation measures as per the following Table.

# Table 9: Key Envisaged Risks and mitigation measures

| S/No | Identified Risk | Risk category | Analysis |  |  |  | Mitigation | Lead Actor |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Causes | Likelihood | Impact | Risk rating |  |  |
| 1 | Inadequate funding of planned interventions | Both External and operational | - Dwindling External financing - Reduction of some Central Government Grants - Low local revenue collection | low | moderate | moderate | Steady improvement in local revenue collection | Finance Department |
|  |  |  |  |  |  |  | Periodic monitoring and review of Budget performance | Finance and Planning Departments |
| 2 | Epidemics of crop and livestock Diseases | External | Uncontrollable natural and environmental factors | High | High | High | Improve resilience of farmers to crop and livestock diseases | Production Department |
|  |  |  |  |  |  |  | Undertake Disaster Response and Management Planning | Producion and Planning Departments |
| 3 | Hailstorms | External | Uncontrollable natural and environmental factors | High | High | High | Improve resilience of farmers to Hailstorms | Production Department |
|  |  |  |  |  |  |  | Undertake Disaster Response and Management Planning | Producion and Planning Departments |
| 4 | Prolonged dry spells | External | - Uncontrollable natural and environmental factors - Deforestation - Wetland Degradation | High | High | High | Improve resilience of farmers to prolonged dry spells | Production Department |
|  |  |  |  |  |  |  | Promote afforestation and reforestation | Natural Resources and Production Departments |
|  |  |  |  |  |  |  | Intensify awareneness about wetland and forest conservation | Natural Resources and Production Departments |
|  |  |  |  |  |  |  | Enforcement of environmental laws on sustainale use of forests and wetlands | Police |
|  |  |  |  |  |  |  | Undertake Disaster Response and Management Planning | Producion and Planning Departments |
| 5 | Epidemics of infectious diseases | External | Uncontrollable natural and environmental factors | High | High | High | Improve resilience of the population to the Epidemics | Health and Production Departments |
|  |  |  |  |  |  |  | Undertake Disaster Response and Management Planning | Health and Planning Departments |
| 6 | Road Accidents | Strategic | - Improved road network - Increased traffic - Poor road use | High | moderate | High | Increase community awareness about safe use | Police |
|  |  |  |  |  |  |  | Enforce Road Traffic Rules to reduce occurance of the accidents | Police |
| 7 | Low community participation in Development programmes | Operational/ Preventable | Poor mindset among the community | moderate | moderate | moderate | Step up community mobilization and sensitization programmes for mindset change | Community Department |
|  |  |  |  |  |  |  | Intensify Implementation of Burungi Bwansi Policy | LLGs |

# CHAPTER EIGHT: MONITORING, EVALUATION AND LEARNING

## 8.1 Monitoring and Evaluation (M&E) Frameworks

8.1.1. Objectives of the M&E strategy

The Monitoring and Evaluation (M&E) strategy will enable stakeholders to regularly and systematically track implementation of selected priorities and assess progress of the plan with regard to the agreed objectives and outcomes. The M&E strategy is in line with the NDP M&E Framework for the NDPIV. Specifically, the M&E strategy will help District to ascertain the following;

i Were the planned activities implemented as planned?

ii Were resources availed and used timely as planned?

iii Did the LG achieve what it wanted to achieve i.e.; Implementation of activities resulted

into the planned outputs?

iv Did the outputs result in the expected outcomes?

8.1.2. The LGDP Results Framework

The LGDP has adapted the NDPIV Results Framework. The framework indicates the Level of Results, Description of Results, the indicators that will be measured to track and assess progress, its base year value and the targets for each of the Five years. The LGDP Results Framework is as per Appendix 2 of the Plan.

8.1.3. Reporting Arrangements

The LGDP Results Framework provides for periodic reporting and how it will be done and at what level. These include description of main M&E events including the outputs, period of reporting implementation progress, the key actors; and the reporting and results framework. The M&E outputs will be produced timely and sequentially to enable M&E information inform planning, budgeting and develop corrective actions for a smooth implementation of the Plan.

## 8.2 Monitoring and Evaluation Roles and Responsibilities of Key Actors

Some of the key National and Local Government M&E stakeholders and reporting frameworks to which

the LGDP M&E framework will partake are given in following Table

# Table10: M&E Stakeholders and Reporting Frameworks

| Institution | Framework | Key features |
| --- | --- | --- |
| The National Planning Authority | The National Development Report | The National Development Report is an annual report produced by NPA to provide information on the country’s current development status and the progress made against NDP indicators at all levels of the Plan’s results framework. The report also covers the contribution of non-state actors |
|  | Certificate of Compliance Report (COC) | The certificate of compliance is an annual assessment of the annual budgets to the LGDP/MDA plan and NDP |
| Office of the Prime Minister (OPM) | Government Annual Performance Report | The Government Annual Performance report assesses performance of Government MDAs and Local Governments against key objectives outlined in the National Development Plan, and the medium terms objectives and budget spending across main government MDAs implementing the NDP. |
|  | Annual National Assessment | Annual assessment of minimum conditions and performance measures ascertain local government performance against basic services and functions. The assessment also gauges the level of compliance of local governments to the provisions of the laws and national guidelines. |
| Ministry of Finance, Planning and Economic Development | Budget Monitoring and Accountability Mechanisms | MoFPED has got a Budget Monitoring and Accountability unit that tracks financial flows to MDAs and LGs and monitors inputs, outputs and progress of implementation of government programmes and projects included in annual budgets of government MDAs. |
|  | Performance Contracts (Performance Form B) | Through Performance Contracts, MoFPED obliges all Government Accounting Officers to report against commitments made in the annual Performance contracts. This reporting is quarterly. |
| Ministry of Public Service | Client Charters | The Ministry of Public Service (MoPS) has started the process of developing client charters which define service standards and expectations between public bodies, and between service providers and users. Similar charters have been developed and agreed to by local governments. |
| The District Planning Department | Performance Contracts (Performance Form B) | The District Planning Department coordinates preparation of Annual Performance Contracts (Form Bs) which are commitments signed between the LG Accounting Officer and MoFPED. They are drafted by Heads of Department and consolidated by the District Planning Department through the Programme Budgeting System. They are based on the approved District annual workplan and Budget that is aligned with the LGDP. |
|  | Monthly Progress Reports | The District Planning Department coordinates preparation of Monthly Progress Reports which are discussed in Monthly District Technical Planning Committee meetings and also shared with the District Executive Committee. They are drafted by Heads of Department and consolidated by the District Planning Department. |
|  | Quarterly Budget and Physical Performance Reports | The District Planning Department coordinates preparation of Quarterly Budget and Physical Performance Reports which are submitted by the LG Accounting Officer to MoFPED, MDAs, the District Executive Committee and Council Standing Committees. They are drafted by Heads of Department and consolidated by the District Planning Department through the Programme Budgeting System. |
|  | Quarterly Joint Monitoring Reports | The District Planning Department coordinates preparation of Quarterly Joint Monitoring Reports which are discussed in District Technical Planning Committee and District Executive Committee meetings. |
|  | Annual Mock Assessment Reports | The District Planning Department coordinates preparation of Annual Mock Assessment Reports which are discussed in District Technical Planning Committee and District Executive Committee meetings. This is done in preparation for the National Assessment conducted by OPM. |
|  | Mid- Term Review Report | The District Planning Department coordinates preparation of Mid- Term Review Report to Assess mid-term progress of LGDP projects and programmes to ensure consistency of implementation with overall focus and objectives. It is discussed by the District Technical Planning Committee, District Executive Committee meetings , District Council and also submitted to the NPA. |
|  | End of Term Review Report | The District Planning Department coordinates preparation of End of Term Review Report to Assess final progress of LGDP performance. It is discussed by the District Technical Planning Committee, District Executive Committee meetings , District Council and also submitted to the NPA. |

## 8.3 Major Monitoring and Evaluation Events

8.3.1 Programme/Sub-programme Quarterly Progress reporting

The purpose of Programme/Sub-programme Quarterly Progress reporting will be to document progress of implementation of the annual work plan, the drivers of progress, challenges and recommendations for improving implementation of the Plan. It will be done through preparation of Quarterly Programme Progress reports using the Programme Budgeting system. The Lead Agency will be the LG Programme/Sub-programme Heads and other Key actors will include LLGs, NGOs and Development Partners.

8.3.2 LGDP Annual Performance Review

The purpose of LGDP Annual Performance Review will be to carry out an Internal review of LGDP implementation (Programmes, interventions and projects) pointing out the challenges and recommendations for improving implementation of the Plan. It will be done through preparation of Local Government Annual Performance Report using the Programme Budgeting system. The Lead Agency will be the LG Programme/Sub-programme Heads. Other Key actors will include LLGs, NGOs and Development Partners. It will be done in July/August annually.

8.3.3 Alignment of BFPs and budgets to the LGDP

The Alignment of BFPs and budgets to the LGDP will be preceeded by issuance of the 1st Budget Call Circular to Heads of Programmes/ Sub programmes and LLGs by the Accounting Officer. It will involve preparation of the LG BFP which is aligned to the LGDP. The Lead Agency will be the Accounting Officer and Budget Desk and other Key actors will include MoFPED, NPA, DTPC Members, LLGs, DEC, NGOs, Development Partners and other LG stakeholders. It will be done in October/November annually.

8.3.4 Budgeting and Financial Planning

This will be preceeded by issuance of the 2nd Budget Call Circular to Heads of Programmes/ Sub programmes and LLGs by the Accounting Officer. It will involve preparation of the LG - Annual Budget Estimates, Performance Contracts and Annual Work Plan.  The Lead Agency will be the Accounting Officer and Budget Desk. Other Key actors will include MoFPED, NPA, DTPC Members, LLGs, DEC, NGOs, Development Partners and other LG stakeholders. It will be done in February to May annually.

8.3.5 Statistics Production and use in the LGDP implementation

This will be the basis for the midterm and end of term assessment of the LGDP.  The main outputs for this are Annual Statistical abstracts and Quarterly Progress Reports. The Lead Agency will be the UBOS and MoFPED. Other Key actors will include OPM, NPA, MoFPED, other MDAs as well as LGs. It will be done annually/ quarterly.

8.3.6 Mid -term Evaluation of the Plan

The purpose of Mid -term Evaluation of the Plan will be to Assess mid-term progress of LGDP projects and programmes to ensure consistency of implementation with overall focus and objectives. It will involve preparation of the LGDP mid-term review report and the Lead Agency will be the District. Other Key actors will include NPA, MDAs, MoFPED, OPM, LGs, private sector, CSOs. It will be done in January to June 2028.

8.3.7 End of Term Evaluation of the Plan

This will be the assessment of the end of term evaluation of LGDP including projects and programmes. It will involve preparation of the LGDP End evaluation report and the Lead Agency will be the District. Other Key actors will include MDAs, MoFPED, OPM, LGs, private sector, CSOs. It will be done in June 2030.